## ProjectSchedule (hidden)
PRIMARY REFORMER ERECTION SCHEDULE
|  | EQUIPMENT INSTALLATION WORKS | [5 empty] | 2021 | [97 empty] | 2022 | [364 empty] | 2023
insulation WORKS
| *Schedule is based on the latest delivery schedule submitted by TCM on the28th FEB 2022 | [6 empty] | 2021-10-01 | [6 empty] | 2021-10-08 | [6 empty] | 2021-10-15 | [6 empty] | 2021-10-22 | [6 empty] | 2021-10-29 | [6 empty] | 2021-11-05 | [6 empty] | 2021-11-12 | [6 empty] | 2021-11-19 | [6 empty] | 2021-11-26 | [6 empty] | 2021-12-03 | [6 empty] | 2021-12-10 | [6 empty] | 2021-12-17 | [6 empty] | 2021-12-24 | [6 empty] | 2021-12-31 | [6 empty] | 2022-01-07 | [6 empty] | 2022-01-14 | [6 empty] | 2022-01-21 | [6 empty] | 2022-01-28 | [6 empty] | 2022-02-04 | [6 empty] | 2022-02-11 | [6 empty] | 2022-02-18 | [6 empty] | 2022-02-25 | [6 empty] | 2022-03-04 | [6 empty] | 2022-03-11 | [6 empty] | 2022-03-18 | [6 empty] | 2022-03-25 | [6 empty] | 2022-04-01 | [6 empty] | 2022-04-08 | [6 empty] | 2022-04-15 | [6 empty] | 2022-04-22 | [6 empty] | 2022-04-29 | [6 empty] | 2022-05-06 | [6 empty] | 2022-05-13 | [6 empty] | 2022-05-20 | [6 empty] | 2022-05-27 | [6 empty] | 2022-06-03 | [6 empty] | 2022-06-10 | [6 empty] | 2022-06-17 | [6 empty] | 2022-06-24 | [6 empty] | 2022-07-01 | [6 empty] | 2022-07-08 | [6 empty] | 2022-07-15 | [6 empty] | 2022-07-22 | [6 empty] | 2022-07-29 | [6 empty] | 2022-08-05 | [6 empty] | 2022-08-12 | [6 empty] | 2022-08-19 | [6 empty] | 2022-08-26 | [6 empty] | 2022-09-02 | [6 empty] | 2022-09-09 | [6 empty] | 2022-09-16 | [6 empty] | 2022-09-23 | [6 empty] | 2022-09-30 | [6 empty] | 2022-10-07 | [6 empty] | 2022-10-14 | [6 empty] | 2022-10-21 | [6 empty] | 2022-10-28 | [6 empty] | 2022-11-04 | [6 empty] | 2022-11-11 | [6 empty] | 2022-11-18 | [6 empty] | 2022-11-25 | [6 empty] | 2022-12-02 | [6 empty] | 2022-12-09 | [6 empty] | 2022-12-16 | [6 empty] | 2022-12-23 | [6 empty] | 2022-12-30 | [6 empty] | 2023-01-06 | [6 empty] | 2023-01-13 | [6 empty] | 2023-01-20 | [6 empty] | 2023-01-27 | [6 empty] | 2023-02-03 | [6 empty] | 2023-02-10
 | time axis 2021-10-01 to 2023-02-16
|  |  | DELIVERY |  | ERECTION | bar: 2022-11-04 to 2023-02-16
| BLOCK | TASK | START | FINISH | START | FINISH | DAYS | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05
1 | RADIANT SECTION | RADIANT WALLS 1 steel | 2021-11-11 | 2021-11-11 | 2021-12-04 | 2021-12-13 | 9
2 |  | RADIANT WALLS 2 steel | 2021-11-11 | 2021-11-12 | 2021-12-05 | 2022-01-31 | 57
2 |  | RADIANT WALLS 3 steel | 2021-11-12 | 2021-11-12 | 2021-12-14 | 2021-12-15 | 1
2 |  | RADIANT FLOOR steel | 2021-11-11 | 2022-01-04 | 2022-01-18 | 2022-01-27 | 9
1 |  | PLATFORM RADIANT ELEV LEVEL1 +103.765 | 2021-12-15 | 2021-12-20 | 2022-01-28 | 2022-03-22 | 53
2 |  | TEMPORARY SUPPORT STEEL steel | 2021-12-15 | 2022-01-04 | 2022-02-02 | 2022-02-12 | 10
2 |  | STEELWORK STAIRS | 2021-12-08 | 2021-12-16 | 2022-02-09 | 2022-04-12 | 62
2 |  | PLATFORM RADIANT ELEV LEVEL3 +109,665 | 2021-12-15 | 2022-01-04 | 2022-02-13 | 2022-03-25 | 40
|  | RADIANT WALLS 4 steel | 2021-11-11 | 2021-11-11 | 2022-02-14 | 2022-02-17 | 3
1 |  | PLATFORM - TRUSSES +114,659 | 2021-12-08 | 2021-12-16 | 2022-02-19 | 2022-03-05 | 14
2 |  | PLATFORM RADIANT ELEV LEVEL2 +106.040 | 2021-12-15 | 2021-12-15 | 2022-02-20 | 2022-03-23 | 31
2 |  | RADIANT ARCH DUCT steel | 2021-11-01 | 2021-12-16 | 2022-02-25 | 2022-07-15 | 140
|  | RADIANT PENTHOUSE (steel column & bracing) | 2022-03-21 | 2022-03-28 | 2022-03-28 | 2022-04-10 | 13
2 |  | PLATFORM RADIANT ELEV LEVEL4 +116,615 | 2021-12-08 | 2022-01-04 | 2022-04-05 | 2022-07-10 | 96
1 |  | RADIANT HARPS |  |  | 2022-04-21 | 2022-07-16 | 86
2 |  | ARCH DUCT TILES & BURNERS |  |  | 2022-04-25 | 2022-05-05 | 10
|  | RADIANT ARCH DUCT PYROFOLD MODULES 'H' GRADE - 1425°C |  |  | 2022-05-03 | 2022-06-17 | 45
|  | TRANSFER LINE Buble aluminia |  |  | 2022-05-03 | 2022-05-09 | 6
2 |  | RADIANT PENTHOUSE TRUSS assembly | 2022-03-21 | 2022-03-28 | 2022-05-10 | 2022-05-19 | 9
1 |  | ARCH DUCT SUPPORT (temporary steel for transfer l) |  |  | 2022-05-12 | 2022-05-13 | 1
1 |  | TRANSFER LINE | 2022-05-20 | 2022-05-27 | 2022-05-15 | 2022-07-04 | 50
2 |  | RISER TRANSITION |  |  | 2022-05-20 | 2022-05-26 | 6
|  | RADIANT PENTHOUSE TRUSS erection | 2022-03-21 | 2022-03-28 | 2022-05-20 | 2022-07-16 | 57
2 |  | RISER TRANSITION Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-27 | 2022-06-07 | 11
2 |  | OUTLET MANIFOLD Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-27 | 2022-06-02 | 6
1 |  | OUTLET MANIFOLD |  |  | 2022-06-05 | 2022-07-01 | 26
1 |  | PENTHOUSE SIDING | 2022-03-21 | 2022-03-28 | 2022-07-01 | 2022-07-10 | 9
1 |  | RADIANT HARP SUPPORT (steel in ph truss for hangers) | 2022-03-21 | 2022-03-28 | 2022-07-02 | 2022-07-10 | 8
1 |  | SPRING HANGERS FOR TRANSFER LINES | 2022-03-01 | 2022-03-08 | 2022-07-02 | 2022-07-04 | 2
1 |  | INLET MANIFOLD |  |  | 2022-07-02 | 2022-07-15 | 13
1 |  | SPRING HANGERS FOR RADIANT COILS | 2022-03-01 | 2022-03-08 | 2022-07-02 | 2022-07-15 | 13
2 |  | PENTHOUSE TRUSS REMOVABLE | 2022-03-21 | 2022-03-28 | 2022-07-02 | 2022-07-15 | 13
2 |  | PENTHOUSE MONITOR | 2022-03-21 | 2022-03-28 | 2022-07-03 | 2022-07-13 | 10
2 |  | PENTHOUSE ROOFING | 2022-03-21 | 2022-03-28 | 2022-07-10 | 2022-08-10 | 31
1 |  | TUNEL BURNERS DUCTS | 2022-06-15 | 2022-06-22 | 2022-07-10 | 2022-08-01 | 22
1 |  | PENTHOUSE LOUVER | 2022-03-21 | 2022-03-28 | 2022-07-11 | 2022-07-26 | 15
2 |  | RADIANT ARCH DUCT Ceramic Fiber Blanket |  |  | 2022-07-13 | 2022-07-20 | 7
2 |  | RADIANT ARCH DUCT Insulating Board type Ceraboard 115 - 1400° C |  |  | 2022-07-13 | 2022-07-20 | 7
1 |  | PLATFORM RADIANT ELEV LEVEL5 +119,120 |  |  | 2022-07-14 | 2022-07-21 | 7
1 |  | PENTHOUSE PLATFORMS | 2022-03-21 | 2022-03-28 | 2022-07-15 | 2022-08-01 | 17
1 |  | RADIANT WALLS 1 Scaffold instalation |  |  | 2022-07-16 | 2022-07-26 | 10
2 |  | RADIANT WALLS 1 Bituminous coating |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 1 Ceramic fiber blanket |  |  | 2022-07-16 | 2022-07-26 | 10
2 |  | RADIANT WALLS 2 Scaffold instalation |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 2 Bituminous coating |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 2 Ceramic Fiber Blanket |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 3 Scaffold instalation |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 3 Bituminous coating |  |  | 2022-07-16 | 2022-07-26 | 10
|  | RADIANT WALLS 3 Ceramic Fiber Blanket |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 4 Scaffold instalation |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 4 Bituminous coating |  |  | 2022-07-16 | 2022-07-26 | 10
1 |  | RADIANT WALLS 4 Ceramic Fiber Blanket |  |  | 2022-07-16 | 2022-07-26 | 10
2 |  | RADIANT HARPS (catalyst tube) Rockwool PROROX PS 960 |  |  | 2022-07-16 | 2022-07-19 | 3
1 |  | RADIANT HARPS (catalyst tube) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-16 | 2022-07-22 | 6
2 |  | INLET MANIFOLD Ceramic Fiber Blanket |  |  | 2022-07-16 | 2022-07-18 | 2
1 |  | PENTHOUSE FANS | 2022-02-06 | 2022-02-21 | 2022-07-20 | 2022-07-30 | 10
1 |  | RADIANT WALLS 1 PYROBLOC MODULES |  |  | 2022-07-26 | 2022-08-26 | 31
1 |  | RADIANT WALLS 2 PYROBLOC MODULES |  |  | 2022-07-26 | 2022-08-26 | 31
1 |  | RADIANT WALLS 3 PYROBLOC MODULES |  |  | 2022-07-26 | 2022-08-26 | 31
1 |  | RADIANT WALLS 4 PYROBLOC MODULES |  |  | 2022-07-26 | 2022-08-26 | 31
1 |  | PIGITAILS | 2022-03-01 | 2022-03-08 | 2022-08-01 | 2022-10-01 | 61
1 |  | TUNEL BURNERS |  |  | 2022-08-01 | 2022-08-10 | 9
1 |  | RADIANT ARCH SEALS | 2021-12-15 | 2022-03-21 | 2022-08-04 | 2022-09-04 | 31
2 |  | Ceramic Fiber Blanket |  |  | 2022-08-20 | 2022-09-03 | 14
1 |  | High Duty Fire Brick |  |  | 2022-08-26 | 2022-10-15 | 50
2 |  | PIGITAILS Ceramic Fiber Blanket |  |  | 2022-10-01 | 2022-10-06 | 5
1 |  | RADIANT ARCH SEALS CERAMIC HT GLASS FIBRE CLOTH - 1260°C |  |  | 2022-10-01 | 2022-10-06 | 5
2 |  | TUNEL BURNERS DUCTS insualation |  |  | 2022-10-01 | 2022-10-10 | 9
1 |  | Fiber Board Superwool |  |  | 2022-10-15 | 2022-10-22 | 7
2 |  | CONVECTION MODULE 1 | 2022-03-21 | 2022-03-28 | 2022-03-31 | 2022-04-02 | 2
2 |  | CONVECTION MODULE 1 Insulating Fiber Board Superwool Plus 1100 - T=1100°C |  |  | 2022-04-03 | 2022-04-16 | 13
2 |  | CONVECTION MODULE 1 Insulating Fiber Board Superwool Plus Blok 1100 - T=1100°C |  |  | 2022-04-03 | 2022-04-16 | 13
2 |  | CONVECTION MODULE 1 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-04-03 | 2022-04-16 | 13
|  | CONVECTION MODULE 1 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-03 | 2022-04-16 | 13
1 |  | CONVECTION MODULE 2 | 2021-12-18 | 2021-12-19 | 2022-04-03 | 2022-04-04 | 1
1 |  | CONVECTION MODULE 3 | 2022-03-21 | 2022-03-28 | 2022-04-05 | 2022-04-08 | 3
2 |  | CONVECTION MODULE 3 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-04-08 | 2022-04-24 | 16
2 |  | CONVECTION MODULE 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-08 | 2022-04-24 | 16
|  | CONVECTION MODULE 3 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-08 | 2022-04-24 | 16
2 |  | CONVECTION MODULE 3 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-04-08 | 2022-04-24 | 16
1 |  | CONVECTION MODULE 3 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-04-08 | 2022-04-24 | 16
1 |  | CONVECTION MODULE 4 | 2021-12-21 | 2021-12-22 | 2022-04-09 | 2022-04-10 | 1
2 |  | CONVECTION MODULE 5 | 2022-03-21 | 2022-03-28 | 2022-04-11 | 2022-04-12 | 1
2 |  | HEADER BOX CONVECTION EXTERNAL |  |  | 2022-04-13 | 2022-04-16 | 3
2 |  | RADIANT TO CONVECTION TRUSS | 2022-03-21 | 2022-03-28 | 2022-04-13 | 2022-04-17 | 4
2 |  | CONVECTION MODULE 6 | 2022-03-21 | 2022-03-28 | 2022-04-13 | 2022-04-16 | 3
2 |  | TRANSITION DUCTS Insulating Fiber Board Superwool Plus Blok 1100 - T=1100°C |  |  | 2022-04-14 | 2022-04-24 | 10
1 |  | TRANSITION DUCTS Insulating Castable Medium weight Firelite LW |  |  | 2022-04-14 | 2022-04-24 | 10
1 |  | TRANSITION DUCTS Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-14 | 2022-04-24 | 10
|  | CONVECTION MODULE 7 | 2021-12-18 | 2021-12-28 | 2022-04-17 | 2022-04-18 | 1
|  | CROSSOVERS |  |  | 2022-04-19 | 2022-07-18 | 90
|  | CONVECTION MODULE 8 | 2022-03-21 | 2022-03-28 | 2022-04-19 | 2022-04-23 | 4
|  | TRANSITION DUCT |  |  | 2022-04-20 | 2022-04-29
|  | TRANSITION DUCTS PYROFOLD MODULES 'H' GRADE - 1425°C |  |  | 2022-04-24 | 2022-04-27 | 3
|  | CONVECTION MODULE 9 | 2022-03-21 | 2022-03-28 | 2022-04-24 | 2022-04-27 | 3
|  | CONVECTION MODULE 10 | 2021-12-18 | 2021-12-28 | 2022-04-28 | 2022-04-29 | 1
|  | CONVECTION MODULE 11 | 2021-12-18 | 2021-12-28 | 2022-04-30 | 2022-05-01 | 1
|  | TRANSITION DUCTS PLATFORMS | 2022-03-21 | 2022-03-28 | 2022-05-01 | 2022-05-15 | 14
|  | CONVECTION BREECHING | 2021-12-18 | 2021-12-28 | 2022-05-03 | 2022-05-15 | 12
|  | HEADER BOX CONVECTION EXTERNAL Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-06 | 2022-05-10 | 4
|  | HEADER BOX CONVECTION EXTERNAL Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-05-06 | 2022-05-10 | 4
|  | CROSSOVERS Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-11 | 2022-05-14 | 3
|  | CONVECTION MODULE 6 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-11 | 2022-05-25
|  | CONVECTION MODULE 6 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-11 | 2022-05-25
|  | CONVECTION MODULE 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-11 | 2022-05-25
|  | CONVECTION MODULE 6 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-11 | 2022-05-25
|  | CONVECTION MODULE 6 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-05-11 | 2022-05-25
|  | HEADER BOX CONVECTION EXTERNAL Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-11 | 2022-05-21 | 10
|  | HEADER BOX CONVECTION EXTERNAL FIBRE GLASS CLOTH - Waterproof |  |  | 2022-05-11 | 2022-05-12 | 1
|  | HEADER BOX CONVECTION EXTERNAL Insulating Ceramic Fiber Paper KAOWOOL 2000 PAPER - 1260°C |  |  | 2022-05-11 | 2022-05-14 | 3
|  | CONVECTION MODULE 8 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-11 | 2022-05-25 | 14
|  | CONVECTION MODULE 8 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-11 | 2022-05-25 | 14
|  | CONVECTION MODULE 8 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-11 | 2022-05-25 | 14
|  | CONVECTION MODULE 8 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-05-11 | 2022-05-25 | 14
|  | PLATFORM CONVECTION ELEV LEVEL1 | 2022-03-21 | 2022-03-28 | 2022-05-17 | 2022-05-27 | 10
|  | HOT AIR DUCT SUPPORT (steel on top of convection) | 2022-03-21 | 2022-03-28 | 2022-05-17 | 2022-05-27 | 10
|  | PLATFORM CONVECTION ELEV LEVEL3 | 2022-03-21 | 2022-03-28 | 2022-05-23 | 2022-05-28 | 5
|  | CONVECTION MODULE 9 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-25 | 2022-06-07 | 13
|  | CONVECTION MODULE 9 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-25 | 2022-06-07 | 13
|  | CONVECTION MODULE 9 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-25 | 2022-06-07 | 13
|  | CONVECTION BREECHING Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-05-25 | 2022-06-10 | 16
|  | CONVECTION BREECHING Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-25 | 2022-06-10 | 16
|  | CONVECTION BREECHING Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-25 | 2022-06-10 | 16
|  | CONVECTION BREECHING Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-25 | 2022-06-10 | 16
|  | CONVECTION BREECHING PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-05-25 | 2022-06-10 | 16
|  | PLATFORM CONVECTION ELEV LEVEL4 | 2022-03-21 | 2022-03-28 | 2022-05-25 | 2022-06-10 | 16
|  | SUPERHEATERS AIR DUCT 1 insualation |  |  | 2022-05-25 | 2022-06-05 | 11
|  | PLATFORM CONVECTION ELEV LEVEL5 | 2022-03-21 | 2022-03-28 | 2022-06-01 | 2022-06-21 | 20
|  | PLATFORM CONVECTION ELEV LEVEL2 | 2022-03-21 | 2022-03-28 | 2022-06-06 | 2022-06-08 | 2
|  | SUPERHEATERS AIR DUCT 1 assembly |  |  | 2022-06-06 | 2022-06-08 | 2
|  | SUPERHEATERS AIR DUCT 2 insualation |  |  | 2022-06-06 | 2022-06-16 | 10
|  | HEADER BOX CONVECTION EXTERNAL |  |  | 2022-06-07 | 2022-06-14
|  | SUPERHEATERS AIR DUCT 1 erection |  |  | 2022-06-09 | 2022-06-10 | 1
|  | PLATFORM CONVECTION ELEV LEVEL6 | 2022-03-21 | 2022-03-28 | 2022-06-10 | 2022-06-20 | 10
|  | CONVECTION AIR DUCTS downwards 1 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-06-15 | 2022-06-20 | 5
|  | CONVECTION AIR DUCTS downwards 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-15 | 2022-06-20 | 5
|  | PLATFORM CONVECTION ELEV LEVEL7 | 2022-03-21 | 2022-03-28 | 2022-06-15 | 2022-06-20 | 5
|  | EXPANSION JOINTS |  |  | 2022-06-15 | 2022-06-29 | 14
|  | DAMPERS |  |  | 2022-06-15 | 2022-06-29
|  | SUPERHEATERS AIR DUCT 2 assembly |  |  | 2022-06-17 | 2022-06-19 | 2
|  | CONVECTION AIR DUCTS 2 downwards Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-18 | 2022-06-23 | 5
|  | CONVECTION AIR DUCTS 2 downwards Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-18 | 2022-06-23 | 5
|  | CONVECTION AIR DUCT downwards 1 assembly (bottom) | 2022-06-15 | 2022-06-22 | 2022-06-20 | 2022-06-23 | 3
|  | PLATFORM CONVECTION ELEV LEVEL8 | 2022-03-21 | 2022-03-28 | 2022-06-20 | 2022-06-26 | 6
|  | SUPERHEATERS AIR DUCT 2 erection |  |  | 2022-06-20 | 2022-06-21 | 1
|  | CONVECTION AIR DUCTS downwards 3 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-21 | 2022-06-26 | 5
|  | CONVECTION AIR DUCTS downwards 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-21 | 2022-06-26 | 5
|  | CONVECTION AIR DUCTS downwards 1 erection | 2022-06-15 | 2022-06-22 | 2022-06-24 | 2022-06-25 | 1
|  | CONVECTION AIR DUCT downwards 2 assembly (bottom) | 2022-06-15 | 2022-06-22 | 2022-06-24 | 2022-06-27 | 3
|  | CONVECTION AIR DUCT downwards 4 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-24 | 2022-06-29 | 5
|  | CONVECTION AIR DUCT downwards 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-24 | 2022-06-29 | 5
|  | PLATFORM CONVECTION ELEV LEVEL9 | 2022-03-21 | 2022-03-28 | 2022-06-25 | 2022-07-01 | 6
|  | CONVECTION AIR DUCT downwards 5 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-27 | 2022-07-02 | 5
|  | CONVECTION AIR DUCT downwards 5 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-27 | 2022-07-02 | 5
|  | CONVECTION AIR DUCTS downwards 2 erection | 2022-06-15 | 2022-06-22 | 2022-06-28 | 2022-06-29 | 1
|  | CONVECTION AIR DUCT downwards 3 assembly (midle) | 2022-06-15 | 2022-06-22 | 2022-06-28 | 2022-06-30 | 2
|  | CONVECTION AIR DUCTS downwards 3 erection | 2022-06-15 | 2022-06-22 | 2022-06-30 | 2022-07-01 | 1
|  | CONVECTION AIR DUCTS 4 downwards assembly (midle) | 2022-06-15 | 2022-06-22 | 2022-06-30 | 2022-07-02 | 2
|  | CONVECTION AIR DUCT downwards 6 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-30 | 2022-07-05 | 5
|  | CONVECTION AIR DUCT downwards 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-30 | 2022-07-05 | 5
|  | SUPERHEAT BURNERS |  |  | 2022-07-01 | 2022-07-10 | 9
|  | EXPANSION JOINTS |  |  | 2022-07-01 | 2022-07-10 | 9
|  | CONVECTION AIR DUCTS downwards 4 erection | 2022-06-15 | 2022-06-22 | 2022-07-03 | 2022-07-04 | 1
|  | CONVECTION AIR DUCTS 5 downwards assembly (top radius) | 2022-06-15 | 2022-06-22 | 2022-07-03 | 2022-07-05 | 2
|  | DUCT HORIZONTAL L1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-04 | 2022-07-13 | 9
|  | DUCT HORIZONTAL L1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-04 | 2022-07-13 | 9
|  | DUCT HORIZONTAL L2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-04 | 2022-07-13 | 9
|  | DUCT HORIZONTAL L2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-04 | 2022-07-13 | 9
|  | CONVECTION AIR DUCTS downwards 5 erection | 2022-06-15 | 2022-06-22 | 2022-07-06 | 2022-07-07 | 1
|  | CONVECTION AIR DUCTS 6 downwards assembly (top radius) | 2022-06-15 | 2022-06-22 | 2022-07-06 | 2022-07-08 | 2
|  | CONVECTION AIR DUCTS downwards 6 erection | 2022-06-15 | 2022-06-22 | 2022-07-09 | 2022-07-10 | 1
|  | DUCT HORIZONTAL L1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-13 | 2022-07-16 | 3
|  | DUCT HORIZONTAL R1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-13 | 2022-07-22 | 9
|  | DUCT HORIZONTAL R1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-13 | 2022-07-22 | 9
|  | DUCT HORIZONTAL R2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-13 | 2022-07-22 | 9
|  | DUCT HORIZONTAL R2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-13 | 2022-07-22 | 9
|  | DUCT HORIZONTAL L1 erection | 2022-06-15 | 2022-06-22 | 2022-07-17 | 2022-07-18 | 1
|  | DUCT HORIZONTAL L2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-17 | 2022-07-19 | 2
|  | DUCT HORIZONTAL arc L Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-18 | 2022-07-25 | 7
|  | DUCT HORIZONTAL arc L Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-18 | 2022-07-25 | 7
|  | DUCT HORIZONTAL arc R Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-18 | 2022-07-25 | 7
|  | DUCT HORIZONTAL arc R Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-18 | 2022-07-25 | 7
|  | DUCT HORIZONTAL L2 erection | 2022-06-15 | 2022-06-22 | 2022-07-20 | 2022-07-21 | 1
|  | DUCT HORIZONTAL R1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-23 | 2022-07-26 | 3
|  | DUCT HORIZONTAL R1 erection | 2022-06-15 | 2022-06-22 | 2022-07-27 | 2022-07-28 | 1
|  | DUCT HORIZONTAL R2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-27 | 2022-07-29 | 2
|  | DUCT HORIZONTAL R2 erection | 2022-06-15 | 2022-06-22 | 2022-07-30 | 2022-07-31 | 1
|  | DUCT HORIZONTAL arc L assembly | 2022-06-15 | 2022-06-22 | 2022-08-01 | 2022-08-02 | 1
|  | DUCT HORIZONTAL arc L erection | 2022-06-15 | 2022-06-22 | 2022-08-03 | 2022-08-04 | 1
|  | DUCT HORIZONTAL arc R assembly | 2022-06-15 | 2022-06-22 | 2022-08-03 | 2022-08-05 | 2
|  | DUCT HORIZONTAL arc R erection | 2022-06-15 | 2022-06-22 | 2022-08-06 | 2022-08-07 | 1
| APH | CONVECTION TRANSITION DUCTS 1 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-01 | 2022-04-09 | 8
|  | CONVECTION TRANSITION DUCTS 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-01 | 2022-04-09 | 8
|  | CONVECTION TRANSITION DUCTS 2 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-01 | 2022-04-09 | 8
|  | CONVECTION TRANSITION DUCTS 2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-01 | 2022-04-09 | 8
|  | CONVECTION TRANSITION DUCTS 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-09 | 2022-04-16 | 7
|  | CONVECTION TRANSITION DUCTS 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-09 | 2022-04-16 | 7
|  | CONVECTION TRANSITION DUCTS 4 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-09 | 2022-04-16 | 7
|  | CONVECTION TRANSITION DUCTS 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-09 | 2022-04-16 | 7
|  | CONVECTION TRANSITION DUCTS 1 erection |  |  | 2022-05-02 | 2022-05-03 | 1
|  | CONVECTION TRANSITION DUCTS 2 erection |  |  | 2022-05-04 | 2022-05-06 | 2
|  | CONVECTION TRANSITION DUCTS 3 erection |  |  | 2022-05-07 | 2022-05-09 | 2
|  | CONVECTION TRANSITION DUCTS 4 erection |  |  | 2022-05-10 | 2022-05-12 | 2
|  | DUCT UPWARDS L1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-20 | 2022-07-22 | 2
|  | DUCT UPWARDS L2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-22 | 2022-07-24 | 2
|  | DUCT UPWARDS R1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-24 | 2022-07-26 | 2
|  | DUCT UPWARDS R2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-26 | 2022-07-28 | 2
|  | DUCT UPWARDS L1 Insulating Castable Low Iron Firelite 2300 VL | 2022-07-27 | 2022-08-06 | 2022-07-27 | 2022-08-06 | 10
|  | DUCT UPWARDS L1 Ceramic Fiber Blanket CERABLANKET- 1260°C | 2022-07-27 | 2022-08-06 | 2022-07-27 | 2022-08-06 | 10
|  | DUCT UPWARDS L2 Insulating Castable Low Iron Firelite 2300 VL | 2022-08-26 | 2022-09-05 | 2022-07-27 | 2022-08-06 | 10
|  | DUCT UPWARDS L2 Ceramic Fiber Blanket CERABLANKET- 1260°C | 2022-08-26 | 2022-09-05 | 2022-07-27 | 2022-08-06 | 10
|  | DUCT UPWARDS R1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-08-06 | 2022-08-17 | 11
|  | DUCT UPWARDS R1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-08-06 | 2022-08-17 | 11
|  | COMBUSTION HOT AIR DUCTS insualation | 2022-06-15 | 2022-06-22 | 2022-08-14 | 2022-08-25 | 11
|  | DUCT UPWARDS R2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-08-14 | 2022-08-25 | 11
|  | DUCT UPWARDS R2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-08-14 | 2022-08-25 | 11
|  | FLUE GAS DUCT UNDER APH Insulating Castable Lightweight Firelite 124 L |  |  | 2022-08-20 | 2022-08-26 | 6
|  | FLUE GAS DUCT UNDER APH Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-08-20 | 2022-08-26 | 6
|  | FLUE GAS DUCT UNDER APH (hopper/cap) |  |  | 2022-08-27 | 2022-08-28 | 1
|  | APH SUPPORT STRUCTURE |  |  | 2022-08-28 | 2022-08-29 | 1
|  | APH BLOCK 1B |  |  | 2022-08-30 | 2022-08-31 | 1
|  | APH BLOCK 1C |  |  | 2022-08-30 | 2022-08-31 | 1
|  | APH BLOCK 2A |  |  | 2022-09-01 | 2022-09-02 | 1
|  | APH BLOCK 2B |  |  | 2022-09-01 | 2022-09-02 | 1
|  | APH BLOCK 2C |  |  | 2022-09-03 | 2022-09-04 | 1
|  | APH BLOCK 3A |  |  | 2022-09-03 | 2022-09-04 | 1
|  | APH BLOCK 3B |  |  | 2022-09-05 | 2022-09-06 | 1
|  | APH BLOCK 3C |  |  | 2022-09-05 | 2022-09-06 | 1
|  | COMBUSTION HOT AIR DUCTS (top of APH) |  |  | 2022-09-07 | 2022-09-09 | 2
|  | DUCT UPWARDS L1 erection | 2022-06-15 | 2022-06-22 | 2022-09-09 | 2022-09-10 | 1
|  | DUCT UPWARDS L2 L2 erection | 2022-06-15 | 2022-06-22 | 2022-09-09 | 2022-09-10 | 1
|  | EXP JOINTS |  |  | 2022-09-09 | 2022-09-11 | 2
|  | DUCT UPWARDS R1 erection | 2022-06-15 | 2022-06-22 | 2022-09-10 | 2022-09-11 | 1
|  | DUCT UPWARDS R2 L2 erection | 2022-06-15 | 2022-06-22 | 2022-09-10 | 2022-09-11 | 1
| DUCT | FLUE GAS DUCT (bottom panels) Insulating Castable Lightweight Firelite 124 L |  |  | 2022-07-20 | 2022-08-01 | 12
|  | FLUE GAS DUCT (bottom panels) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-20 | 2022-08-01 | 12
|  | FLUE GAS DUCT (side & top panels) Insulating Castable Lightweight Firelite 124 L |  |  | 2022-07-20 | 2022-08-06 | 17
|  | FLUE GAS DUCT (side & top panels) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-20 | 2022-08-06 | 17
|  | FLUE GAS DUCT (bottom panels) erection | 2022-06-15 | 2022-06-22 | 2022-08-01 | 2022-08-04 | 3
|  | STEEL UNDER COLD AIR DUCTS assembly | 2022-06-15 | 2022-06-22 | 2022-08-04 | 2022-08-06 | 2
|  | FLUE GAS DUCT (side & top panels) erection | 2022-06-15 | 2022-06-22 | 2022-08-06 | 2022-08-25 | 19
|  | STEEL UNDER COLD AIR DUCTS erection | 2022-06-15 | 2022-06-22 | 2022-08-07 | 2022-08-08 | 1
|  | COMBUSTION COLD AIR DUCTS 1 assebmbly |  |  | 2022-08-09 | 2022-08-11 | 2
|  | COMBUSTION COLD AIR DUCTS 1 erection |  |  | 2022-08-11 | 2022-08-12 | 1
|  | COMBUSTION COLD AIR DUCTS 2 assembly |  |  | 2022-08-11 | 2022-08-13 | 2
|  | DAMPERS |  |  | 2022-08-11 | 2022-08-23 | 12
|  | EXP JOINTS |  |  | 2022-08-11 | 2022-08-23 | 12
|  | COMBUSTION COLD AIR DUCTS 2 erection |  |  | 2022-08-13 | 2022-08-14 | 1
|  | COMBUSTION COLD AIR DUCTS 3 assembly |  |  | 2022-08-13 | 2022-08-15 | 2
|  | COMBUSTION COLD AIR DUCTS 3 erection |  |  | 2022-08-15 | 2022-08-16 | 1
|  | COMBUSTION COLD AIR DUCTS 4 assembly |  |  | 2022-08-15 | 2022-08-17 | 2
|  | COMBUSTION COLD AIR DUCTS 5 assembly |  |  | 2022-08-17 | 2022-08-19 | 2
|  | COMBUSTION COLD AIR DUCTS 4 erection |  |  | 2022-08-18 | 2022-08-19 | 1
|  | COMBUSTION COLD AIR DUCTS 6 assembly |  |  | 2022-08-19 | 2022-08-21 | 2
|  | COMBUSTION COLD AIR DUCTS 5 erection |  |  | 2022-08-20 | 2022-08-21 | 1
|  | COMBUSTION COLD AIR DUCTS 6 erection |  |  | 2022-08-22 | 2022-08-23 | 1
|  | DUCT PLATFORMS |  |  | 2022-08-23 | 2022-08-28 | 5
| STACK | STACK 1 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-18 | 2022-09-29 | 11
|  | STACK 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-18 | 2022-09-29 | 11
|  | STACK 2 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-18 | 2022-09-29 | 11
|  | STACK 2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-18 | 2022-09-29 | 11
|  | STACK 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-18 | 2022-09-30 | 12
|  | STACK 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-18 | 2022-09-30 | 12
|  | STACK 1 steel assembly TOS =112,300 | 2022-06-15 | 2022-06-22 | 2022-09-29 | 2022-10-01 | 2
|  | STACK 4 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-29 | 2022-10-12 | 13
|  | STACK 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-29 | 2022-10-12 | 13
|  | STACK 5 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-29 | 2022-10-13 | 14
|  | STACK 5 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-29 | 2022-10-13 | 14
|  | STACK 6 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-29 | 2022-10-13 | 14
|  | STACK 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-29 | 2022-10-13 | 14
|  | STACK 2 steel assembly TOS =121,300 | 2022-03-21 | 2022-03-28 | 2022-09-30 | 2022-10-02 | 2
|  | STACK 3 steel assembly TOS =130,300 | 2022-06-15 | 2022-06-22 | 2022-10-01 | 2022-10-04 | 3
|  | STACK 4 steel assembly TOS =139,300 | 2022-06-15 | 2022-06-22 | 2022-10-13 | 2022-10-15 | 2
|  | STACK 5 steel assembly TOS =148,310 | 2022-06-15 | 2022-06-22 | 2022-10-13 | 2022-10-16 | 3
|  | STACK 6 steel assembly TOS =157,000 | 2022-06-15 | 2022-06-22 | 2022-10-14 | 2022-10-17 | 3
|  | STACK 1 erection | 2022-06-15 | 2022-06-22 | 2022-10-18 | 2022-10-19 | 1
|  | STACK 2 erection | 2022-03-21 | 2022-03-28 | 2022-10-19 | 2022-10-20 | 1
|  | STACK 3 erection | 2022-06-15 | 2022-06-22 | 2022-10-20 | 2022-10-21 | 1
|  | STACK 4 erection | 2022-06-15 | 2022-06-22 | 2022-10-21 | 2022-10-22 | 1
|  | STACK 5 erection | 2022-06-15 | 2022-06-22 | 2022-10-22 | 2022-10-23 | 1
|  | STACK 6 erection | 2022-06-15 | 2022-06-22 | 2022-10-23 | 2022-10-24 | 1
| MACHINERY | ID FANS | 2022-02-28 | 2022-03-10 | 2022-03-20 | 2022-04-15 | 26
|  | FD FAN | 2022-06-15 | 2022-06-22 | 2022-07-01 | 2022-07-25 | 24
|  | AIR INTAKE | 2022-06-15 | 2022-06-22 | 2022-07-05 | 2022-07-20 | 15
|  | STEAM TURBINE |  |  | 2022-08-10 | 2022-09-10 | 31
|  | ELECTRIC MOTOR |  |  | 2022-08-10 | 2022-09-10 | 31
|  | LUBE OIL SYSTEM |  |  | 2022-08-10 | 2022-09-10 | 31
|  | SAPH |  |  | 2022-08-15 | 2022-08-16 | 1
|  | INTERCOONNECTING PIPING |  |  |  |  | 0
| SCR | SKID |  |  |  |  | 0
|  | CATALYST |  |  |  |  | 0
Note on C31: Author: In this step also need to place inlet manifolds on top of arch duct, for temporary storage)
Note on D73: Author: John zink hamworthy

## ProjectSchedule (2)
PRIMARY REFORMER ERECTION SCHEDULE
|  | EQUIPMENT INSTALLATION WORKS | [5 empty] | 2021 | [195 empty] | 2022
INSULATION WORKS
| *Schedule is based on the latest delivery schedule submitted by TCM on the28th FEB 2022 | [104 empty] | 2021-10-01 | [6 empty] | 2021-10-08 | [6 empty] | 2021-10-15 | [6 empty] | 2021-10-22 | [6 empty] | 2021-10-29 | [6 empty] | 2021-11-05 | [6 empty] | 2021-11-12 | [6 empty] | 2021-11-19 | [6 empty] | 2021-11-26 | [6 empty] | 2021-12-03 | [6 empty] | 2021-12-10 | [6 empty] | 2021-12-17 | [6 empty] | 2021-12-24 | [6 empty] | 2021-12-31 | [6 empty] | 2022-01-07 | [6 empty] | 2022-01-14 | [6 empty] | 2022-01-21 | [6 empty] | 2022-01-28 | [6 empty] | 2022-02-04 | [6 empty] | 2022-02-11 | [6 empty] | 2022-02-18 | [6 empty] | 2022-02-25 | [6 empty] | 2022-03-04 | [6 empty] | 2022-03-11 | [6 empty] | 2022-03-18 | [6 empty] | 2022-03-25 | [6 empty] | 2022-04-01 | [6 empty] | 2022-04-08 | [6 empty] | 2022-04-15 | [6 empty] | 2022-04-22 | [6 empty] | 2022-04-29 | [6 empty] | 2022-05-06 | [6 empty] | 2022-05-13 | [6 empty] | 2022-05-20 | [6 empty] | 2022-05-27 | [6 empty] | 2022-06-03 | [6 empty] | 2022-06-10 | [6 empty] | 2022-06-17 | [6 empty] | 2022-06-24 | [6 empty] | 2022-07-01 | [6 empty] | 2022-07-08 | [6 empty] | 2022-07-15 | [6 empty] | 2022-07-22 | [6 empty] | 2022-07-29 | [6 empty] | 2022-08-05 | [6 empty] | 2022-08-12 | [6 empty] | 2022-08-19 | [6 empty] | 2022-08-26 | [6 empty] | 2022-09-02 | [6 empty] | 2022-09-09 | [6 empty] | 2022-09-16 | [6 empty] | 2022-09-23 | [6 empty] | 2022-09-30 | [6 empty] | 2022-10-07 | [6 empty] | 2022-10-14 | [6 empty] | 2022-10-21 | [6 empty] | 2022-10-28 | [6 empty] | 2022-11-04 | [6 empty] | 2022-11-11 | [6 empty] | 2022-11-18 | [6 empty] | 2022-11-25 | [6 empty] | 2022-12-02 | [6 empty] | 2022-12-09 | [6 empty] | 2022-12-16 | [6 empty] | 2022-12-23 | [6 empty] | 2022-12-30
 | time axis 2021-10-01 to 2023-04-14
|  |  | DELIVERY |  | ERECTION
| BLOCK | TASK | START | FINISH | START | FINISH | DAYS | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14
1 | RADIANT SECTION | RADIANT WALLS 1 steel | 2021-11-11 | 2021-11-11 | 2021-12-04 | 2021-12-13 | 9
1 |  | RADIANT WALLS 2 steel | 2021-11-11 | 2021-11-12 | 2021-12-05 | 2022-01-31 | 57
1 |  | RADIANT WALLS 3 steel | 2021-11-12 | 2021-11-12 | 2021-12-14 | 2021-12-15 | 1
1 |  | RADIANT FLOOR steel | 2021-11-11 | 2022-01-04 | 2022-01-18 | 2022-01-27 | 9
1 |  | PLATFORM RADIANT ELEV LEVEL1 +103.765 | 2021-12-15 | 2021-12-20 | 2022-01-28 | 2022-03-22 | 53
1 |  | TEMPORARY SUPPORT STEEL steel | 2021-12-15 | 2022-01-04 | 2022-02-02 | 2022-02-12 | 10
1 |  | STEELWORK STAIRS | 2021-12-08 | 2021-12-16 | 2022-02-09 | 2022-04-12 | 62
1 |  | PLATFORM RADIANT ELEV LEVEL3 +109,665 | 2021-12-15 | 2022-01-04 | 2022-02-13 | 2022-03-25 | 40
1 |  | RADIANT WALLS 4 steel | 2021-11-11 | 2021-11-11 | 2022-02-14 | 2022-02-17 | 3
1 |  | PLATFORM - TRUSSES +114,659 | 2021-12-08 | 2021-12-16 | 2022-02-19 | 2022-03-05 | 14
1 |  | PLATFORM RADIANT ELEV LEVEL2 +106.040 | 2021-12-15 | 2021-12-15 | 2022-02-20 | 2022-03-23 | 31
1 |  | RADIANT ARCH DUCT steel | 2021-11-01 | 2021-12-16 | 2022-02-25 | 2022-07-15 | 140
1 |  | RADIANT PENTHOUSE (steel column & bracing) | 2022-03-21 | 2022-03-28 | 2022-03-28 | 2022-04-10 | 13
1 |  | PLATFORM RADIANT ELEV LEVEL4 +116,615 | 2021-12-08 | 2022-01-04 | 2022-04-05 | 2022-07-10 | 96
1 |  | RADIANT HARPS |  |  | 2022-04-21 | 2022-07-16 | 86
1 |  | ARCH DUCT TILES & BURNERS |  |  | 2022-04-25 | 2022-05-05 | 10
1 |  | RADIANT ARCH DUCT PYROFOLD MODULES 'H' GRADE - 1425°C |  |  | 2022-05-03 | 2022-06-17 | 45
1 |  | TRANSFER LINE Buble aluminia |  |  | 2022-05-03 | 2022-05-09 | 6
1 |  | RADIANT PENTHOUSE TRUSS assembly | 2022-03-21 | 2022-03-28 | 2022-05-10 | 2022-05-19 | 9
1 |  | ARCH DUCT SUPPORT (temporary steel for transfer l) |  |  | 2022-05-12 | 2022-05-13 | 1
1 |  | TRANSFER LINE | 2022-05-20 | 2022-05-27 | 2022-05-15 | 2022-07-04 | 50
1 |  | RISER TRANSITION |  |  | 2022-05-20 | 2022-05-26 | 6
1 |  | RADIANT PENTHOUSE TRUSS erection | 2022-03-21 | 2022-03-28 | 2022-05-20 | 2022-07-16 | 57
1 |  | RISER TRANSITION Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-27 | 2022-06-07 | 11
1 |  | OUTLET MANIFOLD Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-27 | 2022-06-02 | 6
1 |  | OUTLET MANIFOLD |  |  | 2022-06-05 | 2022-07-01 | 26
1 |  | PENTHOUSE SIDING | 2022-03-21 | 2022-03-28 | 2022-07-01 | 2022-07-10 | 9
1 |  | RADIANT HARP SUPPORT (steel in ph truss for hangers) | 2022-03-21 | 2022-03-28 | 2022-07-02 | 2022-07-10 | 8
1 |  | SPRING HANGERS FOR TRANSFER LINES | 2022-03-01 | 2022-03-08 | 2022-07-02 | 2022-07-04 | 2
1 |  | INLET MANIFOLD |  |  | 2022-07-02 | 2022-07-15 | 13
1 |  | SPRING HANGERS FOR RADIANT COILS | 2022-03-01 | 2022-03-08 | 2022-07-02 | 2022-07-15 | 13
1 |  | PENTHOUSE TRUSS REMOVABLE | 2022-03-21 | 2022-03-28 | 2022-07-02 | 2022-07-15 | 13
1 |  | PENTHOUSE MONITOR | 2022-03-21 | 2022-03-28 | 2022-07-03 | 2022-07-13 | 10
1 |  | PENTHOUSE ROOFING | 2022-03-21 | 2022-03-28 | 2022-07-10 | 2022-08-10 | 31
1 |  | TUNEL BURNERS DUCTS | 2022-06-15 | 2022-06-22 | 2022-07-10 | 2022-08-01 | 22
1 |  | PENTHOUSE LOUVER | 2022-03-21 | 2022-03-28 | 2022-07-11 | 2022-07-26 | 15
1 |  | RADIANT ARCH DUCT Ceramic Fiber Blanket |  |  | 2022-07-13 | 2022-07-18 | 5
1 |  | RADIANT ARCH DUCT Insulating Board type Ceraboard 115 - 1400° C |  |  | 2022-07-15 | 2022-07-20 | 5
1 |  | PLATFORM RADIANT ELEV LEVEL5 +119,120 |  |  | 2022-07-14 | 2022-07-21 | 7
1 |  | PENTHOUSE PLATFORMS | 2022-03-21 | 2022-03-28 | 2022-07-15 | 2022-08-01 | 17
1 |  | RADIANT WALLS 1 Scaffold instalation |  |  | 2022-07-16 | 2022-07-19 | 3
1 |  | RADIANT WALLS 1 Bituminous coating |  |  | 2022-07-17 | 2022-07-20 | 3
1 |  | RADIANT WALLS 1 Ceramic fiber blanket |  |  | 2022-07-18 | 2022-07-22 | 4
1 |  | RADIANT WALLS 2 Scaffold instalation |  |  | 2022-07-19 | 2022-07-23 | 4
1 |  | RADIANT WALLS 2 Bituminous coating |  |  | 2022-07-20 | 2022-07-24 | 4
1 |  | RADIANT WALLS 2 Ceramic Fiber Blanket |  |  | 2022-07-21 | 2022-07-25 | 4
1 |  | RADIANT WALLS 3 Scaffold instalation |  |  | 2022-07-22 | 2022-07-26 | 4
1 |  | RADIANT WALLS 3 Bituminous coating |  |  | 2022-07-23 | 2022-07-26 | 3
1 |  | RADIANT WALLS 3 Ceramic Fiber Blanket |  |  | 2022-07-24 | 2022-07-26 | 2
1 |  | RADIANT WALLS 4 Scaffold instalation |  |  | 2022-07-20 | 2022-07-26 | 6
1 |  | RADIANT WALLS 4 Bituminous coating |  |  | 2022-07-21 | 2022-07-26 | 5
1 |  | RADIANT WALLS 4 Ceramic Fiber Blanket |  |  | 2022-07-23 | 2022-07-26 | 3
1 |  | RADIANT HARPS (catalyst tube) Rockwool PROROX PS 960 |  |  | 2022-07-16 | 2022-07-19 | 3
1 |  | RADIANT HARPS (catalyst tube) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-16 | 2022-07-22 | 6
1 |  | INLET MANIFOLD Ceramic Fiber Blanket |  |  | 2022-07-16 | 2022-07-18 | 2
1 |  | PENTHOUSE FANS | 2022-02-06 | 2022-02-21 | 2022-07-20 | 2022-07-30 | 10
1 |  | RADIANT WALLS 1 PYROBLOC MODULES |  |  | 2022-07-26 | 2022-08-10 | 15
1 |  | RADIANT WALLS 2 PYROBLOC MODULES |  |  | 2022-08-01 | 2022-08-14 | 13
1 |  | RADIANT WALLS 3 PYROBLOC MODULES |  |  | 2022-08-05 | 2022-08-20 | 15
1 |  | RADIANT WALLS 4 PYROBLOC MODULES |  |  | 2022-08-10 | 2022-08-26 | 16
1 |  | PIGITAILS | 2022-03-01 | 2022-03-08 | 2022-08-01 | 2022-10-01 | 61
1 |  | TUNEL BURNERS |  |  | 2022-08-01 | 2022-08-10 | 9
1 |  | RADIANT ARCH SEALS | 2021-12-15 | 2022-03-21 | 2022-08-04 | 2022-09-04 | 31
1 |  | Ceramic Fiber Blanket |  |  | 2022-08-20 | 2022-09-03 | 14
1 |  | High Duty Fire Brick |  |  | 2022-08-26 | 2022-10-15 | 50
1 |  | PIGITAILS Ceramic Fiber Blanket |  |  | 2022-10-01 | 2022-10-06 | 5
1 |  | RADIANT ARCH SEALS CERAMIC HT GLASS FIBRE CLOTH - 1260°C |  |  | 2022-10-01 | 2022-10-06 | 5
1 |  | TUNEL BURNERS DUCTS insualation |  |  | 2022-10-01 | 2022-10-10 | 9
1 |  | Fiber Board Superwool |  |  | 2022-10-15 | 2022-10-22 | 7
1 | CONVECTION SECTION | CONVECTION MODULE 1 | 2022-03-21 | 2022-03-28 | 2022-03-31 | 2022-04-02 | 2
1 |  | CONVECTION MODULE 1 Insulating Fiber Board Superwool Plus 1100 - T=1100°C |  |  | 2022-04-03 | 2022-04-06 | 3
1 |  | CONVECTION MODULE 1 Insulating Fiber Board Superwool Plus Blok 1100 - T=1100°C |  |  | 2022-04-06 | 2022-04-09 | 3
1 |  | CONVECTION MODULE 1 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-04-09 | 2022-04-12 | 3
1 |  | CONVECTION MODULE 1 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-12 | 2022-04-16 | 4
1 |  | CONVECTION MODULE 2 | 2021-12-18 | 2021-12-19 | 2022-04-03 | 2022-04-04 | 1
1 |  | CONVECTION MODULE 3 | 2022-03-21 | 2022-03-28 | 2022-04-05 | 2022-04-08 | 3
1 |  | CONVECTION MODULE 3 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-04-08 | 2022-04-12 | 4
1 |  | CONVECTION MODULE 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-12 | 2022-04-16 | 4
1 |  | CONVECTION MODULE 3 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-16 | 2022-04-20 | 4
1 |  | CONVECTION MODULE 3 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-04-20 | 2022-04-24 | 4
1 |  | CONVECTION MODULE 3 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-04-21 | 2022-04-24 | 3
1 |  | CONVECTION MODULE 4 | 2021-12-21 | 2021-12-22 | 2022-04-09 | 2022-04-10 | 1
1 |  | CONVECTION MODULE 5 | 2022-03-21 | 2022-03-28 | 2022-04-11 | 2022-04-12 | 1
1 |  | HEADER BOX CONVECTION EXTERNAL |  |  | 2022-04-13 | 2022-04-16 | 3
1 |  | RADIANT TO CONVECTION TRUSS | 2022-03-21 | 2022-03-28 | 2022-04-13 | 2022-04-17 | 4
1 |  | CONVECTION MODULE 6 | 2022-03-21 | 2022-03-28 | 2022-04-13 | 2022-04-16 | 3
1 |  | TRANSITION DUCTS Insulating Fiber Board Superwool Plus Blok 1100 - T=1100°C |  |  | 2022-04-14 | 2022-04-18 | 4
1 |  | TRANSITION DUCTS Insulating Castable Medium weight Firelite LW |  |  | 2022-04-18 | 2022-04-21 | 3
1 |  | TRANSITION DUCTS Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-04-21 | 2022-04-24 | 3
1 |  | CONVECTION MODULE 7 | 2021-12-18 | 2021-12-28 | 2022-04-17 | 2022-04-18 | 1
1 |  | CROSSOVERS |  |  | 2022-04-19 | 2022-07-18 | 90
1 |  | CONVECTION MODULE 8 | 2022-03-21 | 2022-03-28 | 2022-04-19 | 2022-04-23 | 4
1 |  | TRANSITION DUCT |  |  | 2022-04-20 | 2022-04-29 | 9
1 |  | TRANSITION DUCTS PYROFOLD MODULES 'H' GRADE - 1425°C |  |  | 2022-04-24 | 2022-04-27 | 3
1 |  | CONVECTION MODULE 9 | 2022-03-21 | 2022-03-28 | 2022-04-24 | 2022-04-27 | 3
1 |  | CONVECTION MODULE 10 | 2021-12-18 | 2021-12-28 | 2022-04-28 | 2022-04-29 | 1
1 |  | CONVECTION MODULE 11 | 2021-12-18 | 2021-12-28 | 2022-04-30 | 2022-05-01 | 1
1 |  | TRANSITION DUCTS PLATFORMS | 2022-03-21 | 2022-03-28 | 2022-05-01 | 2022-05-15 | 14
1 |  | CONVECTION BREECHING | 2021-12-18 | 2021-12-28 | 2022-05-03 | 2022-05-15 | 12
1 |  | HEADER BOX CONVECTION EXTERNAL Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-06 | 2022-05-08 | 2
1 |  | HEADER BOX CONVECTION EXTERNAL Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-05-08 | 2022-05-10 | 2
1 |  | CROSSOVERS Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-11 | 2022-05-14 | 3
1 |  | CONVECTION MODULE 6 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-11 | 2022-05-15 | 4
1 |  | CONVECTION MODULE 6 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-13 | 2022-05-18 | 5
1 |  | CONVECTION MODULE 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-15 | 2022-05-20 | 5
1 |  | CONVECTION MODULE 6 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-18 | 2022-05-23 | 5
1 |  | CONVECTION MODULE 6 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-05-20 | 2022-05-25 | 5
1 |  | HEADER BOX CONVECTION EXTERNAL Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-05-11 | 2022-05-21 | 10
1 |  | HEADER BOX CONVECTION EXTERNAL FIBRE GLASS CLOTH - Waterproof |  |  | 2022-05-11 | 2022-05-12 | 1
1 |  | HEADER BOX CONVECTION EXTERNAL Insulating Ceramic Fiber Paper KAOWOOL 2000 PAPER - 1260°C |  |  | 2022-05-11 | 2022-05-14 | 3
1 |  | CONVECTION MODULE 8 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-11 | 2022-05-16 | 5
1 |  | CONVECTION MODULE 8 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-13 | 2022-05-19 | 6
1 |  | CONVECTION MODULE 8 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-15 | 2022-05-22 | 7
1 |  | CONVECTION MODULE 8 PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-05-17 | 2022-05-25 | 8
1 |  | PLATFORM CONVECTION ELEV LEVEL1 | 2022-03-21 | 2022-03-28 | 2022-05-17 | 2022-05-27 | 10
1 |  | HOT AIR DUCT SUPPORT (steel on top of convection) | 2022-03-21 | 2022-03-28 | 2022-05-17 | 2022-05-27 | 10
1 |  | PLATFORM CONVECTION ELEV LEVEL3 | 2022-03-21 | 2022-03-28 | 2022-05-23 | 2022-05-28 | 5
1 |  | CONVECTION MODULE 9 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-25 | 2022-06-01 | 7
1 |  | CONVECTION MODULE 9 Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-27 | 2022-06-03 | 7
1 |  | CONVECTION MODULE 9 Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-29 | 2022-06-07 | 9
1 |  | CONVECTION BREECHING Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-05-25 | 2022-06-02 | 8
1 |  | CONVECTION BREECHING Insulating Castable Lightweight Firelite 124 L |  |  | 2022-05-27 | 2022-06-04 | 8
1 |  | CONVECTION BREECHING Ceramic Fiber Blanket CERACHEM BLANKET -1425°C |  |  | 2022-05-29 | 2022-06-06 | 8
1 |  | CONVECTION BREECHING Insulating Ceramic Fiber Paper KAOWOOL PAPER - 1400°C |  |  | 2022-05-31 | 2022-06-08 | 8
1 |  | CONVECTION BREECHING PYROBLOC MODULES Type 'M' 1425°C |  |  | 2022-06-02 | 2022-06-10 | 8
1 |  | PLATFORM CONVECTION ELEV LEVEL4 | 2022-03-21 | 2022-03-28 | 2022-05-25 | 2022-06-10 | 16
1 |  | SUPERHEATERS AIR DUCT 1 insualation |  |  | 2022-05-25 | 2022-06-05 | 11
1 | CONVECTION SECTION | PLATFORM CONVECTION ELEV LEVEL5 | 2022-03-21 | 2022-03-28 | 2022-06-01 | 2022-06-21 | 20
1 |  | PLATFORM CONVECTION ELEV LEVEL2 | 2022-03-21 | 2022-03-28 | 2022-06-06 | 2022-06-08 | 2
1 |  | SUPERHEATERS AIR DUCT 1 assembly |  |  | 2022-06-06 | 2022-06-08 | 2
1 |  | SUPERHEATERS AIR DUCT 2 insualation |  |  | 2022-06-06 | 2022-06-16 | 10
1 |  | HEADER BOX CONVECTION EXTERNAL |  |  | 2022-06-07 | 2022-06-14 | 7
1 |  | SUPERHEATERS AIR DUCT 1 erection |  |  | 2022-06-09 | 2022-06-10 | 1
1 |  | PLATFORM CONVECTION ELEV LEVEL6 | 2022-03-21 | 2022-03-28 | 2022-06-10 | 2022-06-20 | 10
1 |  | CONVECTION AIR DUCTS downwards 1 Insulating Castable Low Iron Firelite 2300 VLI |  |  | 2022-06-15 | 2022-06-20 | 5
1 |  | CONVECTION AIR DUCTS downwards 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-15 | 2022-06-20 | 5
1 |  | PLATFORM CONVECTION ELEV LEVEL7 | 2022-03-21 | 2022-03-28 | 2022-06-15 | 2022-06-20 | 5
1 |  | EXPANSION JOINTS |  |  | 2022-06-15 | 2022-06-29 | 14
1 |  | DAMPERS |  |  | 2022-06-15 | 2022-06-29 | 14
1 |  | SUPERHEATERS AIR DUCT 2 assembly |  |  | 2022-06-17 | 2022-06-19 | 2
1 |  | CONVECTION AIR DUCTS 2 downwards Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-18 | 2022-06-23 | 5
1 |  | CONVECTION AIR DUCTS 2 downwards Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-18 | 2022-06-23 | 5
1 |  | CONVECTION AIR DUCT downwards 1 assembly (bottom) | 2022-06-15 | 2022-06-22 | 2022-06-20 | 2022-06-23 | 3
1 |  | PLATFORM CONVECTION ELEV LEVEL8 | 2022-03-21 | 2022-03-28 | 2022-06-20 | 2022-06-26 | 6
1 |  | SUPERHEATERS AIR DUCT 2 erection |  |  | 2022-06-20 | 2022-06-21 | 1
1 |  | CONVECTION AIR DUCTS downwards 3 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-21 | 2022-06-26 | 5
1 |  | CONVECTION AIR DUCTS downwards 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-21 | 2022-06-26 | 5
1 |  | CONVECTION AIR DUCTS downwards 1 erection | 2022-06-15 | 2022-06-22 | 2022-06-24 | 2022-06-25 | 1
1 |  | CONVECTION AIR DUCT downwards 2 assembly (bottom) | 2022-06-15 | 2022-06-22 | 2022-06-24 | 2022-06-27 | 3
1 |  | CONVECTION AIR DUCT downwards 4 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-24 | 2022-06-29 | 5
1 |  | CONVECTION AIR DUCT downwards 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-24 | 2022-06-29 | 5
1 |  | PLATFORM CONVECTION ELEV LEVEL9 | 2022-03-21 | 2022-03-28 | 2022-06-25 | 2022-07-01 | 6
1 |  | CONVECTION AIR DUCT downwards 5 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-27 | 2022-07-02 | 5
1 |  | CONVECTION AIR DUCT downwards 5 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-27 | 2022-07-02 | 5
1 |  | CONVECTION AIR DUCTS downwards 2 erection | 2022-06-15 | 2022-06-22 | 2022-06-28 | 2022-06-29 | 1
1 |  | CONVECTION AIR DUCT downwards 3 assembly (midle) | 2022-06-15 | 2022-06-22 | 2022-06-28 | 2022-06-30 | 2
1 |  | CONVECTION AIR DUCTS downwards 3 erection | 2022-06-15 | 2022-06-22 | 2022-06-30 | 2022-07-01 | 1
1 |  | CONVECTION AIR DUCTS 4 downwards assembly (midle) | 2022-06-15 | 2022-06-22 | 2022-06-30 | 2022-07-02 | 2
1 |  | CONVECTION AIR DUCT downwards 6 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-06-30 | 2022-07-05 | 5
1 |  | CONVECTION AIR DUCT downwards 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-30 | 2022-07-05 | 5
1 |  | SUPERHEAT BURNERS |  |  | 2022-07-01 | 2022-07-10 | 9
1 |  | EXPANSION JOINTS |  |  | 2022-07-01 | 2022-07-10 | 9
1 |  | CONVECTION AIR DUCTS downwards 4 erection | 2022-06-15 | 2022-06-22 | 2022-07-03 | 2022-07-04 | 1
1 |  | CONVECTION AIR DUCTS 5 downwards assembly (top radius) | 2022-06-15 | 2022-06-22 | 2022-07-03 | 2022-07-05 | 2
1 |  | DUCT HORIZONTAL L1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-04 | 2022-07-08 | 4
1 |  | DUCT HORIZONTAL L1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-06 | 2022-07-10 | 4
1 |  | DUCT HORIZONTAL L2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-08 | 2022-07-11 | 3
1 |  | DUCT HORIZONTAL L2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-09 | 2022-07-13 | 4
1 |  | CONVECTION AIR DUCTS downwards 5 erection | 2022-06-15 | 2022-06-22 | 2022-07-06 | 2022-07-07 | 1
1 |  | CONVECTION AIR DUCTS 6 downwards assembly (top radius) | 2022-06-15 | 2022-06-22 | 2022-07-06 | 2022-07-08 | 2
1 |  | CONVECTION AIR DUCTS downwards 6 erection | 2022-06-15 | 2022-06-22 | 2022-07-09 | 2022-07-10 | 1
1 |  | DUCT HORIZONTAL L1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-13 | 2022-07-16 | 3
1 |  | DUCT HORIZONTAL R1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-13 | 2022-07-18 | 5
1 |  | DUCT HORIZONTAL R1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-14 | 2022-07-19 | 5
1 |  | DUCT HORIZONTAL R2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-15 | 2022-07-21 | 6
1 |  | DUCT HORIZONTAL R2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-16 | 2022-07-22 | 6
1 |  | DUCT HORIZONTAL L1 erection | 2022-06-15 | 2022-06-22 | 2022-07-17 | 2022-07-18 | 1
1 |  | DUCT HORIZONTAL L2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-17 | 2022-07-19 | 2
1 |  | DUCT HORIZONTAL arc L Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-18 | 2022-07-22 | 4
1 |  | DUCT HORIZONTAL arc L Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-19 | 2022-07-23 | 4
1 |  | DUCT HORIZONTAL arc R Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-07-20 | 2022-07-24 | 4
1 |  | DUCT HORIZONTAL arc R Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-21 | 2022-07-25 | 4
1 |  | DUCT HORIZONTAL L2 erection | 2022-06-15 | 2022-06-22 | 2022-07-20 | 2022-07-21 | 1
1 |  | DUCT HORIZONTAL R1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-23 | 2022-07-26 | 3
1 |  | DUCT HORIZONTAL R1 erection | 2022-06-15 | 2022-06-22 | 2022-07-27 | 2022-07-28 | 1
1 |  | DUCT HORIZONTAL R2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-27 | 2022-07-29 | 2
1 |  | DUCT HORIZONTAL R2 erection | 2022-06-15 | 2022-06-22 | 2022-07-30 | 2022-07-31 | 1
1 |  | DUCT HORIZONTAL arc L assembly | 2022-06-15 | 2022-06-22 | 2022-08-01 | 2022-08-02 | 1
1 |  | DUCT HORIZONTAL arc L erection | 2022-06-15 | 2022-06-22 | 2022-08-03 | 2022-08-04 | 1
1 |  | DUCT HORIZONTAL arc R assembly | 2022-06-15 | 2022-06-22 | 2022-08-03 | 2022-08-05 | 2
1 |  | DUCT HORIZONTAL arc R erection | 2022-06-15 | 2022-06-22 | 2022-08-06 | 2022-08-07 | 1
1 | APH | CONVECTION TRANSITION DUCTS 1 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-01 | 2022-04-03 | 2
1 |  | CONVECTION TRANSITION DUCTS 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-03 | 2022-04-05 | 2
1 |  | CONVECTION TRANSITION DUCTS 2 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-05 | 2022-04-07 | 2
1 |  | CONVECTION TRANSITION DUCTS 2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-07 | 2022-04-09 | 2
1 |  | CONVECTION TRANSITION DUCTS 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-09 | 2022-04-11 | 2
1 |  | CONVECTION TRANSITION DUCTS 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-11 | 2022-04-13 | 2
1 |  | CONVECTION TRANSITION DUCTS 4 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-04-13 | 2022-04-15 | 2
1 |  | CONVECTION TRANSITION DUCTS 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-04-14 | 2022-04-16 | 2
1 |  | CONVECTION TRANSITION DUCTS 1 erection |  |  | 2022-05-02 | 2022-05-03 | 1
1 |  | CONVECTION TRANSITION DUCTS 2 erection |  |  | 2022-05-04 | 2022-05-06 | 2
1 |  | CONVECTION TRANSITION DUCTS 3 erection |  |  | 2022-05-07 | 2022-05-09 | 2
1 |  | CONVECTION TRANSITION DUCTS 4 erection |  |  | 2022-05-10 | 2022-05-12 | 2
1 |  | DUCT UPWARDS L1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-20 | 2022-07-22 | 2
1 |  | DUCT UPWARDS L2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-22 | 2022-07-24 | 2
1 |  | DUCT UPWARDS R1 assembly | 2022-06-15 | 2022-06-22 | 2022-07-24 | 2022-07-26 | 2
1 |  | DUCT UPWARDS R2 assembly | 2022-06-15 | 2022-06-22 | 2022-07-26 | 2022-07-28 | 2
1 |  | DUCT UPWARDS L1 Insulating Castable Low Iron Firelite 2300 VL | 2022-07-27 | 2022-08-06 | 2022-07-27 | 2022-08-06 | 10
1 |  | DUCT UPWARDS L1 Ceramic Fiber Blanket CERABLANKET- 1260°C | 2022-07-27 | 2022-08-06 | 2022-07-27 | 2022-08-06 | 10
1 |  | DUCT UPWARDS L2 Insulating Castable Low Iron Firelite 2300 VL | 2022-08-26 | 2022-09-05 | 2022-07-27 | 2022-08-06 | 10
1 |  | DUCT UPWARDS L2 Ceramic Fiber Blanket CERABLANKET- 1260°C | 2022-08-26 | 2022-09-05 | 2022-07-27 | 2022-08-06 | 10
1 |  | DUCT UPWARDS R1 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-08-06 | 2022-08-17 | 11
1 |  | DUCT UPWARDS R1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-08-06 | 2022-08-17 | 11
1 |  | DUCT UPWARDS R2 Insulating Castable Low Iron Firelite 2300 VL |  |  | 2022-08-14 | 2022-08-25 | 11
1 |  | DUCT UPWARDS R2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-08-14 | 2022-08-25 | 11
1 |  | FLUE GAS DUCT UNDER APH Insulating Castable Lightweight Firelite 124 L |  |  | 2022-06-20 | 2022-06-26 | 6
1 |  | FLUE GAS DUCT UNDER APH Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-06-20 | 2022-06-26 | 6
1 |  | FLUE GAS DUCT UNDER APH (hopper/cap) |  |  | 2022-06-27 | 2022-06-28 | 1
1 |  | APH SUPPORT STRUCTURE |  |  | 2022-06-28 | 2022-06-29 | 1
1 |  | APH BLOCK 1B |  |  | 2022-06-30 | 2022-07-01 | 1
1 |  | APH BLOCK 1C |  |  | 2022-07-02 | 2022-07-03 | 1
1 |  | APH BLOCK 2A |  |  | 2022-07-04 | 2022-07-05 | 1
1 |  | APH BLOCK 2B |  |  | 2022-07-06 | 2022-07-07 | 1
1 |  | APH BLOCK 2C |  |  | 2022-07-08 | 2022-07-09 | 1
1 |  | APH BLOCK 3A |  |  | 2022-07-10 | 2022-07-11 | 1
1 |  | APH BLOCK 3B |  |  | 2022-07-12 | 2022-07-13 | 1
1 |  | APH BLOCK 3C |  |  | 2022-07-14 | 2022-07-15 | 1
1 |  | COMBUSTION HOT AIR DUCTS insualation | 2022-06-15 | 2022-06-22 | 2022-07-14 | 2022-07-20 | 6
1 |  | COMBUSTION HOT AIR DUCTS (top of APH) |  |  | 2022-07-20 | 2022-07-21 | 1
1 |  | DUCT UPWARDS L1 erection | 2022-06-15 | 2022-06-22 | 2022-09-09 | 2022-09-10 | 1
1 |  | DUCT UPWARDS L2 L2 erection | 2022-06-15 | 2022-06-22 | 2022-09-09 | 2022-09-10 | 1
1 |  | EXP JOINTS |  |  | 2022-09-09 | 2022-09-11 | 2
1 |  | DUCT UPWARDS R1 erection | 2022-06-15 | 2022-06-22 | 2022-09-10 | 2022-09-11 | 1
1 |  | DUCT UPWARDS R2 L2 erection | 2022-06-15 | 2022-06-22 | 2022-09-10 | 2022-09-11 | 1
1 | DUCT | FLUE GAS DUCT (bottom panels) Insulating Castable Lightweight Firelite 124 L |  |  | 2022-07-20 | 2022-07-26 | 6
1 |  | FLUE GAS DUCT (bottom panels) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-26 | 2022-08-01 | 6
1 |  | FLUE GAS DUCT (side & top panels) Insulating Castable Lightweight Firelite 124 L |  |  | 2022-07-20 | 2022-08-01 | 12
1 |  | FLUE GAS DUCT (side & top panels) Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-07-25 | 2022-08-06 | 12
1 |  | FLUE GAS DUCT (bottom panels) erection | 2022-06-15 | 2022-06-22 | 2022-08-01 | 2022-08-04 | 3
1 |  | STEEL UNDER COLD AIR DUCTS assembly | 2022-06-15 | 2022-06-22 | 2022-08-04 | 2022-08-06 | 2
1 |  | FLUE GAS DUCT (side & top panels) erection | 2022-06-15 | 2022-06-22 | 2022-08-06 | 2022-08-25 | 19
1 |  | STEEL UNDER COLD AIR DUCTS erection | 2022-06-15 | 2022-06-22 | 2022-08-07 | 2022-08-08 | 1
1 |  | COMBUSTION COLD AIR DUCTS 1 assebmbly |  |  | 2022-08-09 | 2022-08-11 | 2
1 |  | COMBUSTION COLD AIR DUCTS 1 erection |  |  | 2022-08-11 | 2022-08-12 | 1
1 |  | COMBUSTION COLD AIR DUCTS 2 assembly |  |  | 2022-08-11 | 2022-08-13 | 2
1 |  | DAMPERS |  |  | 2022-08-11 | 2022-08-23 | 12
1 |  | EXP JOINTS |  |  | 2022-08-11 | 2022-08-23 | 12
1 |  | COMBUSTION COLD AIR DUCTS 2 erection |  |  | 2022-08-13 | 2022-08-14 | 1
1 |  | COMBUSTION COLD AIR DUCTS 3 assembly |  |  | 2022-08-13 | 2022-08-15 | 2
1 |  | COMBUSTION COLD AIR DUCTS 3 erection |  |  | 2022-08-15 | 2022-08-16 | 1
1 |  | COMBUSTION COLD AIR DUCTS 4 assembly |  |  | 2022-08-15 | 2022-08-17 | 2
1 |  | COMBUSTION COLD AIR DUCTS 5 assembly |  |  | 2022-08-17 | 2022-08-19 | 2
1 |  | COMBUSTION COLD AIR DUCTS 4 erection |  |  | 2022-08-18 | 2022-08-19 | 1
1 |  | COMBUSTION COLD AIR DUCTS 6 assembly |  |  | 2022-08-19 | 2022-08-21 | 2
1 |  | COMBUSTION COLD AIR DUCTS 5 erection |  |  | 2022-08-20 | 2022-08-21 | 1
1 |  | COMBUSTION COLD AIR DUCTS 6 erection |  |  | 2022-08-22 | 2022-08-23 | 1
1 |  | DUCT PLATFORMS |  |  | 2022-08-23 | 2022-08-28 | 5
1 | STACK | STACK 1 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-18 | 2022-09-23 | 5
1 |  | STACK 1 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-19 | 2022-09-25 | 6
1 |  | STACK 2 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-20 | 2022-09-27 | 7
1 |  | STACK 2 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-21 | 2022-09-28 | 7
1 |  | STACK 3 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-22 | 2022-09-29 | 7
1 |  | STACK 3 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-22 | 2022-09-30 | 8
1 |  | STACK 1 steel assembly TOS =112,300 | 2022-06-15 | 2022-06-22 | 2022-09-29 | 2022-10-01 | 2
1 |  | STACK 4 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-29 | 2022-10-06 | 7
1 |  | STACK 4 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-10-02 | 2022-10-12 | 10
1 |  | STACK 5 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-09-29 | 2022-10-06 | 7
1 |  | STACK 5 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-09-30 | 2022-10-08 | 8
1 |  | STACK 6 Insulating Castable Lightweight Firelite 124 L |  |  | 2022-10-02 | 2022-10-10 | 8
1 |  | STACK 6 Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 2022-10-05 | 2022-10-13 | 8
1 |  | STACK 2 steel assembly TOS =121,300 | 2022-03-21 | 2022-03-28 | 2022-09-30 | 2022-10-02 | 2
1 |  | STACK 3 steel assembly TOS =130,300 | 2022-06-15 | 2022-06-22 | 2022-10-01 | 2022-10-04 | 3
1 |  | STACK 4 steel assembly TOS =139,300 | 2022-06-15 | 2022-06-22 | 2022-10-13 | 2022-10-15 | 2
1 |  | STACK 5 steel assembly TOS =148,310 | 2022-06-15 | 2022-06-22 | 2022-10-13 | 2022-10-16 | 3
1 |  | STACK 6 steel assembly TOS =157,000 | 2022-06-15 | 2022-06-22 | 2022-10-14 | 2022-10-17 | 3
1 |  | STACK 1 erection | 2022-06-15 | 2022-06-22 | 2022-10-18 | 2022-10-19 | 1
1 |  | STACK 2 erection | 2022-03-21 | 2022-03-28 | 2022-10-19 | 2022-10-20 | 1
1 |  | STACK 3 erection | 2022-06-15 | 2022-06-22 | 2022-10-20 | 2022-10-21 | 1
1 |  | STACK 4 erection | 2022-06-15 | 2022-06-22 | 2022-10-21 | 2022-10-22 | 1
1 |  | STACK 5 erection | 2022-06-15 | 2022-06-22 | 2022-10-22 | 2022-10-23 | 1
1 |  | STACK 6 erection | 2022-06-15 | 2022-06-22 | 2022-10-23 | 2022-10-24 | 1
1 | MACHINERY | ID FANS | 2022-02-28 | 2022-03-10 | 2022-03-20 | 2022-04-15 | 26
1 |  | FD FAN | 2022-06-15 | 2022-06-22 | 2022-07-01 | 2022-07-25 | 24
1 |  | AIR INTAKE | 2022-06-15 | 2022-06-22 | 2022-07-05 | 2022-07-20 | 15
1 |  | STEAM TURBINE |  |  | 2022-08-10 | 2022-09-10 | 31
1 |  | ELECTRIC MOTOR |  |  | 2022-08-10 | 2022-09-10 | 31
1 |  | LUBE OIL SYSTEM |  |  | 2022-08-10 | 2022-09-10 | 31
1 |  | SAPH |  |  | 2022-08-15 | 2022-08-16 | 1
1 |  | INTERCOONNECTING PIPING |  |  |  |  | 0
1 | SCR | SKID |  |  |  |  | 0
1 |  | CATALYST |  |  |  |  | 0
Note on C24: Author: Radiient after this with FS
Note on C31: Author: In this step also need to place inlet manifolds on top of arch duct, for temporary storage)
Note on D73: Author: John zink hamworthy

## Sheet2
FLUE GAS DUCT UNDER APH (hopper/cap) |  |  | 44739 | 44740
FLUE GAS DUCT UNDER APH Insulating Castable Lightweight Firelite 124 L |  |  | 44732 | 44738
FLUE GAS DUCT UNDER APH Ceramic Fiber Blanket CERABLANKET- 1260°C |  |  | 44732 | 44738
APH SUPPORT STRUCTURE |  |  | 44740 | 44741
APH BLOCK 1B |  |  | 44742 | 44743
APH BLOCK 1C |  |  | 44744 | 44745
APH BLOCK 2A |  |  | 44746 | 44747
APH BLOCK 2B |  |  | 44748 | 44749
APH BLOCK 2C |  |  | 44750 | 44751
APH BLOCK 3A |  |  | 44752 | 44753
APH BLOCK 3B |  |  | 44754 | 44755
APH BLOCK 3C |  |  | 44756 | 44757
COMBUSTION HOT AIR DUCTS (top of APH) |  |  | 44762 | 44763
COMBUSTION HOT AIR DUCTS insualation | 44727 | 44734 | 44756 | 44762

## Flanges
WBS | Number of Bolts | Number of Flanges
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 24 | 1
1103A | 20 | 1
1104A | 24 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1107C | 24 | 1
1107C | 20 | 1
1105A | 24 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105A | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1105D | 24 | 1
1102 | 24 | 1
1102 | 20 | 1
1102 | 20 | 1
1106A | 24 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106A | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 24 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1107A | 24 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107A | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 24 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1105D | 20 | 1
1105D | 20 | 1
1106D | 20 | 1
1106D | 20 | 1
1107D | 20 | 1
1107D | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1103A | 20 | 1
1102 | 24 | 1
1103A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
1104A | 20 | 1
PAYN36A | 20 | 1
PAYN36A | 20 | 1
PAYN36A | 20 | 1
PAYN36A | 20 | 1
141

## Sheet1 (hidden)
ActivityID | Activity Name | Original Duration | Start | Finish | UoM | Labor Units % Complete | Quantity OPFC | UoM
Total |  | 1127 | 2019-08-01 | 2022-08-31 |  | 37.39%
OPFC&BLSLevel3.ForecastSchedule04.06.2021VLS |  | 1127 | 2019-08-01 | 2022-08-31 |  | 37.39%
MILESTONES |  | 1127 | 2019-08-01 | 2022-08-31 |  | 0%
PROJECTMILESTONES |  | 1127 | 2019-08-01 | 2022-08-31 |  | 0%
MIL-PM-1000 | Project Start | 0 | 2019-08-01 |  |  | 0%
MIL-PM-1040 | Commencement Date of Construction works at site | 0 | 2019-10-01 |  |  | 0%
MIL-PM-1020 | Start of Civil and Underground works | 0 | 2019-10-01 |  |  | 0%
MIL-PM-1010 | Signing of Contract | 0 |  | 2019-10-12 |  | 0%
MIL-PM-1030 | Completion of temporary accommodation Camp (496 beds) - ready for occupancy | 0 |  | 2019-12-05 |  | 0%
MIL-PM-1070 | Start of FAR Building Steel Structures | 0 | 2020-01-31 |  |  | 0%
MIL-PM-1050 | Completion of temporary accommodation Camp (880 beds) - ready for occupancy | 0 |  | 2020-03-06 |  | 0%
MIL-PM-1100 | Start Installation of Compressor A / B / C (Entire Package Erection Compressor / WHRU / Lube Oil / etc.) | 0 | 2020-03-08 |  |  | 0%
MIL-PM-1060 | Completion of temporary accommodation Camp (1216 beds) - ready for occupancy | 0 |  | 2020-05-30 |  | 0%
MIL-PM-1090 | Start of Aboveground Piping Works | 0 | 2020-06-25 |  |  | 0%
MIL-PM-1080 | Completion of temporary accommodation Camp (1408 beds) - ready for occupancy | 0 |  | 2020-07-15 |  | 0%
MIL-PM-1190 | Shut down 2021 | 0 |  | 30-Jun-21* |  | 0%
MIL-PM-1110 | Completion of All Concrete Foundations and Underground works | 0 |  | 2021-11-02 |  | 0%
MIL-PM-1200 | FAR Beneficial Use | 0 |  | 16-Feb-22* |  | 0%
MIL-PM-1210 | Compressor A Beneficial Use | 0 |  | 21-Feb-22* |  | 0%
MIL-PM-1130 | FAR Building Mechaniccally completed (ready for Commissioning) | 0 |  | 25-Feb-22* |  | 0%
MIL-PM-1120 | 10kV power supply to FAR | 0 |  | 2022-02-25 |  | 0%
MIL-PM-1140 | Compressor A train Mechanically Completed | 0 |  | 15-Mar-22* |  | 0%
MIL-PM-1230 | Compressor B Beneficial Use | 0 |  | 01-Apr-22* |  | 0%
MIL-PM-1150 | Compressor B train Mechanically Completed | 0 |  | 15-Apr-22* |  | 0%
MIL-PM-1220 | Compressor C Beneficial Use | 0 |  | 15-May-22* |  | 0%
MIL-PM-1170 | Compressor C train Mechanically Completed | 0 |  | 31-May-22* |  | 0%
MIL-PM-1180 | Project Finish | 0 |  | 2022-08-31 |  | 0%
PRIORITYSUB-SYSTEMMILESTONES |  | 413 | 2021-06-04 | 2022-07-21 |  | 0%
FARBUILDINGSOFTMCMILESTONES |  | 0 | 2021-10-17 | 2021-10-17 |  | 0%
A1000 | Temporary DG Available | 0 | 2021-10-17 |  |  | 0%
A1010 | UPS Ready for Pre-commissioning | 0 | 2021-10-17 |  |  | 0%
A1030 | Electrical Panels Ready for Pre-commissioning | 0 | 2021-10-17 |  |  | 0%
SOFTMCMILESTONES |  | 413 | 2021-06-04 | 2022-07-21 |  | 0%
VCR-01 |  | 135 | 2021-10-13 | 2022-02-25 |  | 0%
GC-MC-40.03.02/03 | Syst. 40.03.02/03 - SMC LTR-40901A/B 10/0,4 transformer normal to normal | 21 | 2021-10-13 | 2021-11-03 |  | 0%
GC-MC-40.03.09 | Syst. 40.03.09 - SMC LP-40981/2 FAR normal lighting and small power | 21 | 2021-11-03 | 2021-11-24 |  | 0%
GC-MC-40.03.05 | Syst. 40.03.05 - SMC LSB-40970 10kV switchboard essential | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.03.06/07 | Syst. 40.03.06/07 - SMC LTR-40971A/B 10/0,4 transformer normal to essential | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.03.01 | Syst. 40.03.01 - SMC LSB-40900 10 kV switchboard normal | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.03.04 | Syst. 40.03.04 - SMC LSB-40901 0,4 kV switchboard normal | 21 | 2021-11-22 | 2021-12-13 |  | 0%
GC-MC-40.03.08 | Syst. 40.03.08 - SMC LSB-40971 0,4 kV switchboard essential | 21 | 2021-11-22 | 2021-12-13 |  | 0%
GC-MC-40.01.01 | Syst. 40.01.01 - SMC Earthing FAR | 21 | 2021-11-26 | 2021-12-17 |  | 0%
GC-MC-40.11.06 | Syst. 40.11.06 - SMC 110 Vdc 1,5*1,5 hours autonomy FAR location | 21 | 2021-12-10 | 2021-12-31 |  | 0%
GC-MC-40.11.02 | Syst. 40.11.02 - SMC 230 V 5*5 hours autonomy compressor UPS | 21 | 2021-12-10 | 2021-12-31 |  | 0%
GC-MC-68.01 | Syst. 68.01 - SMC (HVAC, Field Auxiliary Room (FAR)) | 21 | 2021-12-12 | 2022-01-02 |  | 0%
GC-MC-40.11.05 | Syst. 40.11.05 - SMC 110 Vdc 1,5*1,5 hours autonomy | 21 | 2021-12-13 | 2022-01-10 |  | 0%
GC-MC-40.11.01 | Syst. 40.11.01 - SMC 400/230 V 2*2 hours autonomy LER 906/907/908, IFAR loads SS-911/912 loads | 21 | 2021-12-20 | 2022-01-10 |  | 0%
GC-MC-40.03.14 | Syst. 40.03.14 - SMC LSB-40927 FAR HVAC essential power supply | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.03.15 | Syst. 40.03.15 - SMC LSB-40952 FAR HT essential | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.03.16 | Syst. 40.03.16 - SMC LP-40988 FAR others essential | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.03.11 | Syst. 40.03.11 - SMC LP-40992 FAR HVAC power supply | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.03.10 | Syst. 40.03.10 - SMC LP-40951 FAR HT normal | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.03.12 | Syst. 40.03.12 - SMC LP-40907 FAR others | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.11.03 | Syst. 40.11.03 - SMC 230 V 4*4 hours autonomy telecom UPS | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.11.04 | Syst. 40.11.04 - SMC 230 V 1 hour autonomy (escape lighting B-901 and nearby areas) | 21 | 2021-12-30 | 2022-01-20 |  | 0%
GC-MC-40.02.01/02 | Syst. 40.02.01/02 - SMC Power line from LSB-4001-A16/B10 | 21 | 2022-01-02 | 2022-01-23 |  | 0%
GC-MC-84.01 | Syst. 84.01 - SMC (Plant Buildings, Field Auxiliary Room (FAR)) | 21 | 2022-01-03 | 2022-01-24 |  | 0%
GC-MC-40.03.18 | Syst. 40.03.18 - SMC LP-40991 Essential instrument DB | 21 | 2022-01-17 | 2022-02-14 |  | 0%
GC-MC-40.03.17 | Syst. 40.03.17 - SMC LP-40983 Essential lighting DB | 21 | 2022-01-19 | 2022-02-16 |  | 0%
GC-MC-40.03.13 | Syst. 40.03.13 - SMC LSB-40906 Nitroget unit | 21 | 2022-01-27 | 2022-02-17 |  | 0%
GC-MC-40.03.19 | Syst. 40.03.19 - SMC LP-40983C Essential instrument DB (Maint Building) | 21 | 2022-01-28 | 2022-02-25 |  | 0%
VCR-02 |  | 134 | 2021-10-29 | 2022-03-11 |  | 0%
GC-MC-30.15 | Syst. 30.15 - SMC (Fire & Gas Detection F&G Detection - Instrument Air & N2 Area) | 21 | 2021-10-29 | 2021-11-18 |  | 0%
GC-MC-40.01.03 | Syst. 40.01.03 - SMC Earthing IAC | 21 | 2021-11-26 | 2021-12-17 |  | 0%
GC-MC-47.01 | Syst. 47.01 - SMC Air Compressor and Dryer Package A + Instrument Air Receiver | 21 | 2021-12-03 | 2021-12-24 |  | 0%
GC-MC-47.02 | Syst. 47.02 - SMC Air Compressor and Dryer Package B | 21 | 2021-12-03 | 2021-12-24 |  | 0%
GC-MC-47.03 | Syst. 47.03 - SMC Instrument Air Plant Area | 21 | 2021-12-03 | 2021-12-24 |  | 0%
GC-MC-48.01 | Syst. 48.01 - SMC (N2 Package and Receivers) | 21 | 2021-12-03 | 2021-12-24 |  | 0%
GC-MC-40.12.05 | Syst. 40.12.05 - SMC Air starting system | 21 | 2021-12-06 | 2022-01-03 |  | 0%
GC-MC-40.12.04 | Syst. 40.12.04 - SMC Cooling water system | 21 | 2021-12-06 | 2022-01-03 |  | 0%
GC-MC-40.12.03 | Syst. 40.12.03 - SMC Fuel system | 21 | 2021-12-06 | 2022-01-03 |  | 0%
GC-MC-74.01.01 | Syst. 74.01.01 - SMC LAN System and Fiber Optic Cable | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-30.03 | Syst. 30.03 - SMC (F & G Detection - Field Auxiliary Room (FAR)) | 21 | 2022-01-03 | 2022-01-24 |  | 0%
GC-MC-40.01.09 | Syst. 40.01.09 - SMC Earthing others | 21 | 2022-01-14 | 2022-02-04 |  | 0%
GC-MC-40.01.02 | Syst. 40.01.02 - SMC Earthing EDG | 21 | 2022-01-21 | 2022-02-11 |  | 0%
GC-MC-40.12.10 | Syst. 40.12.10 - SMC Aux. power supply switchboard | 21 | 2022-01-24 | 2022-02-21 |  | 0%
GC-MC-30.02 | Syst. 30.02 - SMC (F & G Detection - Standby Generation (EDG area)) | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-40.12.01 | Syst. 40.12.01 - SMC Fire detection and Fire suppression system | 21 | 2022-01-26 | 2022-02-23 |  | 0%
GC-MC-40.12.02 | Syst. 40.12.02 - SMC Ventilation system | 21 | 2022-01-28 | 2022-02-25 |  | 0%
GC-MC-30.16 | Syst. 30.16 - SMC (Fire & Gas Detection F&G Detection - Open Drain Area) | 21 | 2022-01-29 | 2022-02-18 |  | 0%
GC-MC-40.12 | Syst. 40.12 - SMC Emergency DG package | 21 | 2022-02-01 | 2022-02-22 |  | 0%
GC-MC-40.12.08 | Syst. 40.12.08 - SMC Black start diesel engine system | 21 | 2022-02-02 | 2022-03-02 |  | 0%
GC-MC-40.12.07 | Syst. 40.12.07 - SMC Cold start diesel engine system | 21 | 2022-02-02 | 2022-03-02 |  | 0%
GC-MC-40.12.06 | Syst. 40.12.06 - SMC Control / protection system | 21 | 2022-02-02 | 2022-03-02 |  | 0%
GC-MC-61.01 | Syst. 61.01 - SMC ICSS System F&G Site Acceptance Tests (SAT) | 21 | 2022-02-02 | 2022-02-23 |  | 0%
GC-MC-61.02 | Syst. 61.02 - SMC PCS (SAT) | 21 | 2022-02-02 | 2022-02-23 |  | 0%
GC-MC-61.03 | Syst. 61.03 - SMC ESD System (SAT) | 21 | 2022-02-02 | 2022-02-23 |  | 0%
GC-MC-40.12.09 | Syst. 40.12.09 - SMC Small power system (lighting, sockets etc.) | 21 | 2022-02-11 | 2022-03-11 |  | 0%
VCR-03 |  | 213 | 2021-06-04 | 2022-01-02 |  | 0%
GC-MC-90.04 | Syst. 90.04 - SMC BLS Civil and structures | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-09.06 | Syst. 09.06 - SMC (BLS (Multiphase Inlet Lines T1)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-62.10 | Syst. 62.10 - SMC (BLS (Closed Drain)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-56.06 | Syst. 56.06 - SMC (BLS (Rich MEG) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-05.04 | Syst. 05.04 - SMC (OPF Tie-in (Condensate Return Lines T1) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-17.01 | Syst. 17.01 - SMC (BLS (Demulsifier)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-45.01 | Syst. 45.01 - SMC (BLS (Potable Water)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-43.01 | Syst. 43.01 - SMC (BLS (Fresh Water)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-04.22 | Syst. 04.22 - SMC (BLS (Gas/Liquid Return Line T1 & T2)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-05.01 | Syst. 05.01 - SMC (OPF Tie-in (Condensate Return Lines T2) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-09.05 | Syst. 09.05 - SMC (BLS (Multiphase Inlet Lines T2)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-30.01 | Syst. 30.01 - SMC (BLS (F & G)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-47.08 | Syst. 47.08 - SMC (BLS (Instrument Air) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-56.01 | Syst. 56.01 - SMC (OPF Tie-in (Lean MEG)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-40.14 | Syst. 40.14 - SMC BLS - Electrical (Heat Tracing, Lightings, Earthing, Small Power) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-22.03 | Syst. 22.03 - SMC BLS (Buffer Sump and Piping) & Open Drain | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-48.03.01 | Syst. 48.03.01 - SMC (Nitrogen N2 Distribution-Equipment Purge (BLS)) | 21 | 2021-06-09 | 2021-06-29 |  | 0%
GC-MC-61.06 | Syst. 61.06 - SMC (DCS, Safeguarding & SCADA Systems BLS and OPF CCR) | 21 | 2021-06-10 | 2021-06-30 |  | 0%
GC-MC-09.01 | Syst. 09.01 - SMC (BLS (Parking Loop)) | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-44.01 | Syst. 44.01 - SMC (BLS (Piltun Gas Supply Line)) | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-45.02 | Syst. 45.02 - SMC Water Users FAR (HVAC Humidifiers) | 21 | 2021-12-12 | 2022-01-02 |  | 0%
VCR-04 |  | 340 | 2021-06-04 | 2022-05-09 |  | 0%
GC-MC-60.05 | Syst. 60.05 - SMC (BLS (Firewater)) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-62.09 | Syst. 62.09 - SMC (Closed Drain Header) | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-44.04 | Syst. 44.04 - SMC (Fuel/Seal Gas Turbine A) | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-44.03 | Syst. 44.03 - SMC (LP Fuel Gas Purge) | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-48.02 | Syst. 48.02 - SMC N2 Distribution - Gas Compression Seals, Flare Purge, and HTF Sump Vessel | 21 | 2021-11-25 | 2021-12-16 |  | 0%
GC-MC-40.01.16 | Syst. 40.01.16 -SMC (Power Generation Earthing - HP Flare & Close Drain Area) | 21 | 2021-12-22 | 2022-01-11 |  | 0%
GC-MC-60.07 | Syst. 60.07 - SMC CO2 Fire Fighting - FAR (Piping discipline only for FAR SMC) | 21 | 2022-01-03 | 2022-01-24 |  | 0%
GC-MC-30.17 | Syst. 30.17 - SMC (Fire & Gas Detection F&G Detection - Fuel & Seal Gas Area) | 21 | 2022-01-04 | 2022-01-24 |  | 0%
GC-MC-30.19 | Syst. 30.19 - SMC (Fire & Gas Detection F&G Detection - Main Process Pipe Rack) | 21 | 2022-01-16 | 2022-02-05 |  | 0%
GC-MC-61.05 | Syst. 61.05 - SMC Rotating Equipment Data Acquisition System (RDAS) SAT and Integration | 21 | 2022-02-02 | 2022-02-23 |  | 0%
GC-MC-61.04 | Syst. 61.04 - SMC (DCS, Safeguarding & SCADA Systems F&G System) | 21 | 2022-02-03 | 2022-02-23 |  | 0%
GC-MC-60.03 | Syst. 60.03 - SMC (Firewater Distribution - Ring Main All Process Areas) | 21 | 2022-02-07 | 2022-02-28 |  | 0%
GC-MC-44.02 | Syst. 44.02 - SMC (Fuel & Seal Gas Package) | 21 | 2022-02-09 | 2022-03-02 |  | 0%
GC-MC-62.02 | Syst. 62.02 - SMC HP Flare Header, Drum, Pumps, Stack, and Propane Bottles | 21 | 2022-02-09 | 2022-03-02 |  | 0%
GC-MC-30.18 | Syst. 30.18 - SMC (Fire & Gas Detection F&G Detection - HP Flare & Close Drain Area) | 21 | 2022-02-20 | 2022-03-12 |  | 0%
GC-MC-43.02 | Syst. 43.02 - SMC (Service Water Distribution) | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-60.02 | Syst. 60.02 - SMC Firewater Distribution - Ring Main Utilities | 21 | 2022-04-18 | 2022-05-09 |  | 0%
VCR-05 |  | 221 | 2021-11-02 | 2022-06-11 |  | 0%
GC-MC-40.04.01 | Syst. 40.04.01 - SMC LSB-40911A switchboard normal | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.04.02 | Syst. 40.04.02 - SMC LP-40991A normal lighting and small power DB | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.04.03 | Syst. 40.04.03 - SMC LSB-40922A switchboard essential | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.04.05 | Syst. 40.04.05 - SMC LP-40923A 400 V essential for K-04901A (inside building) | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.04.06 | Syst. 40.04.06 - SMC LP-40922A 400 V essential lighting and small power | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.04.07 | Syst. 40.04.07 - SMC LP-40996A HVAC LER | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-40.11.09 | Syst. 40.11.09 - SMC UPS for comppressor A | 21 | 2021-11-02 | 2021-11-23 |  | 0%
GC-MC-84.06 | Syst. 84.06 - SMC (LER Building B-906) | 21 | 2021-11-07 | 2021-11-28 |  | 0%
GC-MC-40.01.10 | Syst. 40.01.10 - SMC (Power Generation Earthing - LER (B-906)) | 21 | 2021-11-13 | 2021-12-03 |  | 0%
GC-MC-40.08.10 | Syst. 40.08.10 - SMC LP-40973A/B LUP-40913A/B power supply B-911 | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.08.09 | Syst. 40.08.09 - SMC LP-40902 Essential building room heater DB | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.08.08 | Syst. 40.08.08 - SMC LP-40975A/B LUP-40901A/B power supply B-911 | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-30.13 | Syst. 30.13 - SMC (Fire & Gas Detection F&G Detection - Substation B-911) | 21 | 2021-12-03 | 2021-12-23 |  | 0%
GC-MC-60.11 | Syst. 60.11 - SMC (Fire Fighting System CO2 Fire Fighting - Substation B-911) | 21 | 2021-12-03 | 2021-12-23 |  | 0%
GC-MC-47.04 | Syst. 47.04 - SMC Instrument Air & Gas Compression Area | 21 | 2021-12-03 | 2021-12-24 |  | 0%
GC-MC-40.01.04 | Syst. 40.01.04 - SMC (Earthing Compressor A) | 21 | 2021-12-04 | 2021-12-25 |  | 0%
GC-MC-40.07.01 | Syst. 40.07.01 - SMC LTR-40903A transformer normal to normal | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.02 | Syst. 40.07.02 - SMC LTR-40903B transformer normal to normal | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.03 | Syst. 40.07.03 - SMC LSB-40903 supply to LSB-40914 (compressor A) & LSB-40915 (compressor B) | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.04 | Syst. 40.07.04 - SMC LVS-40916 compressor A VFDs | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.06 | Syst. 40.07.06 - SMC LP-40984 normal lighting and small power | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.07 | Syst. 40.07.07 - SMC LP-40941/942/943/944/945/946/947/948/949 Normal HT | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.07.08 | Syst. 40.07.08 - SMC LSB-40920 Circulating Pump Station and Flare Knock out Srum Switchboard | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.01 | Syst. 40.08.01 - SMC LTR-40972A transformer normal to essential | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.02 | Syst. 40.08.02 - SMC LTR-40972B transformer essential to essential | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.03 | Syst. 40.08.03 - SMC LSB-40972 supply to essential | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.04 | Syst. 40.08.04 - SMC LP-40985 lighting essential | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.05 | Syst. 40.08.05 - SMC LP-40935/?/40940 essential HT | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.08.07 | Syst. 40.08.07 - SMC LP-40989 essential aux power | 21 | 2021-12-07 | 2021-12-28 |  | 0%
GC-MC-40.01.15 | Syst. 40.01.15 - SMC (Power Generation Earthing - Fuel & Seal Gas, Heat Transfer Fluid Areas) | 21 | 2021-12-10 | 2021-12-30 |  | 0%
GC-MC-84.10 | Syst. 84.10 - SMC (Substation Building B-911) | 21 | 2021-12-20 | 2022-01-10 |  | 0%
GC-MC-40.01.13 | Syst. 40-01-13 - SMC (Power Generation Earthing - Substation B-911) | 21 | 2021-12-23 | 2022-01-12 |  | 0%
GC-MC-04.01.02 | Syst. 04.01.02 - SMC GTC Package A Filter house | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.03 | Syst. 04.01.03 - SMC GTC Package A GT enclosure ventilation system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.04 | Syst. 04.01.04 - SMC GTC Package A CC enclosure ventilation system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.05 | Syst. 04.01.05 - SMC GTC Package A GT enclosure fire fighting system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.06 | Syst. 04.01.06 - SMC GTC Package A CC enclosure fire fighting system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.07 | Syst. 04.01.07 - SMC GTC Package A Compressor Seal gas system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.08 | Syst. 04.01.08 - SMC GTC Package A Lube oil system | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-04.01.17 | Syst. 40.01.17 - SMC (Power Generation Earthing - Main Process Pipe Rack) | 21 | 2022-01-02 | 2022-01-22 |  | 0%
GC-MC-40.01.14 | Syst. 40.01.14 - SMC (Power Generation Earthing - Substation B-912) | 21 | 2022-01-03 | 2022-01-23 |  | 0%
GC-MC-40.08.06 | Syst. 40.08.06 - SMC LSB-40994 B911 HVAC | 21 | 2022-01-06 | 2022-01-27 |  | 0%
GC-MC-68.10 | Syst. 68.10 - SMC (HVAC, SS Building B-911) | 21 | 2022-01-06 | 2022-01-27 |  | 0%
GC-MC-40.04.09 | Syst. 40.04.09 - SMC LP-40925A/B LUP-40911A/B power supply LER-906 | 21 | 2022-01-12 | 2022-02-02 |  | 0%
GC-MC-40.04.08 | Syst. 40.04.08 - SMC LP-40977A/B LUP-40901A/B power supply LER-906 | 21 | 2022-01-12 | 2022-02-02 |  | 0%
GC-MC-68.07 | Syst. 68.07 - SMC (HVAC, LER Building B-906) | 21 | 2022-01-12 | 2022-02-02 |  | 0%
GC-MC-40.09.01 | Syst. 40.09.01 - SMC LTR-40904A transformer normal to normal | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.09.02 | Syst. 40.09.02 - SMC LTR-40904B transformer normal to normal | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.09.03 | Syst. 40.09.03 - SMC LSB-40904 supply to LSB-40916 (compressor C) | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.09.04 | Syst. 40.09.04 - SMC OPFC LVS-40918 Compressor C VFDs | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.09.05 | Syst. 40.09.05 - SMC OPFC LP-40986/A Normal Lighting and Small Power | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.09.06 | Syst. 40.09.06 - SMC OPFC LSB-40951/952 Normal HT | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.10.01 | Syst. 40.10.01 - SMC LP-40987/A lighting essential | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.10.02 | Syst. 40.10.02 - SMC LP-40950 essential HT | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.10.03 | Syst. 40.10.03 - SMC LSB-40995 B912 HVAC | 21 | 2022-01-17 | 2022-02-07 |  | 0%
GC-MC-40.11.07 | Syst. 40.11.07 - SMC (Power Generation UPS-40913A/B, 110 Vdc SS912 Location) | 21 | 2022-01-18 | 2022-02-07 |  | 0%
GC-MC-40.11.08 | Syst. 40.11.08 - SMC (Power Generation UPS-40916, 110V DC SS912 Escape Route lighting) | 21 | 2022-01-18 | 2022-02-07 |  | 0%
GC-MC-30.10 | Syst. 30.10 - SMC (F & G Detection - LER (B-906) | 21 | 2022-01-27 | 2022-02-17 |  | 0%
GC-MC-60.08 | Syst. 60.08 - SMC (Fire Fighting System CO2 Fire Fighting - LER (B-906)) | 21 | 2022-01-28 | 2022-02-17 |  | 0%
GC-MC-40.04.04 | Syst. 40.04.04 - SMC LP-40997A HVAC DB for compressor building essential | 21 | 2022-01-31 | 2022-02-21 |  | 0%
GC-MC-04.01 | Syst. 04.01 - SMC (Gas Turbine/Compressor/UCP and Auxiliaries A) | 21 | 2022-01-31 | 2022-02-21 |  | 0%
GC-MC-30.04 | Syst. 30.04 - SMC (F & G Detection - Compressor A and Building) | 21 | 2022-01-31 | 2022-02-21 |  | 0%
GC-MC-04.30 | Syst. 04.30 - SMC GTC package A WHRU system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.29 | Syst. 04.29 - SMC Water washing skid | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-41.03 | Syst. 41.03 - SMC (HTF Turbine A WHRU) | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-84.02 | Syst. 84.02 - SMC (Gas Compressor A Building) | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.03 | Syst. 04.03 - SMC (Compressor A Suction/Discharge piping) | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-68.02 | Syst. 68.02 - SMC (HVAC, Gas Compressor A) | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.01 | Syst. 04.01.01 - SMC GTC Package A Fire & Gas detection system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.09 | Syst. 04.01.09 - SMC GTC Package A Turning gear | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.10 | Syst. 04.01.10 - SMC GTC Package A IGV system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.11 | Syst. 04.01.11 - SMC GTC Package A GT Control system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.12 | Syst. 04.01.12 - SMC GTC Package A CC Control system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.13 | Syst. 04.01.13 - SMC GTC Package A Fuel gas system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.14 | Syst. 04.01.14 - SMC GTC Package A Starting system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-04.01.29 | Syst. 04.01.29 - SMC GTC Package A Water washing system | 21 | 2022-02-05 | 2022-02-26 |  | 0%
GC-MC-40.10.06 | Syst. 40.10.06 - SMC LP-40903 Essential building room heater DB | 21 | 2022-02-10 | 2022-03-03 |  | 0%
GC-MC-40.10.05 | Syst. 40.10.05 - SMC LP-40976A/B LUP-40901A/B power supply B-912 | 21 | 2022-02-10 | 2022-03-03 |  | 0%
GC-MC-40.09.07 | Syst. 40.09.07 - SMC LP-40953 | 21 | 2022-02-10 | 2022-03-03 |  | 0%
GC-MC-40.10.04 | Syst. 40.10.04 - SMC LP-40990 essential aux power | 21 | 2022-02-17 | 2022-03-10 |  | 0%
GC-MC-30.14 | Syst. 30.14 - SMC (Fire & Gas Detection F&G Detection - Substation B-912) | 21 | 2022-03-03 | 2022-03-23 |  | 0%
GC-MC-60.12 | Syst. 60.12 - SMC (Fire Fighting System CO2 Fire Fighting - Substation B-912) | 21 | 2022-03-03 | 2022-03-23 |  | 0%
GC-MC-40.07.05 | Syst. 40.07.05 - SMC LVS-40917 compressor B VFDs | 21 | 2022-03-06 | 2022-03-27 |  | 0%
GC-MC-40.01.11 | Syst. 40.01.11 - SMC (Power Generation Earthing - LER (B-907)) | 21 | 2022-03-12 | 2022-04-01 |  | 0%
GC-MC-41.05 | Syst. 41.05 - SMC HTF Dump Cooler, Distribution to GTCs and Compressor Discharge Coolers | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-41.01 | Syst. 41.01 - SMC (HTF, Hot MEG/Water Package) | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-40.01.12 | Syst. 40.01.12 - SMC (Power Generation Earthing - LER (B-908)) | 21 | 2022-04-16 | 2022-05-06 |  | 0%
GC-MC-68.11 | Syst. 68.11 - SMC (HVAC, SS Building B-912) | 21 | 2022-05-16 | 2022-06-06 |  | 0%
GC-MC-84.11 | Syst. 84.11 - SMC (Substation Building B-912) | 21 | 2022-05-21 | 2022-06-11 |  | 0%
VCR-06 |  | 149 | 2021-11-17 | 2022-04-15 |  | 0%
GC-MC-40.13.02 | Syst. 40.13.02 - SMC ENMC B911 | 21 | 2021-11-17 | 2021-12-08 |  | 0%
GC-MC-40.11.10 | Syst. 40.11.10 - SMC UPS for comppressor B | 21 | 2022-01-10 | 2022-01-31 |  | 0%
GC-MC-40.05.09 | Syst. 40.05.09 - SMC LP-40926A/B LUP-40911A/B power supply LER-907 | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-40.05.08 | Syst. 40.05.08 - SMC LP-40978A/B LUP-40901A/B power supply LER-907 | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-44.05 | Syst. 44.05 - SMC (Fuel/Seal Gas Turbine B) | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.02 | Syst. 04.07.02 - SMC GTC Package B Filter house | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.03 | Syst. 04.07.03 - SMC GTC Package B GT enclosure ventilation system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.04 | Syst. 04.07.04 - SMC GTC Package B CC enclosure ventilation system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.05 | Syst. 04.07.05 - SMC GTC Package B GT enclosure fire fighting system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.06 | Syst. 04.07.06 - SMC GTC Package B CC enclosure fire fighting system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.07 | Syst. 04.07.07 - SMC GTC Package B Compressor Seal gas system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-04.07.08 | Syst. 04.07.08 - SMC GTC GTC Package B Lube oil system | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-40.13.01 | Syst. 40.13.01 - SMC ENMC FAR | 21 | 2022-02-02 | 2022-02-23 |  | 0%
GC-MC-40.01.05 | Syst. 40.01.05 - SMC (Earthing Compressor B) | 21 | 2022-02-08 | 2022-03-01 |  | 0%
GC-MC-40.13.03 | Syst. 40.13.03 - SMC ENMC B912 | 21 | 2022-02-10 | 2022-03-03 |  | 0%
GC-MC-30.11 | Syst. 30.11 - SMC (F & G Detection - LER (B-907) | 21 | 2022-02-19 | 2022-03-12 |  | 0%
GC-MC-60.09 | Syst. 60.09 - SMC (Fire Fighting System CO2 Fire Fighting - LER (B-907)) | 21 | 2022-02-20 | 2022-03-12 |  | 0%
GC-MC-40.05.01 | Syst. 40.05.01 - SMC LSB-40911B switchboard normal | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.02 | Syst. 40.05.02 - SMC LP-40981C normal lighting and small power DB | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.03 | Syst. 40.05.03 - SMC LSB-40922B switchboard essential | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.04 | Syst. 40.05.04 - SMC LP-40997B HVAC DB for compressor building essential | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.05 | Syst. 40.05.05 - SMC LP-40923B 400 V essential for K-04901A (inside building) | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.06 | Syst. 40.05.06 - SMC LP-40922B 400 V essential lighting and small power | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-40.05.07 | Syst. 40.05.07 - SMC LP-40996B HVAC LER | 21 | 2022-02-24 | 2022-03-17 |  | 0%
GC-MC-30.05 | Syst. 30.05 - SMC (F & G Detection - Compressor B and Building) | 21 | 2022-03-10 | 2022-03-31 |  | 0%
GC-MC-84.07 | Syst. 84.07 - SMC (LER Building B-907) | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-68.08 | Syst. 68.08 - SMC (HVAC, LER Building B-907) | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07 | Syst. 04.07 - SMC (Gas Turbine/Compressor/UCP and Auxiliaries B) | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.31 | Syst. 04.31 - SMC GTC package B WHRU system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-41.04 | Syst. 41.04 - SMC (HTF, Hot MEG Turbine B) | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.09 | Syst. 04.07.09 - SMC GTC Package B Turning gear | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.10 | Syst. 04.07.10 - SMC GTC Package B IGV system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.11 | Syst. 04.07.11 - SMC GTC Package GT Control system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.12 | Syst. 04.07.12 - SMC GTC Package CC Control system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.13 | Syst. 04.07.13 - SMC GTC Package B Fuel gas system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.14 | Syst. 04.07.14 - SMC GTC Package B Starting system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-04.07.29 | Syst. 04.07.29 - SMC GTC Package B Water washing system | 21 | 2022-03-11 | 2022-04-01 |  | 0%
GC-MC-68.03 | Syst. 68.03 - SMC (HVAC, Gas Compressor B) | 21 | 2022-03-16 | 2022-04-06 |  | 0%
GC-MC-84.03 | Syst. 84.03 - SMC (Gas Compressor B Building) | 21 | 2022-03-25 | 2022-04-15 |  | 0%
GC-MC-04.07.01 | Syst. 04.07.01 - SMC GTC Package B Fire & Gas detection system | 21 | 2022-03-25 | 2022-04-15 |  | 0%
VCR-07 |  | 80 | 2022-03-12 | 2022-05-31 |  | 0%
GC-MC-44.06 | Syst. 44.06 - SMC (Fuel/Seal Gas Turbine C) | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.02 | Syst. 04.13.02 - SMC GTC Package C Filter house | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.03 | Syst. 04.13.03 - SMC GTC Package C GT enclosure ventilation system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.04 | Syst. 04.13.04 - SMC GTC Package C CC enclosure ventilation system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.05 | Syst. 04.13.05 - SMC GTC Package C GT enclosure fire fighting system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.06 | Syst. 04.13.06 - SMC GTC Package C CC enclosure fire fighting system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.07 | Syst. 04.13.07 - SMC GTC Package C Compressor Seal gas system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-04.13.08 | Syst. 04.13.08 - SMC GTC Package C Lube oil system | 21 | 2022-03-12 | 2022-04-02 |  | 0%
GC-MC-40.06.07 | Syst. 40.06.07 - SMC LP-40996C HVAC LER | 21 | 2022-03-21 | 2022-04-11 |  | 0%
GC-MC-30.12 | Syst. 30.12 - SMC (F & G Detection - LER (B-908) | 21 | 2022-03-21 | 2022-04-11 |  | 0%
GC-MC-40.01.06 | Syst. 40.01.06 - SMC (Earthing Compressor C) | 21 | 2022-03-21 | 2022-04-11 |  | 0%
GC-MC-60.10 | Syst. 60.10 - SMC (Fire Fighting System CO2 Fire Fighting - LER (B-908)) | 21 | 2022-03-22 | 2022-04-11 |  | 0%
GC-MC-68.04 | Syst. 68.04 - SMC (HVAC, Gas Compressor C) | 21 | 2022-03-28 | 2022-04-18 |  | 0%
GC-MC-40.06.01 | Syst. 40.06.01 - SMC LSB-40911C switchboard normal | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.06.02 | Syst. 40.06.02 - SMC LP-40981C normal lighting and small power DB | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.06.03 | Syst. 40.06.03 - SMC LSB-40922C switchboard essential | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.06.04 | Syst. 40.06.04 - SMC LP-40997C HVAC DB for compressor building essential | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.06.05 | Syst. 40.06.05 - SMC LP-40923C 400 V essential for K-04901A (inside building) | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.06.06 | Syst. 40.06.06 - SMC LP-40922C 400 V essential lighting and small power | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-40.11.11 | Syst. 40.11.11 - SMC UPS for comppressor C | 21 | 2022-04-05 | 2022-04-26 |  | 0%
GC-MC-68.09 | Syst. 68.09 - SMC (HVAC, LER Building B-908) | 21 | 2022-04-20 | 2022-05-11 |  | 0%
GC-MC-04.13 | Syst. 04.13 - SMC (Gas Turbine/Compressor/UCP and Auxiliaries C) | 21 | 2022-04-20 | 2022-05-11 |  | 0%
GC-MC-40.06.08 | Syst. 40.06.08 - SMC LP-40979A/B LUP-40901A/B power supply LER-908 | 21 | 2022-04-20 | 2022-05-11 |  | 0%
GC-MC-40.06.09 | Syst. 40.06.09 - SMC LP-40927A/B LUP-40911A/B power supply LER-908 | 21 | 2022-04-20 | 2022-05-11 |  | 0%
GC-MC-84.08 | Syst. 84.08 - SMC (LER Building B-908) | 21 | 2022-04-24 | 2022-05-15 |  | 0%
GC-MC-30.06 | Syst. 30.06 - SMC (F & G Detection - Compressor C and Building) | 21 | 2022-04-24 | 2022-05-15 |  | 0%
GC-MC-84.04 | Syst. 84.04 - SMC (Gas Compressor C Building) | 21 | 2022-04-30 | 2022-05-21 |  | 0%
GC-MC-04.13.01 | Syst. 04.13.01 - SMC GTC Package C Fire & Gas detection system | 21 | 2022-04-30 | 2022-05-21 |  | 0%
GC-MC-04.13.09 | Syst. 04.13.09 - SMC GTC Package C Turning gear | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.10 | Syst. 04.13.10 - SMC GTC Package C IGV system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.11 | Syst. 04.13.11 - SMC GTC Package C GT Control system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.12 | Syst. 04.13.12 - SMC GTC Package C CC Control system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.13 | Syst. 04.13.13 - SMC GTC Package C Fuel gas system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.14 | Syst. 04.13.14 - SMC GTC Package C Starting system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
GC-MC-04.13.29 | Syst. 04.13.29 - SMC GTC Package C Water washing system | 21 | 2022-05-10 | 2022-05-31 |  | 0%
VCR-08 |  | 180 | 2021-11-13 | 2022-05-11 |  | 0%
GC-MC-40.13.04 | Syst. 40.13.04 - SMC (Power Generation ENMC LER-906) | 21 | 2021-11-13 | 2021-12-03 |  | 0%
GC-MC-40.01.07 | Syst. 40.01.07 - SMC (Earthing Separation Unit 1) | 21 | 2022-01-01 | 2022-01-22 |  | 0%
GC-MC-30.07 | Syst. 30.07 - SMC (F & G Detection - Inlet Receiver Area Train 1) | 21 | 2022-01-23 | 2022-02-13 |  | 0%
GC-MC-04.19 | Syst. 04.19 - SMC (Gas Compression, Common Suction header) | 21 | 2022-02-09 | 2022-03-02 |  | 0%
GC-MC-04.20 | Syst. 04.20 - SMC (Gas Compression, Common Discharge Header) | 21 | 2022-02-09 | 2022-03-02 |  | 0%
GC-MC-09.03 | Syst. 09.03 - SMC (Train 1 Inlet Receiver) | 21 | 2022-03-06 | 2022-03-27 |  | 0%
GC-MC-40.13.05 | Syst. 40.13.05 - SMC (Power Generation ENMC LER-907) | 21 | 2022-03-07 | 2022-03-27 |  | 0%
GC-MC-05.02 | Syst. 05.02 - SMC (Condensate Treating for Train 1 and Suction Scrubbers Condensate, Tie-in) | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-40.13.06 | Syst. 40.13.06 - SMC (Power Generation ENMC LER-908) | 21 | 2022-04-21 | 2022-05-11 |  | 0%
VCR-09 |  | 413 | 2021-06-04 | 2022-07-21 |  | 0%
GC-MC-60.06 | Syst. 60.06 - SMC (Fire Fighting System OPF Tie-In TP-161A&B Brownfield Scope - North Fire Water System) | 21 | 2021-06-04 | 2021-06-24 |  | 0%
GC-MC-74.05.01 | Syst. 74.05.01 - SMC (Telecommunications PAGA System for BLS) | 21 | 2021-06-10 | 2021-06-30 |  | 0%
GC-MC-09.11 | Syst. 09.11 - SMC Portable Methanol Injection Package | 21 | 2021-11-14 | 2021-12-05 |  | 0%
GC-MC-47.07 | Syst. 47.07 - SMC Utility Air & All Area | 21 | 2021-11-14 | 2021-12-05 |  | 0%
GC-MC-41.02 | Syst. 41.02- SMC HTF Distribution to Maintenance Building | 21 | 08-Dec-21* | 2021-12-29 |  | 0%
GC-MC-74.05 | Syst. 74.05 - SMC PAGA System | 21 | 2021-12-22 | 2022-01-12 |  | 0%
GC-MC-74.04 | Syst. 74.04 - SMC Access Control System | 21 | 2021-12-22 | 2022-01-12 |  | 0%
GC-MC-40.01.18 | Syst. 40.01.18 - SMC (Power Generation Earthing - Open Drain Area) | 21 | 2022-01-14 | 2022-02-03 |  | 0%
GC-MC-40.01.08 | Syst. 40.01.08 - SMC (Earthing Separation Unit 2) | 21 | 2022-01-18 | 2022-02-08 |  | 0%
GC-MC-09.02 | Syst. 09.02 - SMC (Parking Loop Return Line) | 21 | 2022-02-22 | 2022-03-15 |  | 0%
GC-MC-17.02 | Syst. 17.02 - SMC Chemical Distribution Train1/2 (Demulsifier) | 21 | 2022-02-22 | 2022-03-15 |  | 0%
GC-MC-22.02 | Syst. 22.02 - SMC (Open Drains, Buffer Sump and Piping) | 21 | 2022-02-22 | 2022-03-15 |  | 0%
GC-MC-56.05 | Syst. 56.05 - SMC (Rich MEG Return Line (T1/T2)) | 21 | 2022-02-22 | 2022-03-15 |  | 0%
GC-MC-30.08 | Syst. 30.08 - SMC (F & G Detection - Maintenance, Paint & Oil Storage) | 21 | 01-Mar-22* | 2022-03-22 |  | 0%
GC-MC-48.03 | Syst. 48.03 - SMC N2 Distribution - Equipment Purge | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-40.03.21 | Syst. 40.03.21 - SMC LP-40982B Maintenance building DB | 21 | 2022-03-31 | 2022-04-28 |  | 0%
GC-MC-40.03.20 | Syst. 40.03.20 - SMC LP-40907 Maintenance building DB | 21 | 2022-03-31 | 2022-04-28 |  | 0%
GC-MC-74.02 | Syst. 74.02 - SMC Telephone System | 21 | 2022-04-24 | 2022-05-15 |  | 0%
GC-MC-56.02 | Syst. 56.02 - SMC MEG Injection - T1 & T2 | 21 | 2022-04-25 | 2022-05-16 |  | 0%
GC-MC-74.03 | Syst. 74.03 - SMC CCTV System | 21 | 2022-05-31 | 2022-06-21 |  | 0%
GC-MC-68.05 | Syst. 68.05 - SMC (HVAC, Maintenance, Storage Building) | 21 | 2022-06-30 | 2022-07-21 |  | 0%
GC-MC-84.05 | Syst. 84.05 - SMC (Plant Buildings, Maintenance, Storage Building) | 21 | 2022-06-30 | 2022-07-21 |  | 0%
VCR-10 |  | 150 | 2021-12-17 | 2022-05-16 |  | 0%
GC-MC-26.01 | Syst. 26.01 - SMC (Sewage Treatment (FAR)) | 21 | 2021-12-17 | 2022-01-07 |  | 0%
GC-MC-04.09 | Syst. 04.09 - SMC Compressor B Suction/Discharge piping | 21 | 2022-01-25 | 2022-02-15 |  | 0%
GC-MC-05.03 | Syst. 05.03 - SMC Train 2 Condensate | 21 | 2022-02-22 | 2022-03-15 |  | 0%
GC-MC-30.09 | Syst. 30.09 - SMC (F & G Detection - Inlet Receiver Area Train 2) | 21 | 2022-03-13 | 2022-04-03 |  | 0%
GC-MC-04.15 | Syst. 04.15 - SMC Compressor C Suction/Discharge piping | 21 | 2022-03-29 | 2022-04-19 |  | 0%
GC-MC-09.04 | Syst. 09.04 - SMC Train 2 Inlet Receiver | 21 | 2022-04-25 | 2022-05-16 |  | 0%
AdditionalSOFTMCMILESTONES |  | 163 | 2021-06-15 | 2021-11-25 |  | 0%
MC-BLC-HD-001 | BLS Piping Hydrotest | 0 |  | 2021-06-15 |  | 0%
MC-GCA-HD-001 | String A Process Pipelines Hydrotest | 0 |  | 2021-11-25 |  | 0%
ENGINEERING |  | 708 | 2019-08-01 | 2021-07-08 |  | 0%
COMMONAREA |  | 671 | 2019-08-03 | 2021-06-04 |  | 0%
CIVILWORKS |  | 118 | 2019-12-14 | 2020-03-10 |  | 0%
EN-CMN-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 70% | 0 |  | 2019-12-14 |  | 0%
EN-CMN-CS-1010 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-03-10 |  | 0%
UNDERGROUNDPIPINGWORKS |  | 74 | 2019-08-03 | 2019-10-15 |  | 0%
EN-CMN-UG-1000 | U/G Piping Isometrics, IFC 30% | 0 |  | 2019-08-03 |  | 0%
EN-CMN-UG-1010 | U/G Piping Isometrics, IFC 60% | 0 |  | 2019-08-16 |  | 0%
EN-CMN-UG-1020 | U/G Piping Isometrics, IFC 100% | 0 |  | 2019-10-15 |  | 0%
ELECTRICALWORKS |  | 398 | 2020-05-01 | 2021-06-04 |  | 0%
EN-CMN-EL-1000 | Electrical dwgs, IFC 30% | 0 |  | 2020-05-01 |  | 0%
EN-CMN-EL-1010 | Electrical dwgs, IFC 60% | 0 |  | 2020-05-14 |  | 0%
EN-CMN-EL-1020 | Electrical dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENTATIONWORKS |  | 405 | 2020-04-10 | 2021-06-04 |  | 0%
EN-CMN-IN-1000 | Instrumentation dwgs, IFC 30% | 0 |  | 2020-04-10 |  | 0%
EN-CMN-IN-1010 | Instrumentation dwgs, IFC 60% | 0 |  | 2020-04-24 |  | 0%
EN-CMN-IN-1020 | Instrumentation dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
FIELDAUXILLARYROOM(FAR)-AREA |  | 594 | 2019-10-18 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2020-01-15 | 2020-01-15 |  | 0%
EN-FAR-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-01-15 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2019-10-18 | 2019-10-18 |  | 0%
EN-FAR-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2019-10-18 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 294 | 2020-04-26 | 2021-06-04 |  | 0%
EN-FAR-PI-1000 | A/G Piping Isometrics, IFC 40% | 0 |  | 2020-04-26 |  | 0%
EN-FAR-PI-1010 | A/G Piping Isometrics, IFC 100% | 0 |  | 2021-06-04 |  | 0%
HVAC |  | 162 | 2020-05-01 | 2020-10-10 |  | 0%
EN-FAR-HV-1000 | HVAC Drawings, IFC 40% | 0 |  | 2020-05-01 |  | 0%
EN-FAR-HV-1010 | HVAC Drawings, IFC 100% | 0 |  | 2020-10-10 |  | 0%
ELECTRICALWORKS |  | 398 | 2020-05-01 | 2021-06-04 |  | 0%
EN-FAR-EL-1000 | Electrical dwgs, IFC 40% | 0 |  | 2020-05-01 |  | 0%
EN-FAR-EL-1010 | Electrical dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENTATIONWORKS |  | 419 | 2020-04-10 | 2021-06-04 |  | 0%
EN-FAR-IN-1000 | Instrumentation dwgs, IFC 40% | 0 |  | 2020-04-10 |  | 0%
EN-FAR-IN-1010 | Instrumentation dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
GASCOMPRESSOR&LERBUILDING-A |  | 334 | 2019-08-01 | 2020-09-10 |  | 0%
CIVILWORKS |  | 2 | 2019-10-14 | 2019-10-14 |  | 0%
EN-GCA-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% COMPRESSOR BUILDING | 0 |  | 2019-10-14 |  | 0%
EN-GCA-CS-1010 | Foundation and Pre-Cast Concrete Drawings - IFC 100% LER | 0 |  | 2019-10-14 |  | 0%
STEELSTRUCTUREWORKS |  | 24 | 2020-02-28 | 2020-03-23 |  | 0%
EN-GCA-CS-1030 | LER Building - Structure & Fireproof IFC 100% | 0 |  | 2020-02-28 |  | 0%
EN-GCA-CS-1020 | Gas Compressor - Structure & Fireproof IFC 100% | 0 |  | 2020-03-23 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2019-08-01 | 2019-08-01 |  | 0%
EN-GCA-PI-1000 | Gas Compressor - A/G Piping Isometrics, IFC 100% | 0 |  | 2019-08-01 |  | 0%
HVAC |  | 5 | 2020-05-10 | 2020-05-15 |  | 0%
EN-GCA-HV-1000 | Gas Compressor - HVAC Drawings, IFC 100% | 0 |  | 2020-05-10 |  | 0%
EN-GCA-HV-1010 | LER Building - HVAC Drawings, IFC 100% | 0 |  | 2020-05-15 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-04-20 | 2020-04-20 |  | 0%
EN-GCA-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-04-20 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-10 | 2020-09-10 |  | 0%
EN-GCA-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-10 |  | 0%
GASCOMPRESSOR&LERBUILDING-B |  | 386 | 2019-09-23 | 2020-10-13 |  | 0%
CIVILWORKS |  | 37 | 2019-09-23 | 2019-10-30 |  | 0%
EN-GCB-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% COMPRESSOR BUILDING | 0 |  | 2019-09-23 |  | 0%
EN-GCB-CS-1010 | Foundation and Pre-Cast Concrete Drawings - IFC 100% LER | 0 |  | 2019-10-30 |  | 0%
STEELSTRUCTUREWORKS |  | 7 | 2020-04-13 | 2020-04-20 |  | 0%
EN-GCB-CS-1030 | LER Building - Structure & Fireproof IFC 100% | 0 |  | 2020-04-13 |  | 0%
EN-GCB-CS-1020 | Gas Compressor - Structure & Fireproof IFC 100% | 0 |  | 2020-04-20 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-05-14 | 2020-05-14 |  | 0%
EN-GCB-PI-1000 | Gas Compressor - A/G Piping Isometrics, IFC 100% | 0 |  | 2020-05-14 |  | 0%
HVAC |  | 16 | 2020-04-22 | 2020-05-08 |  | 0%
EN-GCB-HV-1010 | LER Building - HVAC Drawings, IFC 100% | 0 |  | 2020-04-22 |  | 0%
EN-GCB-HV-1000 | Gas Compressor - HVAC Drawings, IFC 100% | 0 |  | 2020-05-08 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-08-31 | 2020-08-31 |  | 0%
EN-GCB-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-13 | 2020-10-13 |  | 0%
EN-GCB-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-10-13 |  | 0%
TSFAREAS |  | 0 | 2019-08-01 | 2019-08-01 |  | 0%
EN-TSF-CS-1000 | Civil Works Drawings | 0 |  | 2019-08-01 |  | 0%
GASCOMPRESSOR&LERBUILDING-C |  | 377 | 2019-10-03 | 2020-10-14 |  | 0%
CIVILWORKS |  | 30 | 2019-10-03 | 2019-11-02 |  | 0%
EN-GCC-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% COMPRESSOR BUILDING | 0 |  | 2019-10-03 |  | 0%
EN-GCC-CS-1010 | Foundation and Pre-Cast Concrete Drawings - IFC 100% LER | 0 |  | 2019-11-02 |  | 0%
STEELSTRUCTUREWORKS |  | 57 | 2020-03-25 | 2020-05-21 |  | 0%
EN-GCC-CS-1020 | Gas Compressor - Structure & Fireproof IFC 100% | 0 |  | 2020-03-25 |  | 0%
EN-GCC-CS-1030 | LER Building - Structure & Fireproof IFC 100% | 0 |  | 2020-05-21 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-05-24 | 2020-05-24 |  | 0%
EN-GCC-PI-1000 | Gas Compressor - A/G Piping Isometrics, IFC 100% | 0 |  | 2020-05-24 |  | 0%
HVAC |  | 21 | 2020-05-03 | 2020-05-24 |  | 0%
EN-GCC-HV-1000 | Gas Compressor - HVAC Drawings, IFC 100% | 0 |  | 2020-05-03 |  | 0%
EN-GCC-HV-1010 | LER Building - HVAC Drawings, IFC 100% | 0 |  | 2020-05-24 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-20 | 2020-09-20 |  | 0%
EN-GCC-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-09-20 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-14 | 2020-10-14 |  | 0%
EN-GCC-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-10-14 |  | 0%
COMPRESSORMAINPIPERACKA |  | 263 | 2019-09-10 | 2020-05-30 |  | 0%
CIVILWORKS |  | 0 | 2019-09-10 | 2019-09-10 |  | 0%
EN-GCA-CS-1100 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-09-10 |  | 0%
STEELSTRUCTUREWORKS |  | 130 | 2019-10-20 | 2020-02-25 |  | 0%
EN-GCA-CS-1110 | Structure & Fireproof IFC 30% | 0 |  | 2019-10-20 |  | 0%
EN-GCA-CS-1120 | Structure & Fireproof IFC 60% | 0 |  | 2019-11-03 |  | 0%
EN-GCA-CS-1130 | Structure & Fireproof IFC 100% | 0 |  | 2020-02-25 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 75 | 2020-03-12 | 2020-04-10 |  | 0%
EN-GCA-PI-1100 | A/G Piping Isometrics, IFC 30% | 0 |  | 2020-03-12 |  | 0%
EN-GCA-PI-1110 | A/G Piping Isometrics, IFC 60% | 0 |  | 2020-03-26 |  | 0%
EN-GCA-PI-1120 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-04-10 |  | 0%
ELECTRICALWORKS |  | 21 | 2020-04-11 | 2020-05-02 |  | 0%
EN-GCA-EL-1100 | Electrical dwgs, IFC 30% | 0 |  | 2020-04-11 |  | 0%
EN-GCA-EL-1110 | Electrical dwgs, IFC 60% | 0 |  | 2020-04-25 |  | 0%
EN-GCA-EL-1120 | Electrical dwgs, IFC 100% | 0 |  | 2020-05-02 |  | 0%
INSTRUMENTATIONWORKS |  | 28 | 2020-05-02 | 2020-05-30 |  | 0%
EN-GCA-IN-1100 | Instrumentation dwgs, IFC 30% | 0 |  | 2020-05-02 |  | 0%
EN-GCA-IN-1110 | Instrumentation dwgs, IFC 60% | 0 |  | 2020-05-16 |  | 0%
EN-GCA-IN-1120 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-05-30 |  | 0%
COMPRESSORMAINPIPERACKB |  | 231 | 2019-10-10 | 2020-05-28 |  | 0%
CIVILWORKS |  | 0 | 2019-10-10 | 2019-10-10 |  | 0%
EN-GCB-CS-1100 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-10-10 |  | 0%
STEELSTRUCTUREWORKS |  | 107 | 2019-10-29 | 2020-02-13 |  | 0%
EN-GCB-CS-1110 | Structure & Fireproof IFC 30% | 0 |  | 2019-10-29 |  | 0%
EN-GCB-CS-1120 | Structure & Fireproof IFC 60% | 0 |  | 2019-12-10 |  | 0%
EN-GCB-CS-1130 | Structure & Fireproof IFC 100% | 0 |  | 2020-02-13 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 28 | 2020-04-30 | 2020-05-28 |  | 0%
EN-GCB-PI-1100 | A/G Piping Isometrics, IFC 30% | 0 |  | 2020-04-30 |  | 0%
EN-GCB-PI-1110 | A/G Piping Isometrics, IFC 60% | 0 |  | 2020-05-14 |  | 0%
EN-GCB-PI-1120 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-05-28 |  | 0%
ELECTRICALWORKS |  | 28 | 2020-03-17 | 2020-04-14 |  | 0%
EN-GCB-EL-1100 | Electrical dwgs, IFC 30% | 0 |  | 2020-03-17 |  | 0%
EN-GCB-EL-1110 | Electrical dwgs, IFC 60% | 0 |  | 2020-03-31 |  | 0%
EN-GCB-EL-1120 | Electrical dwgs, IFC 100% | 0 |  | 2020-04-14 |  | 0%
INSTRUMENTATIONWORKS |  | 29 | 2020-03-06 | 2020-04-04 |  | 0%
EN-GCB-IN-1100 | Instrumentation dwgs, IFC 30% | 0 |  | 2020-03-06 |  | 0%
EN-GCB-IN-1110 | Instrumentation dwgs, IFC 60% | 0 |  | 2020-03-20 |  | 0%
EN-GCB-IN-1120 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-04-04 |  | 0%
COMPRESSORMAINPIPERACKC |  | 600 | 2019-10-12 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2019-10-12 | 2019-10-12 |  | 0%
EN-GCC-CS-1100 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-10-12 |  | 0%
STEELSTRUCTUREWORKS |  | 29 | 2020-03-16 | 2020-04-14 |  | 0%
EN-GCC-CS-1110 | Structure & Fireproof IFC 30% | 0 |  | 2020-03-16 |  | 0%
EN-GCC-CS-1120 | Structure & Fireproof IFC 60% | 0 |  | 2020-03-30 |  | 0%
EN-GCC-CS-1130 | Structure & Fireproof IFC 100% | 0 |  | 2020-04-14 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 29 | 2020-03-16 | 2020-04-14 |  | 0%
EN-GCC-PI-1100 | A/G Piping Isometrics, IFC 30% | 0 |  | 2020-03-16 |  | 0%
EN-GCC-PI-1110 | A/G Piping Isometrics, IFC 60% | 0 |  | 2020-03-30 |  | 0%
EN-GCC-PI-1120 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-04-14 |  | 0%
ELECTRICALWORKS |  | 399 | 2020-04-30 | 2021-06-04 |  | 0%
EN-GCC-EL-1100 | Electrical dwgs, IFC 30% | 0 |  | 2020-04-30 |  | 0%
EN-GCC-EL-1110 | Electrical dwgs, IFC 60% | 0 |  | 2020-05-13 |  | 0%
EN-GCC-EL-1120 | Electrical dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENTATIONWORKS |  | 379 | 2020-05-20 | 2021-06-04 |  | 0%
EN-GCC-IN-1100 | Instrumentation dwgs, IFC 30% | 0 |  | 2020-05-20 |  | 0%
EN-GCC-IN-1110 | Instrumentation dwgs, IFC 60% | 0 |  | 2020-08-20 |  | 0%
EN-GCC-IN-1120 | Instrumentation dwgs, IFC 100% | 0 |  | 2021-06-04 |  | 0%
NS-PIPERACK |  | 383 | 2019-09-02 | 2020-09-19 |  | 0%
CIVILWORKS |  | 0 | 2019-09-02 | 2019-09-02 |  | 0%
EN-MPR-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-09-02 |  | 0%
STEELSTRUCTUREWORKS |  | 30 | 2019-10-21 | 2019-11-20 |  | 0%
EN-MPR-CS-1010 | Structure & Fireproof IFC 40% | 0 |  | 2019-10-21 |  | 0%
EN-MPR-CS-1020 | Structure & Fireproof IFC 100% | 0 |  | 2019-11-20 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-05-20 | 2020-05-20 |  | 0%
EN-MPR-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-05-20 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-07-10 | 2020-07-10 |  | 0%
EN-MPR-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-07-10 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-19 | 2020-09-19 |  | 0%
EN-MPR-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-19 |  | 0%
INSTRUMENT&NITROGENAREA |  | 156 | 2020-02-06 | 2020-06-24 |  | 0%
CIVILWORKS |  | 0 | 2020-02-06 | 2020-02-06 |  | 0%
EN-INA-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-02-06 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-05-10 | 2020-05-10 |  | 0%
EN-INA-CS-1010 | Structure & Fireproof IFC Last | 0 |  | 2020-05-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-05-21 | 2020-05-21 |  | 0%
EN-INA-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-05-21 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-06-11 | 2020-06-11 |  | 0%
EN-INA-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-06-11 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-06-24 | 2020-06-24 |  | 0%
EN-INA-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-06-24 |  | 0%
EMERGENCYDIESELGENERATOR |  | 267 | 2019-12-14 | 2020-09-06 |  | 0%
CIVILWORKS |  | 0 | 2019-12-14 | 2019-12-14 |  | 0%
EN-EDG-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-12-14 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-04-30 | 2020-04-30 |  | 0%
EN-EDG-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-04-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-07-12 | 2020-07-12 |  | 0%
EN-EDG-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-07-12 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-07-18 | 2020-07-18 |  | 0%
EN-EDG-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-07-18 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-06 | 2020-09-06 |  | 0%
EN-EDG-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-06 |  | 0%
MAINTENANCEBUIDING |  | 196 | 2020-03-28 | 2020-10-10 |  | 0%
CIVILWORKS |  | 0 | 2020-03-28 | 2020-03-28 |  | 0%
EN-MBL-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-03-28 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-08-28 | 2020-08-28 |  | 0%
EN-MBL-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-08-28 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-28 | 2020-09-28 |  | 0%
EN-MBL-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-09-28 |  | 0%
HVAC |  | 0 | 2020-10-10 | 2020-10-10 |  | 0%
EN-MBL-HV-1000 | HVAC Drawings, IFC 100% | 0 |  | 2020-10-10 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-10-02 | 2020-10-02 |  | 0%
EN-MBL-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-10-02 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-02 | 2020-10-02 |  | 0%
EN-MBL-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-10-02 |  | 0%
OPENDRAINAREA |  | 246 | 2020-06-30 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2020-06-30 | 2020-06-30 |  | 0%
EN-ODA-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-06-30 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-10-27 | 2020-10-27 |  | 0%
EN-ODA-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-10-27 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-28 | 2020-10-28 |  | 0%
EN-ODA-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-10-28 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-ODA-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-ODA-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
GASSEPARATION-1 |  | 588 | 2019-10-24 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2019-10-24 | 2019-10-24 |  | 0%
EN-GS1-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-10-24 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-09-26 | 2020-09-26 |  | 0%
EN-GS1-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-09-26 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-28 | 2020-10-28 |  | 0%
EN-GS1-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-10-28 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-GS1-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-GS1-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
GASSEPARATION-2 |  | 619 | 2019-10-28 | 2021-07-08 |  | 0%
CIVILWORKS |  | 0 | 2019-10-28 | 2019-10-28 |  | 0%
EN-GS2-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-10-28 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-GS2-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 04-Jun-21* |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-19 | 2020-10-19 |  | 0%
EN-GS2-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-10-19 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-23 | 2021-06-23 |  | 0%
EN-GS2-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 23-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-07-08 | 2021-07-08 |  | 0%
EN-GS2-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 08-Jul-21* |  | 0%
GCA-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 222 | 2020-02-06 | 2020-09-15 |  | 0%
CIVILWORKS |  | 0 | 2020-02-06 | 2020-02-06 |  | 0%
EN-GCA-CS-1200 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-02-06 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-04-17 | 2020-04-17 |  | 0%
EN-GCA-CS-1210 | Structure & Fireproof IFC 100% | 0 |  | 2020-04-17 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-08-05 | 2020-08-05 |  | 0%
EN-GCA-PI-1200 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-08-05 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-05 | 2020-09-05 |  | 0%
EN-GCA-EL-1200 | Electrical dwgs, IFC 100% | 0 |  | 2020-09-05 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-15 | 2020-09-15 |  | 0%
EN-GCA-IN-1200 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-15 |  | 0%
GCB-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 146 | 2020-01-23 | 2020-09-16 |  | 0%
CIVILWORKS |  | 0 | 2020-01-23 | 2020-01-23 |  | 0%
EN-GCB-CS-1200 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-01-23 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-05-30 | 2020-05-30 |  | 0%
EN-GCB-CS-1210 | Structure & Fireproof IFC 100% | 0 |  | 2020-05-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-08-05 | 2020-08-05 |  | 0%
EN-GCB-PI-1200 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-08-05 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-05 | 2020-09-05 |  | 0%
EN-GCB-EL-1200 | Electrical dwgs, IFC 100% | 0 |  | 2020-09-05 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-16 | 2020-09-16 |  | 0%
EN-GCB-IN-1200 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-16 |  | 0%
GCC-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 187 | 2020-03-14 | 2020-09-17 |  | 0%
CIVILWORKS |  | 0 | 2020-03-14 | 2020-03-14 |  | 0%
EN-GCC-CS-1200 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-03-14 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-05-30 | 2020-05-30 |  | 0%
EN-GCC-CS-1210 | Structure & Fireproof IFC 100% | 0 |  | 2020-05-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-08-05 | 2020-08-05 |  | 0%
EN-GCC-PI-1200 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-08-05 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-05 | 2020-09-05 |  | 0%
EN-GCC-EL-1200 | Electrical dwgs, IFC 100% | 0 |  | 2020-09-05 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-17 | 2020-09-17 |  | 0%
EN-GCC-IN-1200 | Instrumentation dwgs, IFC 100% | 0 |  | 2020-09-17 |  | 0%
HPFLAREAREA |  | 396 | 2019-12-01 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2019-12-01 | 2019-12-01 |  | 0%
EN-HPF-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-12-01 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-09-10 | 2020-09-10 |  | 0%
EN-HPF-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-09-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-28 | 2020-10-28 |  | 0%
EN-HPF-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-10-28 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-10-30 | 2020-10-30 |  | 0%
EN-HPF-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 2020-10-30 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-HPF-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
FUELSEALGAS |  | 536 | 2019-12-15 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2019-12-15 | 2019-12-15 |  | 0%
EN-FSG-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-12-15 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-06-11 | 2020-06-11 |  | 0%
EN-FSG-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-06-11 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-20 | 2020-09-20 |  | 0%
EN-FSG-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-09-20 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-FSG-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-FSG-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
HEATTRANSFERAREA |  | 469 | 2020-02-20 | 2021-06-04 |  | 0%
CIVILWORKS |  | 0 | 2020-02-20 | 2020-02-20 |  | 0%
EN-HTF-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2020-02-20 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-07-14 | 2020-07-14 |  | 0%
EN-HTF-CS-1010 | Structure & Fireproof IFC 100% | 0 |  | 2020-07-14 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-28 | 2020-09-28 |  | 0%
EN-HTF-PI-1000 | A/G Piping Isometrics, IFC 100% | 0 |  | 2020-09-28 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-HTF-EL-1000 | Electrical dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
EN-HTF-IN-1000 | Instrumentation dwgs, IFC 100% | 0 |  | 04-Jun-21* |  | 0%
SUBSTATIONBUILDINGS(911&912) |  | 272 | 2019-08-01 | 2020-07-07 |  | 0%
CIVILWORKS |  | 27 | 2019-08-01 | 2019-12-05 |  | 0%
EN-TSS-CS-1010 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-08-01 |  | 0%
EN-TSS-CS-1000 | Foundation and Pre-Cast Concrete Drawings - IFC 100% | 0 |  | 2019-12-05 |  | 0%
STEELSTRUCTUREWORKS |  | 61 | 2020-01-20 | 2020-03-21 |  | 0%
EN-TSS-CS-1020 | Substation 911 - Structure & Fireproof IFC 100% | 0 |  | 2020-01-20 |  | 0%
EN-TSS-CS-1030 | Substation 912 - Structure & Fireproof IFC 100% | 0 |  | 2020-03-21 |  | 0%
HVAC |  | 27 | 2020-05-08 | 2020-06-30 |  | 0%
EN-TSS-HV-1000 | Substation 911 - HVAC Drawings, IFC 100% | 0 |  | 2020-05-08 |  | 0%
EN-TSS-HV-1010 | Substation 912 - HVAC Drawings, IFC 100% | 0 |  | 2020-06-30 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-05-10 | 2020-05-10 |  | 0%
EN-TSS-EL-1010 | Substation 912 - Electrical dwgs, IFC 100% | 0 |  | 2020-05-10 |  | 0%
EN-TSS-EL-1000 | Substation 911 - Electrical dwgs, IFC 100% | 0 |  | 2020-05-10 |  | 0%
INSTRUMENTATIONWORKS |  | 57 | 2020-07-07 | 2020-07-07 |  | 0%
EN-TSS-IN-1010 | Substation 912 - Instrumentation dwgs, IFC 100% | 0 |  | 2020-07-07 |  | 0%
EN-TSS-IN-1000 | Substation 911 - Instrumentation dwgs, IFC 100% | 0 |  | 2020-07-07 |  | 0%
PROCUREMENT |  | 700 | 2019-10-13 | 2021-07-01 |  | 0%
COMMONAREA |  | 413 | 2019-10-13 | 2020-08-31 |  | 0%
UNDERGROUNDPIPINGWORKS |  | 241 | 2019-10-13 | 2020-06-10 |  | 0%
PRO-CMN-UG-1000 | U/G Piping Bulk Delivery 30% | 0 |  | 2019-10-13 |  | 0%
PRO-CMN-UG-1010 | U/G Piping Bulk Delivery 60% | 0 |  | 2019-10-27 |  | 0%
PRO-CMN-UG-1020 | U/G Piping Bulk Delivery 100% | 0 |  | 2020-06-10 |  | 0%
ELECTRICALWORKS |  | 190 | 2020-05-23 | 2020-08-31 |  | 0%
PRO-CMN-EL-1000 | Electrical Bulk Delivery (excl. EHT) 30% | 0 |  | 2020-05-23 |  | 0%
PRO-CMN-EL-1010 | Electrical Bulk Delivery (excl. EHT) 60% | 0 |  | 2020-06-23 |  | 0%
PRO-CMN-EL-1020 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
FIELDAUXILLARYROOM(FAR)-AREA |  | 580 | 2019-11-01 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 171 | 2019-11-01 | 2020-05-20 |  | 0%
PRO-FAR-CS-1000 | Delivery of steel structure to the site 40% | 0 |  | 2019-11-01 |  | 0%
PRO-FAR-CS-1010 | Delivery of steel structure to the site 100% | 0 |  | 2020-05-20 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 328 | 2020-07-10 | 2021-06-04 |  | 0%
PRO-FAR-PI-1000 | A/G Piping Bulk Delivery 40% | 0 |  | 2020-07-10 |  | 0%
PRO-FAR-PI-1010 | A/G Piping Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
HVACWORKS |  | 384 | 2020-05-15 | 2021-06-04 |  | 0%
PRO-FAR-HV-1000 | HVAC Material Delivery 40% | 0 |  | 2020-05-15 |  | 0%
PRO-FAR-HV-1010 | HVAC Material Delivery 100% | 0 |  | 2021-06-04 |  | 0%
ELECTRICALWORKS |  | 136 | 2020-06-15 | 2020-08-31 |  | 0%
PRO-FAR-EL-1000 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 2020-06-15 |  | 0%
PRO-FAR-EL-1010 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 14 | 2020-08-31 | 2020-09-30 |  | 0%
PRO-FAR-IN-1000 | Instrumentation Bulk Delivery 40% | 0 |  | 2020-08-31 |  | 0%
PRO-FAR-IN-1010 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
GASCOMPRESSOR&LERBUILDING-A |  | 469 | 2020-02-20 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 95 | 2020-03-11 | 2020-06-14 |  | 0%
PRO-GCA-CS-1020 | LER Building - Delivery of steel structure to the site 100% | 0 |  | 2020-03-11 |  | 0%
PRO-GCA-CS-1000 | Gas Compressor - Delivery of steel structure to the site 50% | 0 |  | 2020-04-05 |  | 0%
PRO-GCA-CS-1010 | Gas Compressor - Delivery of steel structure to the site 100% | 0 |  | 2020-06-14 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 144 | 2020-05-29 | 2020-10-20 |  | 0%
PRO-GCA-PI-1000 | Gas Compressor - A/G Piping Bulk Delivery 50% | 0 |  | 2020-05-29 |  | 0%
PRO-GCA-PI-1010 | Gas Compressor - A/G Piping Bulk Delivery 100% | 0 |  | 2020-10-20 |  | 0%
EQUIPMENTWORKS |  | 74 | 2020-02-20 | 2020-05-04 |  | 0%
PRO-GCA-ME-1000 | Delivery of critical equipment 100% | 0 |  | 2020-02-20 |  | 0%
PRO-GCA-ME-1010 | Delivery of other equipment 100% | 0 |  | 2020-05-04 |  | 0%
HVACWORKS |  | 383 | 2020-05-16 | 2021-06-04 |  | 0%
PRO-GCA-HV-1000 | HVAC Material Delivery 30% | 0 |  | 2020-05-16 |  | 0%
PRO-GCA-HV-1010 | HVAC Material Delivery 60% | 0 |  | 2020-09-10 |  | 0%
PRO-GCA-HV-1020 | HVAC Material Delivery 100% | 0 |  | 2021-06-04 |  | 0%
ELECTRICALWORKS |  | 192 | 2020-04-20 | 2020-08-31 |  | 0%
PRO-GCA-EL-1000 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 2020-04-20 |  | 0%
PRO-GCA-EL-1010 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 111 | 2020-07-10 | 2020-09-30 |  | 0%
PRO-GCA-IN-1000 | Instrumentation Bulk Delivery 40% | 0 |  | 2020-07-10 |  | 0%
PRO-GCA-IN-1010 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
GASCOMPRESSOR&LERBUILDING-B |  | 471 | 2020-02-18 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 129 | 2020-04-03 | 2020-08-10 |  | 0%
PRO-GCB-CS-1000 | Gas Compressor - Delivery of steel structure to the site 50% | 0 |  | 2020-04-03 |  | 0%
PRO-GCB-CS-1010 | Gas Compressor - Delivery of steel structure to the site 100% | 0 |  | 2020-04-17 |  | 0%
PRO-GCB-CS-1020 | LER Building - Delivery of steel structure to the site 100% | 0 |  | 2020-08-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 168 | 2020-05-10 | 2020-10-25 |  | 0%
PRO-GCB-PI-1000 | Gas Compressor - A/G Piping Bulk Delivery 30% | 0 |  | 2020-05-10 |  | 0%
PRO-GCB-PI-1010 | Gas Compressor - A/G Piping Bulk Delivery 100% | 0 |  | 2020-10-25 |  | 0%
EQUIPMENTWORKS |  | 1 | 2020-02-18 | 2020-02-19 |  | 0%
PRO-GCB-ME-1010 | Delivery of other equipment 100% | 0 |  | 2020-02-18 |  | 0%
PRO-GCB-ME-1000 | Delivery of critical equipment 100% | 0 |  | 2020-02-19 |  | 0%
HVACWORKS |  | 290 | 2020-08-17 | 2021-06-04 |  | 0%
PRO-GCB-HV-1000 | HVAC Material Delivery 30% | 0 |  | 2020-08-17 |  | 0%
PRO-GCB-HV-1010 | HVAC Material Delivery 60% | 0 |  | 2020-09-01 |  | 0%
PRO-GCB-HV-1020 | HVAC Material Delivery 100% | 0 |  | 2021-06-04 |  | 0%
ELECTRICALWORKS |  | 61 | 2020-09-12 | 2020-09-30 |  | 0%
PRO-GCB-EL-1000 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 2020-09-12 |  | 0%
PRO-GCB-EL-1010 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-30 |  | 0%
INSTRUMENTATIONWORKS |  | 219 | 2020-10-27 | 2021-06-04 |  | 0%
PRO-GCB-IN-1000 | Instrumentation Bulk Delivery 40% | 0 |  | 2020-10-27 |  | 0%
PRO-GCB-IN-1010 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
GASCOMPRESSOR&LERBUILDING-C |  | 462 | 2020-02-23 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 93 | 2020-04-08 | 2020-08-10 |  | 0%
PRO-GCC-CS-1000 | Gas Compressor - Delivery of steel structure to the site 50% | 0 |  | 2020-04-08 |  | 0%
PRO-GCC-CS-1010 | Gas Compressor - Delivery of steel structure to the site 100% | 0 |  | 2020-04-22 |  | 0%
PRO-GCC-CS-1020 | LER Building - Delivery of steel structure to the site 100% | 0 |  | 2020-08-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 107 | 2020-07-14 | 2020-09-20 |  | 0%
PRO-GCC-PI-1000 | Gas Compressor - A/G Piping Bulk Delivery 30% | 0 |  | 2020-07-14 |  | 0%
PRO-GCC-PI-1010 | Gas Compressor - A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-20 |  | 0%
EQUIPMENTWORKS |  | 143 | 2020-02-23 | 2020-07-19 |  | 0%
PRO-GCC-ME-1000 | Delivery of critical equipment | 0 |  | 2020-02-23 |  | 0%
PRO-GCC-ME-1010 | Delivery of other equipment | 0 |  | 2020-07-19 |  | 0%
HVACWORKS |  | 290 | 2020-08-17 | 2021-06-04 |  | 0%
PRO-GCC-HV-1000 | HVAC Material Delivery 30% | 0 |  | 2020-08-17 |  | 0%
PRO-GCC-HV-1010 | HVAC Material Delivery 60% | 0 |  | 2020-09-10 |  | 0%
PRO-GCC-HV-1020 | HVAC Material Delivery 100% | 0 |  | 2021-06-04 |  | 0%
ELECTRICALWORKS |  | 61 | 2020-09-12 | 2020-09-30 |  | 0%
PRO-GCC-EL-1000 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 2020-09-12 |  | 0%
PRO-GCC-EL-1010 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-30 |  | 0%
INSTRUMENTATIONWORKS |  | 217 | 2020-10-28 | 2021-06-04 |  | 0%
PRO-GCC-IN-1000 | Instrumentation Bulk Delivery 40% | 0 |  | 2020-10-28 |  | 0%
PRO-GCC-IN-1010 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
COMPRESSORMAINPIPERACKA |  | 404 | 2019-11-03 | 2020-09-30 |  | 0%
STEELSTRUCTUREWORKS |  | 132 | 2019-11-03 | 2020-02-25 |  | 0%
PRO-GCA-CS-1100 | Delivery of steel structure to the site 30% | 0 |  | 2019-11-03 |  | 0%
PRO-GCA-CS-1110 | Delivery of steel structure to the site 60% | 0 |  | 2020-01-28 |  | 0%
PRO-GCA-CS-1120 | Delivery of steel structure to the site 100% | 0 |  | 2020-02-25 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 231 | 2020-03-12 | 2020-08-25 |  | 0%
PRO-GCA-PI-1100 | A/G Piping Bulk Delivery 30% | 0 |  | 2020-03-12 |  | 0%
PRO-GCA-PI-1110 | A/G Piping Bulk Delivery 60% | 0 |  | 2020-03-26 |  | 0%
PRO-GCA-PI-1120 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-08-25 |  | 0%
ELECTRICALWORKS |  | 103 | 2020-08-01 | 2020-08-31 |  | 0%
PRO-GCA-EL-1100 | Electrical Bulk Delivery (excl. EHT) 30% | 0 |  | 2020-08-01 |  | 0%
PRO-GCA-EL-1110 | Electrical Bulk Delivery (excl. EHT) 60% | 0 |  | 2020-08-05 |  | 0%
PRO-GCA-EL-1120 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 102 | 2020-08-15 | 2020-09-30 |  | 0%
PRO-GCA-IN-1100 | Instrumentation Bulk Delivery 30% | 0 |  | 2020-08-15 |  | 0%
PRO-GCA-IN-1110 | Instrumentation Bulk Delivery 60% | 0 |  | 2020-08-31 |  | 0%
PRO-GCA-IN-1120 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
COMPRESSORMAINPIPERACKB |  | 584 | 2019-11-12 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 172 | 2019-11-12 | 2020-04-17 |  | 0%
PRO-GCB-CS-1100 | Delivery of steel structure to the site 30% | 0 |  | 2019-11-12 |  | 0%
PRO-GCB-CS-1110 | Delivery of steel structure to the site 60% | 0 |  | 2020-04-03 |  | 0%
PRO-GCB-CS-1120 | Delivery of steel structure to the site 100% | 0 |  | 2020-04-17 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 133 | 2020-05-10 | 2020-09-20 |  | 0%
PRO-GCB-PI-1100 | A/G Piping Bulk Delivery 30% | 0 |  | 2020-05-10 |  | 0%
PRO-GCB-PI-1110 | A/G Piping Bulk Delivery 60% | 0 |  | 2020-07-10 |  | 0%
PRO-GCB-PI-1120 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-20 |  | 0%
ELECTRICALWORKS |  | 275 | 2020-09-01 | 2021-06-04 |  | 0%
PRO-GCB-EL-1100 | Electrical Bulk Delivery (excl. EHT) 30% | 0 |  | 2020-09-01 |  | 0%
PRO-GCB-EL-1110 | Electrical Bulk Delivery (excl. EHT) 60% | 0 |  | 2020-09-15 |  | 0%
PRO-GCB-EL-1120 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENTATIONWORKS |  | 29 | 2020-09-01 | 2020-09-30 |  | 0%
PRO-GCB-IN-1100 | Instrumentation Bulk Delivery 30% | 0 |  | 2020-09-01 |  | 0%
PRO-GCB-IN-1110 | Instrumentation Bulk Delivery 60% | 0 |  | 2020-09-10 |  | 0%
PRO-GCB-IN-1120 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
COMPRESSORMAINPIPERACKC |  | 252 | 2020-03-19 | 2020-09-30 |  | 0%
STEELSTRUCTUREWORKS |  | 42 | 2020-03-19 | 2020-04-30 |  | 0%
PRO-GCC-CS-1100 | Delivery of steel structure to the site 30% | 0 |  | 2020-03-19 |  | 0%
PRO-GCC-CS-1110 | Delivery of steel structure to the site 60% | 0 |  | 2020-04-05 |  | 0%
PRO-GCC-CS-1120 | Delivery of steel structure to the site 100% | 0 |  | 2020-04-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 121 | 2020-04-21 | 2020-08-20 |  | 0%
PRO-GCC-PI-1100 | A/G Piping Bulk Delivery 30% | 0 |  | 2020-04-21 |  | 0%
PRO-GCC-PI-1110 | A/G Piping Bulk Delivery 60% | 0 |  | 2020-05-05 |  | 0%
PRO-GCC-PI-1120 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-08-20 |  | 0%
ELECTRICALWORKS |  | 88 | 2020-08-30 | 2020-09-30 |  | 0%
PRO-GCC-EL-1100 | Electrical Bulk Delivery (excl. EHT) 30% | 0 |  | 2020-08-30 |  | 0%
PRO-GCC-EL-1110 | Electrical Bulk Delivery (excl. EHT) 60% | 0 |  | 2020-09-10 |  | 0%
PRO-GCC-EL-1120 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-30 |  | 0%
INSTRUMENTATIONWORKS |  | 28 | 2020-09-01 | 2020-09-30 |  | 0%
PRO-GCC-IN-1100 | Instrumentation Bulk Delivery 30% | 0 |  | 2020-09-01 |  | 0%
PRO-GCC-IN-1110 | Instrumentation Bulk Delivery 60% | 0 |  | 2020-09-10 |  | 0%
PRO-GCC-IN-1120 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
NS-PIPERACK |  | 577 | 2019-11-04 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 326 | 2019-11-04 | 2020-09-25 |  | 0%
PRO-MPR-CS-1000 | Delivery of steel structure to the site 30% | 0 |  | 2019-11-04 |  | 0%
PRO-MPR-CS-1010 | Delivery of steel structure to the site 60% | 0 |  | 2020-05-09 |  | 0%
PRO-MPR-CS-1020 | Delivery of steel structure to the site 100% | 0 |  | 2020-09-25 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 133 | 2020-05-20 | 2020-09-30 |  | 0%
PRO-MPR-PI-1000 | A/G Piping Bulk Delivery 30% | 0 |  | 2020-05-20 |  | 0%
PRO-MPR-PI-1010 | A/G Piping Bulk Delivery 60% | 0 |  | 2020-07-20 |  | 0%
PRO-MPR-PI-1020 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
ELECTRICALWORKS |  | 71 | 2020-06-21 | 2020-08-31 |  | 0%
PRO-MPR-EL-1000 | Electrical Bulk Delivery (excl. EHT) 30% | 0 |  | 2020-06-21 |  | 0%
PRO-MPR-EL-1010 | Electrical Bulk Delivery (excl. EHT) 60% | 0 |  | 2020-07-15 |  | 0%
PRO-MPR-EL-1020 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 304 | 2020-08-03 | 2021-06-04 |  | 0%
PRO-MPR-IN-1000 | Instrumentation Bulk Delivery 30% | 0 |  | 2020-08-03 |  | 0%
PRO-MPR-IN-1010 | Instrumentation Bulk Delivery 60% | 0 |  | 2020-09-16 |  | 0%
PRO-MPR-IN-1020 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENT&NITROGENAREA |  | 244 | 2020-10-02 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-10-10 | 2020-10-10 |  | 0%
PRO-INA-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-10-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-INA-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
EQUIPMENTWORKS |  | 0 | 2020-10-02 | 2020-10-02 |  | 0%
PRO-INA-ME-1000 | Delivery of Instrument & Nitrogen Package | 0 |  | 2020-10-02 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-10-15 | 2020-10-15 |  | 0%
PRO-INA-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-10-15 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-INA-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
EMERGENCYDIESELGENERATOR |  | 226 | 2020-10-20 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-10-25 | 2020-10-25 |  | 0%
PRO-EDG-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-10-25 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-20 | 2020-10-20 |  | 0%
PRO-EDG-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-10-20 |  | 0%
EQUIPMENTWORKS |  | 0 | 2020-12-31 | 2020-12-31 |  | 0%
PRO-EDG-ME-1000 | Delivery of Emergency Diesel Generator | 0 |  | 2020-12-31 |  | 0%
PRO-EDG-ME-1010 | Delivery of equipment | 0 |  | 2020-12-31 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-EDG-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-EDG-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
MAINTENANCEBUIDING |  | 354 | 2020-06-14 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 137 | 2020-06-14 | 2020-08-30 |  | 0%
PRO-MBL-CS-1000 | Delivery of steel structure to the site 40% | 0 |  | 2020-06-14 |  | 0%
PRO-MBL-CS-1010 | Delivery of steel structure to the site 100% | 0 |  | 2020-08-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-10-26 | 2020-10-26 |  | 0%
PRO-MBL-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-10-26 |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-MBL-ME-1000 | Delivery of equipment | 0 |  | 04-Jun-21* |  | 0%
HVACWORKS |  | 0 | 2020-10-07 | 2020-11-10 |  | 0%
PRO-MBL-HV-1000 | HVAC Material Delivery 40% | 0 |  | 2020-10-07 |  | 0%
PRO-MBL-HV-1010 | HVAC Material Delivery 100% | 0 |  | 2020-11-10 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-08-31 | 2020-08-31 |  | 0%
PRO-MBL-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-31 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-09-30 | 2020-09-30 |  | 0%
PRO-MBL-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-09-30 |  | 0%
OPENDRAINAREA |  | 217 | 2020-09-10 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-09-10 | 2020-09-10 |  | 0%
PRO-ODA-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-09-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-28 | 2020-09-28 |  | 0%
PRO-ODA-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-28 |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-ODA-ME-1000 | Delivery of equipment 100% | 0 |  | 04-Jun-21* |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-ODA-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-ODA-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
GASSEPARATION-1 |  | 405 | 2020-04-26 | 2021-06-05 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-04-26 | 2020-04-26 |  | 0%
PRO-GS1-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-04-26 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-GS1-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-06-05 | 2021-06-05 |  | 0%
PRO-GS1-ME-1000 | Delivery of Gas Separator-1 | 0 |  | 05-Jun-21* |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-01 | 2020-09-01 |  | 0%
PRO-GS1-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-01 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-10 | 2020-10-10 |  | 0%
PRO-GS1-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-10-10 |  | 0%
GASSEPARATION-2 |  | 490 | 2020-05-10 | 2021-06-09 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-05-10 | 2020-05-10 |  | 0%
PRO-GS2-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-05-10 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-GS2-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-06-09 | 2021-06-09 |  | 0%
PRO-GS2-ME-1000 | Delivery & Installation of Gas Separator-2 | 0 |  | 09-Jun-21* |  | 0%
ELECTRICALWORKS |  | 0 | 2020-10-02 | 2020-10-02 |  | 0%
PRO-GS2-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-10-02 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-26 | 2020-10-26 |  | 0%
PRO-GS2-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-10-26 |  | 0%
GCA-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 426 | 2020-05-01 | 2021-07-01 |  | 0%
STEELSTRUCTUREWORKS |  | 89 | 2020-05-01 | 2020-07-29 |  | 0%
PRO-GCA-CS-1200 | Delivery of steel structure to the site 40% | 0 |  | 2020-05-01 |  | 0%
PRO-GCA-CS-1210 | Delivery of steel structure to the site 100% | 0 |  | 2020-07-29 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 217 | 2020-08-20 | 2021-06-04 |  | 0%
PRO-GCA-PI-1200 | A/G Piping Bulk Delivery 40% | 0 |  | 2020-08-20 |  | 0%
PRO-GCA-PI-1210 | A/G Piping Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-01-24 | 2021-01-24 |  | 0%
PRO-GCA-ME-1200 | Delivery of equipment | 0 |  | 2021-01-24 |  | 0%
ELECTRICALWORKS |  | 28 | 2021-06-04 | 2021-07-01 |  | 0%
PRO-GCA-EL-1200 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 04-Jun-21* |  | 0%
PRO-GCA-EL-1210 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2021-07-01 |  | 0%
INSTRUMENTATIONWORKS |  | 27 | 2021-06-04 | 2021-06-30 |  | 0%
PRO-GCA-IN-1200 | Instrumentation Bulk Delivery 40% | 0 |  | 04-Jun-21* |  | 0%
PRO-GCA-IN-1210 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-30 |  | 0%
GCB-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 385 | 2020-05-28 | 2021-06-17 |  | 0%
STEELSTRUCTUREWORKS |  | 63 | 2020-05-28 | 2020-07-30 |  | 0%
PRO-GCB-CS-1200 | Delivery of steel structure to the site 40% | 0 |  | 2020-05-28 |  | 0%
PRO-GCB-CS-1210 | Delivery of steel structure to the site 100% | 0 |  | 2020-07-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 217 | 2020-09-25 | 2021-06-04 |  | 0%
PRO-GCB-PI-1200 | A/G Piping Bulk Delivery 40% | 0 |  | 2020-09-25 |  | 0%
PRO-GCB-PI-1210 | A/G Piping Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-02-20 | 2021-02-20 |  | 0%
PRO-GCB-ME-1200 | Delivery of equipment | 0 |  | 2021-02-20 |  | 0%
ELECTRICALWORKS |  | 14 | 2021-06-04 | 2021-06-17 |  | 0%
PRO-GCB-EL-1200 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 04-Jun-21* |  | 0%
PRO-GCB-EL-1210 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2021-06-17 |  | 0%
INSTRUMENTATIONWORKS |  | 14 | 2021-06-04 | 2021-06-17 |  | 0%
PRO-GCB-IN-1200 | Instrumentation Bulk Delivery 40% | 0 |  | 04-Jun-21* |  | 0%
PRO-GCB-IN-1210 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-17 |  | 0%
GCC-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 371 | 2020-05-28 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 63 | 2020-05-28 | 2020-07-30 |  | 0%
PRO-GCC-CS-1200 | Delivery of steel structure to the site 40% | 0 |  | 2020-05-28 |  | 0%
PRO-GCC-CS-1210 | Delivery of steel structure to the site 100% | 0 |  | 2020-07-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 217 | 2020-09-22 | 2021-06-04 |  | 0%
PRO-GCC-PI-1200 | A/G Piping Bulk Delivery 40% | 0 |  | 2020-09-22 |  | 0%
PRO-GCC-PI-1210 | A/G Piping Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
EQUIPMENTWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-GCC-ME-1200 | Delivery of equipment | 0 |  | 04-Jun-21* |  | 0%
ELECTRICALWORKS |  | 217 | 2020-09-01 | 2021-06-04 |  | 0%
PRO-GCC-EL-1200 | Electrical Bulk Delivery (excl. EHT) 40% | 0 |  | 2020-09-01 |  | 0%
PRO-GCC-EL-1210 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2021-06-04 |  | 0%
INSTRUMENTATIONWORKS |  | 217 | 2020-09-01 | 2021-06-04 |  | 0%
PRO-GCC-IN-1200 | Instrumentation Bulk Delivery 40% | 0 |  | 2020-09-01 |  | 0%
PRO-GCC-IN-1210 | Instrumentation Bulk Delivery 100% | 0 |  | 2021-06-04 |  | 0%
HPFLAREAREA |  | 297 | 2020-08-10 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-08-23 | 2020-08-23 |  | 0%
PRO-HPF-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-08-23 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-HPF-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
EQUIPMENTWORKS |  | 80 | 2020-08-10 | 2020-09-30 |  | 0%
PRO-HPF-ME-1010 | Delivery of Flare Stack | 0 |  | 2020-08-10 |  | 0%
PRO-HPF-ME-1000 | Delivery of Flare KOD Pumps Shelter | 0 |  | 2020-09-30 |  | 0%
ELECTRICALWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-HPF-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 04-Jun-21* |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-HPF-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
FUELSEALGAS |  | 71 | 2020-07-30 | 2020-10-09 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-07-30 | 2020-07-30 |  | 0%
PRO-FSG-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-07-30 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-10 | 2020-09-10 |  | 0%
PRO-FSG-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-10 |  | 0%
EQUIPMENTWORKS |  | 0 | 2020-09-19 | 2020-09-19 |  | 0%
PRO-FSG-ME-1000 | Delivery of equipment | 0 |  | 2020-09-19 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-09-09 | 2020-09-09 |  | 0%
PRO-FSG-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-09 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2020-10-09 | 2020-10-09 |  | 0%
PRO-FSG-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 2020-10-09 |  | 0%
HEATTRANSFERAREA |  | 303 | 2020-08-04 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 0 | 2020-08-04 | 2020-08-04 |  | 0%
PRO-HTF-CS-1000 | Delivery of steel structure to the site 100% | 0 |  | 2020-08-04 |  | 0%
ABOVEGROUNDPIPINGWORKS |  | 0 | 2020-09-22 | 2020-09-22 |  | 0%
PRO-HTF-PI-1000 | A/G Piping Bulk Delivery 100% | 0 |  | 2020-09-22 |  | 0%
EQUIPMENTWORKS |  | 0 | 2020-09-10 | 2020-09-10 |  | 0%
PRO-HTF-ME-1000 | Delivery of equipment | 0 |  | 2020-09-10 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-10-02 | 2020-10-02 |  | 0%
PRO-HTF-EL-1000 | Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-10-02 |  | 0%
INSTRUMENTATIONWORKS |  | 0 | 2021-06-04 | 2021-06-04 |  | 0%
PRO-HTF-IN-1000 | Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
SUBSTATIONBUILDINGS(911&912) |  | 425 | 2020-04-04 | 2021-06-04 |  | 0%
STEELSTRUCTUREWORKS |  | 24 | 2020-04-04 | 2020-04-28 |  | 0%
PRO-TSS-CS-1010 | Substation 912 - Delivery of steel structure to the site 100% | 0 |  | 2020-04-04 |  | 0%
PRO-TSS-CS-1000 | Substation 911 - Delivery of steel structure to the site 100% | 0 |  | 2020-04-28 |  | 0%
EQUIPMENTWORKS |  | 27 | 2020-06-17 | 2020-07-14 |  | 0%
PRO-TSS-ME-1000 | Substation 911 - Delivery of equipment | 0 |  | 2020-06-17 |  | 0%
PRO-TSS-ME-1010 | Substation 912 - Delivery of equipment | 0 |  | 2020-07-14 |  | 0%
HVACWORKS |  | 0 | 2020-12-01 | 2020-12-15 |  | 0%
PRO-TSS-HV-1000 | Substation 911 - HVAC Material Delivery 100% | 0 |  | 2020-12-01 |  | 0%
PRO-TSS-HV-1010 | Substation 912 - HVAC Material Delivery 100% | 0 |  | 2020-12-15 |  | 0%
ELECTRICALWORKS |  | 0 | 2020-08-22 | 2020-09-22 |  | 0%
PRO-TSS-EL-1000 | Substation 911 - Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-08-22 |  | 0%
PRO-TSS-EL-1010 | Substation 912 - Electrical Bulk Delivery (excl. EHT) 100% | 0 |  | 2020-09-22 |  | 0%
INSTRUMENTATIONWORKS |  | 217 | 2020-10-07 | 2021-06-04 |  | 0%
PRO-TSS-IN-1000 | Substation 911 - Instrumentation Bulk Delivery 100% | 0 |  | 2020-10-07 |  | 0%
PRO-TSS-IN-1010 | Substation 912 - Instrumentation Bulk Delivery 100% | 0 |  | 04-Jun-21* |  | 0%
HANDOVERMILESTONES |  | 219 | 2019-09-25 | 2020-05-01 |  | 0%
FIELDAUXILLARYROOM(FAR)-AREA |  | 0 | 2019-11-15 | 2019-11-15 |  | 0%
MIL-HO-001 | Handover of Area | 0 | 2019-11-15 |  |  | 0%
GASCOMPRESSOR&LERBUILDING-A |  | 0 | 2019-10-01 | 2019-10-01 |  | 0%
MIL-HO-002 | Handover of Area | 0 | 2019-10-01 |  |  | 0%
GASCOMPRESSOR&LERBUILDING-B |  | 0 | 2019-10-10 | 2019-10-10 |  | 0%
MIL-HO-003 | Handover of Area | 0 | 2019-10-10 |  |  | 0%
GASCOMPRESSOR&LERBUILDING-C |  | 0 | 2020-03-22 | 2020-03-22 |  | 0%
MIL-HO-004 | Handover of Area | 0 | 2020-03-22 |  |  | 0%
COMPRESSORMAINPIPERACK(A/B/C) |  | 30 | 2019-09-25 | 2019-10-10 |  | 0%
MIL-HO-005-A | Handover of Area Compressor Main Piperack A | 0 | 2019-09-25 |  |  | 0%
MIL-HO-005-B | Handover of Area Compressor Main Piperack B | 0 | 2019-10-06 |  |  | 0%
MIL-HO-005-C | Handover of Area Compressor Main Piperack C | 0 | 2019-10-10 |  |  | 0%
MAINPIPERACKNORTH-SOUTH |  | 0 | 2019-10-01 | 2019-10-01 |  | 0%
MIL-HO-006 | Handover of Area | 0 | 2019-10-01 |  |  | 0%
INSTRUMENT&NITROGENAREA |  | 0 | 2019-10-21 | 2019-10-21 |  | 0%
MIL-HO-007 | Handover of Area | 0 | 2019-10-21 |  |  | 0%
EMERGENCYDIESELGENERATOR |  | 0 | 2019-10-21 | 2019-10-21 |  | 0%
MIL-HO-008 | Handover of Area | 0 | 2019-10-21 |  |  | 0%
MAINTENANCEBUIDING |  | 0 | 2019-10-21 | 2019-10-21 |  | 0%
MIL-HO-009 | Handover of Area | 0 | 2019-10-21 |  |  | 0%
OPENDRAINAREA |  | 0 | 2019-12-25 | 2019-12-25 |  | 0%
MIL-HO-010 | Handover of Area | 0 | 2019-12-25 |  |  | 0%
GASSEPARATION-1 |  | 0 | 2020-03-22 | 2020-03-22 |  | 0%
MIL-HO-011 | Handover of Area | 0 | 2020-03-22 |  |  | 0%
GASSEPARATION-2 |  | 0 | 2020-03-22 | 2020-03-22 |  | 0%
MIL-HO-012 | Handover of Area | 0 | 2020-03-22 |  |  | 0%
GCA-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2020-03-10 | 2020-03-10 |  | 0%
MIL-HO-013 | Handover of Area | 0 | 2020-03-10 |  |  | 0%
GCB-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2020-03-27 | 2020-03-27 |  | 0%
MIL-HO-014 | Handover of Area | 0 | 2020-03-27 |  |  | 0%
GCC-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2020-03-10 | 2020-03-10 |  | 0%
MIL-HO-015 | Handover of Area | 0 | 2020-03-10 |  |  | 0%
HPFLAREAREA |  | 0 | 2020-01-07 | 2020-01-07 |  | 0%
MIL-HO-016 | Handover of Area | 0 | 2020-01-07 |  |  | 0%
FUELSEALGAS |  | 0 | 2019-12-15 | 2019-12-15 |  | 0%
MIL-HO-017 | Handover of Area | 0 | 2019-12-15 |  |  | 0%
HEATTRANSFERAREA |  | 0 | 2020-05-01 | 2020-05-01 |  | 0%
MIL-HO-018 | Handover of Area | 0 | 2020-05-01 |  |  | 0%
SUBSTATIONBUILDINGS(911&912) |  | 0 | 2019-10-05 | 2019-10-05 |  | 0%
MIL-HO-019 | Handover of Area | 0 | 2019-10-05 |  |  | 0%
FINISHMILESTONES |  | 418 | 2021-06-30 | 2022-08-22 |  | 0%
COMMONAREA |  | 0 | 2022-08-19 | 2022-08-19 |  | 0%
MIL-FSH-1180 | Finish of Works - Common area | 0 |  | 2022-08-19 |  | 0%
FIELDAUXILLARYROOM(FAR)-AREA |  | 0 | 2022-02-25 | 2022-02-25 |  | 0%
MIL-FSH-1050 | Finish of Works - Field Auxillary Room | 0 |  | 2022-02-25 |  | 0%
GASCOMPRESSOR&LERBUILDING-A |  | 0 | 2022-03-15 | 2022-03-15 |  | 0%
MIL-FSH-1130 | Finish of Works - Compressor and LER Buildings - String A | 0 |  | 2022-03-15 |  | 0%
GASCOMPRESSOR&LERBUILDING-B |  | 0 | 2022-04-14 | 2022-04-14 |  | 0%
MIL-FSH-1150 | Finish of Works - Compressor and LER Buildings - String B | 0 |  | 2022-04-14 |  | 0%
GASCOMPRESSOR&LERBUILDING-C |  | 0 | 2022-05-20 | 2022-05-20 |  | 0%
MIL-FSH-1190 | Finish of Works - Compressor and LER Buildings - String C | 0 |  | 2022-05-20 |  | 0%
COMPRESSORMAINPIPERACKA |  | 0 | 2021-11-10 | 2021-11-10 |  | 0%
MIL-FSH-1120 | Finish of Works - Compressor Main Piperack - String A | 0 |  | 2021-11-10 |  | 0%
COMPRESSORMAINPIPERACKB |  | 0 | 2021-12-14 | 2021-12-14 |  | 0%
MIL-FSH-1160 | Finish of Works - Compressor Main Piperack - String B | 0 |  | 2021-12-14 |  | 0%
COMPRESSORMAINPIPERACKC |  | 0 | 2022-01-10 | 2022-01-10 |  | 0%
MIL-FSH-1210 | Finish of Works - Compressor Main Piperack - String C | 0 |  | 2022-01-10 |  | 0%
NS-PIPERACK |  | 0 | 2022-06-18 | 2022-06-18 |  | 0%
MIL-FSH-1100 | Finish of Works - North South Piperack | 0 |  | 2022-06-18 |  | 0%
INSTRUMENT&NITROGENAREA |  | 0 | 2022-01-24 | 2022-01-24 |  | 0%
MIL-FSH-1010 | Finish of Works - Instrument and Nitrogen Area | 0 |  | 2022-01-24 |  | 0%
EMERGENCYDIESELGENERATOR |  | 0 | 2022-02-11 | 2022-02-11 |  | 0%
MIL-FSH-1000 | Finish of Works - EDG Area | 0 |  | 2022-02-11 |  | 0%
MAINTENANCEBUIDING |  | 0 | 2022-07-17 | 2022-07-17 |  | 0%
MIL-FSH-1110 | Finish of Works - Maintenance Building | 0 |  | 2022-07-17 |  | 0%
OPENDRAINAREA |  | 0 | 2022-02-10 | 2022-02-10 |  | 0%
MIL-FSH-1070 | Finish of Works - Open Drain Area | 0 |  | 2022-02-10 |  | 0%
GASSEPARATION-1 |  | 0 | 2022-07-27 | 2022-07-27 |  | 0%
MIL-FSH-1040 | Finishing of Works - Gas Separation Unit 1 | 0 |  | 2022-07-27 |  | 0%
GASSEPARATION-2 |  | 0 | 2022-08-22 | 2022-08-22 |  | 0%
MIL-FSH-1090 | Finishing of Works - Gas Separation Unit 2 | 0 |  | 2022-08-22 |  | 0%
GCA-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2022-03-08 | 2022-03-08 |  | 0%
MIL-FSH-1140 | Finish of Works - Air Cooler incl. Cablerack - String A | 0 |  | 2022-03-08 |  | 0%
GCB-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2022-03-30 | 2022-03-30 |  | 0%
MIL-FSH-1170 | Finish of Works - Air Cooler incl. Cablerack - String B | 0 |  | 2022-03-30 |  | 0%
GCC-AIRCOOLER/CABLERACK(COMPRESSORDISHARGECOOLER) |  | 0 | 2022-05-31 | 2022-05-31 |  | 0%
MIL-FSH-1200 | Finish of Works - Air Cooler incl. Cablerack - String C | 0 |  | 2022-05-31 |  | 0%
HPFLAREAREA |  | 0 | 2022-03-26 | 2022-03-26 |  | 0%
MIL-FSH-1220 | Finish of Works - HP Flare & Closed Drain Area | 0 |  | 2022-03-26 |  | 0%
FUELSEALGAS |  | 0 | 2022-01-16 | 2022-01-16 |  | 0%
MIL-FSH-1020 | Finish of Works - Fuel & Seal Gas Area | 0 |  | 2022-01-16 |  | 0%
HEATTRANSFERAREA |  | 0 | 2022-02-26 | 2022-02-26 |  | 0%
MIL-FSH-1080 | Finish of Works - Heat Transfer Fluid Area | 0 |  | 2022-02-26 |  | 0%
SUBSTATIONBUILDINGS(911) |  | 0 | 2022-02-20 | 2022-02-20 |  | 0%
MIL-FSH-1030 | Finish of Works - Transformer Substation (B-911) | 0 |  | 2022-02-20 |  | 0%
SUBSTATIONBUILDINGS(912) |  | 0 | 2022-06-08 | 2022-06-08 |  | 0%
MIL-FSH-1060 | Finish of Works - Transformer Substation (B-912) | 0 |  | 2022-06-08 |  | 0%
BATTERYLIMITSTATION |  | 0 | 2021-06-30 | 2021-06-30 |  | 0%
MIL-FSH-1230 | Finish of Works - Battery Limit Station | 0 |  | 2021-06-30 |  | 0%
SUBCONTRACTORPROCUREMENT |  | 948 | 2019-10-05 | 2022-03-19 |  | 0%
PRO-SP-1010 | UG Piping Material | 200 | 2019-10-05 | 2021-06-04 |  | 0%
PRO-SP-1000 | Civil Material For TSF Area "S" | 114 | 2019-10-10 | 2021-06-05 |  | 0%
PRO-SP-1020 | General Civil Material | 510 | 2019-10-10 | 2022-03-13 |  | 0%
PRO-SP-1030 | Building Substructure Material | 170 | 2019-10-23 | 2021-12-16 |  | 0%
PRO-SP-1040 | Piping Material | 370 | 2020-05-30 | 2022-02-22 |  | 0%
PRO-SP-1100 | FAR Buiding Material - Fireproofing | 154 | 2020-06-15 | 2021-08-18 |  | 0%
PRO-SP-1110 | FAR Building Material - Cladding | 154 | 2020-07-17 | 2021-08-08 |  | 0%
PRO-SP-1060 | Building Electrical Material | 390 | 2020-08-29 | 2021-10-03 |  | 0%
PRO-SP-1070 | HVAC Building Material | 300 | 2020-09-10 | 2022-03-19 |  | 0%
PRO-SP-1080 | Building Instrumentation Material | 365 | 2020-09-30 | 2021-10-13 |  | 0%
PRO-SP-1090 | Building Telecom Material | 141 | 2021-06-04 | 2021-10-22 |  | 0%
OPFCCONSTRUCTION |  | 1087 | 2019-10-01 | 2022-08-22 |  | 36.87%
TSFAREAS |  | 376 | 2019-10-08 | 2020-08-20 |  | 100%
Civil/Structural |  | 376 | 2019-10-08 | 2020-08-20 |  | 100%
CN-TSF-CS-1090 | Excavation - TSF Area (DELETED) | 72 | 2019-10-08 | 2020-04-01 | m3/м3 | 100% |  | m3/м3
CN-TSF-CS-1130 | Backfilling - TSF Area (DELETED) | 105 | 2019-10-08 | 2020-04-15 | m3/м3 | 100% |  | m3/м3
CN-TSF-CS-1100 | Fencing Works - TSF Area (DELETED) | 80 | 2020-06-23 | 2020-08-20 | m/м | 100% |  | m/м
TSFAREA |  | 170 | 2021-06-04 | 2021-11-20 |  | 0%
TelecomTSF |  | 170 | 2021-06-04 | 2021-11-20 |  | 0%
CN-TSF-CS-1101 | Telecom - TSF Area (DELETED) | 170 | 2021-06-04 | 2021-11-20 | m/м | 0% |  | m/м
COMMONAREA |  | 1053 | 2019-10-02 | 2022-08-19 |  | 39.71%
Civil/Structural |  | 501 | 2021-03-21 | 2022-08-19 |  | 6.53%
CN-CMN-CS-1020-5 | Duct Banks - Common Area | 280 | 2021-03-21 | 2022-01-17 | m3/м3 | 90.63% | 306.72 | m3/м3
CN-CMN-CS-1020-4 | Lean Concrete - Common Area | 45 | 2021-05-24 | 2021-05-25 | m3/м3 | 100% | 5 | m3/м3
CN-CMN-CS-1020-3 | Concrete works - Common Area | 132 | 2021-05-26 | 2021-10-27 | m3/м3 | 35.3% | 213.26 | m3/м3
CN-CMN-CS-1020-6 | Structural Steel Works - Ladders Common Area | 55 | 2021-09-13 | 2021-11-06 | m/м | 0% | 316 | m/м
CN-CMN-CS-1020-11 | E/I Supports - Common Area | 50 | 2021-09-28 | 2021-11-16 | tons/тн | 0% | 1 | tons/тн
CN-CMN-CS-1020-10 | Drilling Works (Earthing) - Common Area | 30 | 2021-10-28 | 2021-11-26 | ea/шт | 0% | 4 | ea/шт
CN-CMN-CS-1260 | Install Permanent Roads - Common Area | 140 | 2022-02-26 | 2022-07-15 | m/м | 0% | 4442 | m/м
CN-CMN-CS-1020 | Installation of Open Drain (Newly Added) | 150 | 2022-03-18 | 2022-08-14 | m2/м2 | 0% | 5350 | m2/м2
CN-CMN-CS-1020-7 | Paving - Common Area | 120 | 2022-03-28 | 2022-07-25 | m2/м2 | 0% | 14647 | m2/м2
CN-CMN-CS-1020-2 | Slope protection - Common Area | 120 | 2022-04-22 | 2022-08-19 | m2/м2 | 0% | 60 | m2/м2
CN-CMN-CS-1020-8 | Fencing Works - Common Area | 90 | 2022-05-07 | 2022-08-04 | m/м | 0% | 2357 | m/м
CN-CMN-CS-1020-9 | Gates - Common Area | 26 | 2022-07-25 | 2022-08-19 | ea/шт | 0% | 10 | ea/шт
Piping |  | 910 | 2019-10-02 | 2022-03-29 |  | 79.94%
CN-CMN-PI-1152 | Fabrication / Installation of Pipe HDPE - UG | 200 | 2019-11-23 | 2021-10-12 | IM | 95% | 46935 | IM
UGPipingPart1 |  | 261 | 2019-10-02 | 2020-08-28 |  | 100%
CN-CMN-PI-1000-296 | Prefabrication DRAINAGE SYSTEM / PITS - Part 1 UG | 155 | 2019-10-02 | 2020-03-04 | ea/шт | 100% | 38 | ea/шт
CN-CMN-PI-1000-96 | Buried Pipe Trenches - Part 1 Excavation UG | 53 | 2020-02-01 | 2020-05-05 | m3/м3 | 100% | 234 | m3/м3
CN-CMN-PI-1000-176 | Erection DRAINAGE SYSTEM / PITS - Part 1 UG | 25 | 2020-02-13 | 2020-06-05 | ea/шт | 100% | 38 | ea/шт
CN-CMN-PI-1000-56 | Piping Painting - UG - Part 1 | 41 | 2020-03-29 | 2020-06-26 | m2/м2 | 100% | 836 | m2/м2
CN-CMN-PI-1000-136 | Piping Erection - UG - Part 1 | 45 | 2020-03-30 | 2020-06-24 | DI | 100% | 955 | DI
CN-CMN-PI-1000-256 | Piping Testing (Hydrotesting) - UG - Part 1 | 53 | 2020-04-11 | 2020-08-27 | Стык/Jo | 100% | 1 | Стык/Jo
CN-CMN-PI-1000-216 | Buried Pipe Trenches - Backfilling UG - Part 1 | 42 | 2020-04-18 | 2020-08-28 | m3/м3 | 100% | 234 | m3/м3
UGPipingPart2 |  | 296 | 2019-10-22 | 2020-11-19 |  | 100%
CN-CMN-PI-1000-306 | Prefabrication DRAINAGE SYSTEM / PITS - Part 2 UG | 182 | 2019-10-22 | 2020-05-13 | ea/шт | 100% | 36 | ea/шт
CN-CMN-PI-1000-106 | Buried Pipe Trenches - Part 2 Excavation UG | 37 | 2020-03-15 | 2020-06-26 | m3/м3 | 100% | 222 | m3/м3
CN-CMN-PI-1000-186 | Erection DRAINAGE SYSTEM / PITS - Part 2 UG | 24 | 2020-03-17 | 2020-11-19 | ea/шт | 100% | 36 | ea/шт
CN-CMN-PI-1000-146 | Piping Erection - UG - Part 2 | 43 | 2020-04-02 | 2020-11-19 | DI | 100% | 906 | DI
CN-CMN-PI-1000-66 | Piping Painting - UG - Part 2 | 40 | 2020-06-26 | 2020-11-19 | m2/м2 | 100% | 793 | m2/м2
CN-CMN-PI-1000-266 | Piping Testing (Hydrotesting) - UG - Part 2 | 37 | 2020-06-30 | 2020-11-19 | Стык/Jo | 100% | 1 | Стык/Jo
CN-CMN-PI-1000-226 | Buried Pipe Trenches - Backfilling UG - Part 2 | 34 | 2020-07-10 | 2020-11-19 | m3/м3 | 100% | 222 | m3/м3
UGPipingPart3 |  | 344 | 2020-02-25 | 2020-12-18 |  | 100%
CN-CMN-PI-1000-316 | Prefabrication DRAINAGE SYSTEM / PITS - Part 3 UG | 36 | 2020-02-25 | 2020-05-21 | ea/шт | 100% | 33 | ea/шт
CN-CMN-PI-1000-116 | Buried Pipe Trenches - Part 3 Excavation UG | 29 | 2020-06-11 | 2020-12-01 | m3/м3 | 100% | 204 | m3/м3
CN-CMN-PI-1000-196 | Erection DRAINAGE SYSTEM / PITS - Part 3 UG | 11 | 2020-07-10 | 2020-12-03 | ea/шт | 100% | 33 | ea/шт
CN-CMN-PI-1000-156 | Piping Erection - UG - Part 3 | 63 | 2020-08-11 | 2020-12-17 | DI | 100% | 828 | DI
CN-CMN-PI-1000-76 | Piping Painting - UG - Part 3 | 60 | 2020-08-13 | 2020-12-17 | m2/м2 | 100% | 725 | m2/м2
CN-CMN-PI-1000-276 | Piping Testing (Hydrotesting) - UG - Part 3 | 135 | 2020-09-09 | 2020-12-17 | Стык/Jo | 100% | 1 | Стык/Jo
CN-CMN-PI-1000-236 | Buried Pipe Trenches - Backfilling UG - Part 3 | 33 | 2020-10-02 | 2020-12-18 | m3/м3 | 100% | 204 | m3/м3
UGPipingPart4 |  | 338 | 2020-04-29 | 2021-03-11 |  | 100%
CN-CMN-PI-1000-326 | Prefabrication DRAINAGE SYSTEM / PITS - Part 4 UG | 28 | 2020-04-29 | 2020-05-27 | ea/шт | 100% | 18 | ea/шт
CN-CMN-PI-1000-126 | Buried Pipe Trenches - Part 4 Excavation UG | 31 | 2020-07-24 | 2020-12-06 | m3/м3 | 100% | 111 | m3/м3
CN-CMN-PI-1000-206 | Erection DRAINAGE SYSTEM / PITS - Part 4 UG | 36 | 2020-08-05 | 2021-03-07 | ea/шт | 100% | 18 | ea/шт
CN-CMN-PI-1000-166 | Piping Erection - UG - Part 4 | 46 | 2020-10-05 | 2021-03-08 | DI | 100% | 452 | DI
CN-CMN-PI-1000-86 | Piping Painting - UG - Part 4 | 46 | 2020-10-07 | 2021-03-09 | m2/м2 | 100% | 396 | m2/м2
CN-CMN-PI-1000-246 | Buried Pipe Trenches - Backfilling UG - Part 4 | 27 | 2020-12-05 | 2021-03-10 | m3/м3 | 100% | 111 | m3/м3
CN-CMN-PI-1000-286 | Piping Testing (Hydrotesting) - UG - Part 4 | 43 | 2021-03-08 | 2021-03-11 | Стык/Jo | 100% | 1 | Стык/Jo
UGPipingPart5 |  | 502 | 2020-05-18 | 2021-11-02 |  | 79.96%
CN-CMN-PI-1000-336 | Prefabrication DRAINAGE SYSTEM / PITS - Part 5 UG | 90 | 2020-05-18 | 2021-07-02 | ea/шт | 96% | 60 | ea/шт
CN-CMN-PI-1000-2 | Buried Pipe Trenches - Part 5 Excavation UG | 110 | 2020-07-26 | 2021-08-11 | m3/м3 | 99% | 370 | m3/м3
CN-CMN-PI-1000-1 | Erection DRAINAGE SYSTEM / PITS - Part 5 UG | 220 | 2020-11-25 | 2021-10-03 | ea/шт | 51% | 71 | ea/шт
CN-CMN-PI-1000-16 | Piping Erection - UG - Part 5 | 160 | 2020-11-25 | 2021-10-03 | DI | 90% | 1510 | DI
CN-CMN-PI-1000-26 | Piping Painting - UG - Part 5 | 160 | 2020-12-12 | 2021-10-08 | m2/м2 | 90% | 1321 | m2/м2
CN-CMN-PI-1000-36 | Buried Pipe Trenches - Backfilling UG - Part 5 | 160 | 2020-12-17 | 2021-11-02 | m3/м3 | 54% | 370 | m3/м3
CN-CMN-PI-1000-46 | Piping Testing (Hydrotesting) - UG - Part 5 | 126 | 2021-06-10 | 2021-10-13 | Стык/Jo | 0% | 1 | Стык/Jo
AGPiping |  | 578 | 2020-04-29 | 2022-03-29 |  | 27.51%
CN-CMN-PI-1141 | Pipe Supports - Prefabrication - AG | 40 | 2020-04-29 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-CMN-PI-1000-3 | Piping Erection - AG | 227 | 2021-02-03 | 2022-02-07 | DI | 15.4% | 1575 | DI
CN-CMN-PI-1142 | Pipe Supports - Installation - AG | 227 | 2021-05-09 | 2022-02-07 | tons/тн | 15% | 1 | tons/тн
CN-CMN-PI-1000-6 | Piping Painting - AG | 20 | 2022-01-24 | 2022-02-12 | m2/м2 | 0% | 119 | m2/м2
CN-CMN-PI-1000-4 | Piping Testing (Hydrotesting) - AG | 25 | 2022-01-29 | 2022-02-22 | Стык/Jo | 0% | 1 | Стык/Jo
CN-CMN-PI-1000-5 | Piping Insulation - AG | 45 | 2022-02-13 | 2022-03-29 | m/м | 0% | 556 | m/м
Electrical |  | 260 | 2021-04-24 | 2022-05-11 |  | 26.4%
CN-CMN-EL-1000-1 | Cable Trenches | 210 | 2021-04-24 | 2022-03-22 | m3/м3 | 90% | 8981 | m3/м3
CN-CMN-EL-1000-7 | Electrical Tray Installation AG - Conduit pipe | 110 | 2021-09-09 | 2021-12-27 | m/м | 0% | 6986 | m/м
CN-CMN-EL-1000-2 | Electrical Cable Pulling - Common Area | 210 | 2021-09-24 | 2022-04-21 | m/м | 0% | 7050 | m/м
CN-CMN-EL-1000-6 | Electrical Junction Boxes | 75 | 2021-11-03 | 2022-01-16 | ea/шт | 0% | 166 | ea/шт
CN-CMN-EL-1000-4 | Earthing And Lightning | 60 | 2021-11-28 | 2022-01-26 | ea/шт | 0% | 6 | ea/шт
CN-CMN-EL-1000-5 | Lighting | 120 | 2022-01-02 | 2022-05-01 | ea/шт | 0% | 162 | ea/шт
CN-CMN-EL-1000-3 | Electrical Cable Termination | 111 | 2022-01-21 | 2022-05-11 | ea/шт | 0% | 2505 | ea/шт
Instrumetation |  | 120 | 2022-01-07 | 2022-05-06 |  | 0%
CN-CMN-IN-1000-2 | Instrument Cable Trays | 105 | 2022-01-07 | 2022-04-21 | m/м | 0% | 7823 | m/м
CN-CMN-IN-1000-3 | Instrument Cable Termination | 64 | 2022-03-04 | 2022-05-06 | ea/шт | 0% | 506 | ea/шт
CN-CMN-IN-1000-4 | Instrument Equipment Installation | 22 | 2022-04-10 | 2022-05-01 | ea/шт | 0% | 88 | ea/шт
CN-CMN-IN-1000-5 | Instrument Junction Boxes | 20 | 2022-04-12 | 2022-05-01 | ea/шт | 0% | 27 | ea/шт
HSE |  | 14 | 2022-05-12 | 2022-05-25 |  | 0%
CN-CMN-HS-1010 | HSE Works - Safety Signs, Misc Equipment | 14 | 2022-05-12 | 2022-05-25 | ea/шт | 0% | 5 | ea/шт
MAINPROCESSRACK-AREA51 |  | 992 | 2019-10-01 | 2022-06-18 |  | 50.39%
NORTHSOUTHPIPERACK |  | 992 | 2019-10-01 | 2022-06-18 |  | 50.39%
Civil/Structural |  | 987 | 2019-10-01 | 2022-06-13 |  | 79.63%
CN-MPR-CS-1420 | Backfilling - North South Piperack Area | 150 | 2020-02-15 | 2021-07-16 | m3/м3 | 90.36% | 14247 | m3/м3
CN-MPR-CS-1100 | Fireproofing - Main Piperack | 112 | 2022-02-22 | 2022-06-13 | m2/м2 | 0% | 888.42 | m2/м2
RackModule-EW-PR23 |  | 208 | 2019-10-01 | 2020-11-18 |  | 100%
CN-MPR-CS-1130-1 | Lean Concrete EW-PR23 | 124 | 2019-10-01 | 2019-10-18 | m3/м3 | 100% | 6 | m3/м3
CN-MPR-CS-1130 | Foundation - Rack Module - EW-PR23 | 151 | 2019-10-08 | 2020-03-06 | m3/м3 | 100% | 148 | m3/м3
CN-MPR-CS-1070 | Structural Steel Main Piperack - EW-PR23 | 40 | 2020-02-18 | 2020-11-18 | tons/тн | 100% | 127 | tons/тн
RackModule-NS-PR16 |  | 294 | 2019-11-02 | 2020-09-25 |  | 100%
CN-MPR-CS-1140-1 | Lean Concrete NS-PR16 | 8 | 2019-11-02 | 2019-11-15 | m3/м3 | 100% | 5 | m3/м3
CN-MPR-CS-1140 | Foundation - Rack Module - NS-PR16 | 169 | 2019-11-14 | 2020-09-25 | m3/м3 | 100% | 112 | m3/м3
CN-MPR-CS-1071 | Structural Steel Main Piperack - NS-PR16 | 50 | 2020-06-30 | 2020-07-16 | tons/тн | 100% | 103 | tons/тн
RackModule-NS-PR15 |  | 290 | 2019-11-04 | 2021-02-26 |  | 100%
CN-MPR-CS-1150-1 | Lean Concrete NS-PR15 | 18 | 2019-11-04 | 2019-12-21 | m3/м3 | 100% | 5 | m3/м3
CN-MPR-CS-1150 | Foundation - Rack Module - NS-PR15 | 166 | 2019-11-28 | 2021-02-26 | m3/м3 | 100% | 122.3 | m3/м3
CN-MPR-CS-1072 | Structural Steel Main Piperack - NS-PR15 | 52 | 2020-06-23 | 2020-07-31 | tons/тн | 100% | 115 | tons/тн
RackModule-NS-PR14 |  | 341 | 2019-11-06 | 2020-10-30 |  | 100%
CN-MPR-CS-1160-1 | Lean Concrete NS-PR14 | 4 | 2019-11-06 | 2019-12-18 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1160 | Foundation - Rack Module - NS-PR14 | 160 | 2019-12-05 | 2020-05-26 | m3/м3 | 100% | 109 | m3/м3
CN-MPR-CS-1073 | Structural Steel Main Piperack - NS-PR14 | 45 | 2020-08-18 | 2020-10-30 | tons/тн | 100% | 77 | tons/тн
RackModule-PR-LS03 |  | 162 | 2020-06-15 | 2020-12-06 |  | 100%
CN-MPR-CS-1170-1 | Lean Concrete PR-LS03 | 4 | 2020-06-15 | 2020-06-16 | m3/м3 | 100% | 2 | m3/м3
CN-MPR-CS-1170 | Foundation - Rack Module - PR-LS03 | 12 | 2020-06-24 | 2020-08-28 | m3/м3 | 100% | 36 | m3/м3
CN-MPR-CS-1110 | Structural Steel Main Piperack - PR-LS03 | 30 | 2020-10-03 | 2020-12-06 | tons/тн | 100% | 32 | tons/тн
RackModule-NS-PR13 |  | 344 | 2019-11-16 | 2020-10-15 |  | 100%
CN-MPR-CS-1180-1 | Lean Concrete NS-PR13 | 8 | 2019-11-16 | 2019-12-17 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1180 | Foundation - Rack Module - NS-PR13 | 162 | 2019-12-10 | 2020-08-20 | m3/м3 | 100% | 107.84 | m3/м3
CN-MPR-CS-1074 | Structural Steel Main Piperack - NS-PR13 | 30 | 2020-09-04 | 2020-10-15 | tons/тн | 100% | 59 | tons/тн
RackModule-NS-PR12 |  | 359 | 2019-11-19 | 2021-03-10 |  | 100%
CN-MPR-CS-1190-1 | Lean Concrete NS-PR12 | 8 | 2019-11-19 | 2019-12-22 | m3/м3 | 100% | 5 | m3/м3
CN-MPR-CS-1190 | Foundation - Rack Module - NS-PR12 | 156 | 2019-12-11 | 2020-09-20 | m3/м3 | 100% | 101 | m3/м3
CN-MPR-CS-1430 | Structural Steel Main Piperack - NS-PR12 | 45 | 2020-09-08 | 2021-03-10 | tons/тн | 100% | 98 | tons/тн
RackModule-NS-PR11 |  | 383 | 2019-11-22 | 2021-03-12 |  | 100%
CN-MPR-CS-1200-1 | Lean Concrete NS-PR11 | 4 | 2019-11-22 | 2019-12-16 | m3/м3 | 100% | 6 | m3/м3
CN-MPR-CS-1200 | Foundation - Rack Module - NS-PR11 | 143 | 2019-12-16 | 2020-11-18 | m3/м3 | 100% | 134 | m3/м3
CN-MPR-CS-1112 | Structural Steel Main Piperack - NS-PR11 | 55 | 2020-09-17 | 2021-03-12 | tons/тн | 100% | 95 | tons/тн
RackModule-NS-PR10 |  | 399 | 2019-11-25 | 2020-11-23 |  | 100%
CN-MPR-CS-1210-1 | Lean Concrete NS-PR10 | 4 | 2019-11-25 | 2020-01-03 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1210 | Foundation - Rack Module - NS-PR10 | 145 | 2019-12-22 | 2020-11-22 | m3/м3 | 100% | 98 | m3/м3
CN-MPR-CS-1113 | Structural Steel Main Piperack - NS-PR10 | 40 | 2020-10-02 | 2020-11-23 | tons/тн | 100% | 51 | tons/тн
RackModule-NS-PR09 |  | 372 | 2019-12-22 | 2021-05-21 |  | 100%
CN-MPR-CS-1220-1 | Lean Concrete NS-PR09 | 4 | 2019-12-22 | 2020-08-11 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1220 | Foundation - Rack Module - NS-PR09 | 149 | 2019-12-24 | 2020-10-10 | m3/м3 | 100% | 94 | m3/м3
CN-MPR-CS-1114 | Structural Steel Main Piperack - NS-PR09 | 35 | 2020-10-24 | 2021-05-21 | tons/тн | 100% | 48 | tons/тн
Misc.Foundations |  | 95 | 2021-04-10 | 2021-08-29 |  | 81.81%
CN-MPR-CS-1340 | Foundation - Misc. Foundations (lighting poles etc) Main Piperack North-South | 23 | 2021-04-10 | 2021-07-12 | m3/м3 | 97% | 1 | m3/м3
CN-MPR-CS-1340-1 | Lean Concrete Misc. Foundations (lighting poles etc) Main Piperack North-South | 10 | 2021-04-10 | 2021-04-10 | m3/м3 | 100% | 44.55 | m3/м3
CN-MPR-CS-1090 | Misc Structural Steel - Main Piperack | 72 | 2021-05-12 | 2021-08-29 | m/м | 72.56% | 249 | m/м
Piping |  | 684 | 2020-04-29 | 2022-04-12 |  | 38.47%
CN-MPR-PI-1021 | Pipe Supports - Prefabrication - Main Process Rack | 169 | 2020-04-29 | 2021-01-22 | tons/тн | 100% | 28 | tons/тн
CN-MPR-PI-1000 | Piping Erection - Main Piperack North-South | 400 | 2020-06-25 | 2021-09-21 | DI | 54.2% | 6246 | DI
CN-MPR-PI-1020 | Piping Testing (RT, PWHT) - Main Piperack North-South | 270 | 2020-06-30 | 2021-09-26 | Стык/Jo | 53.5% | 742 | Стык/Jo
CN-MPR-PI-1022 | Pipe Supports - Installation Main Process Rack | 270 | 2020-10-14 | 2021-08-10 | tons/тн | 60% | 28 | tons/тн
CN-MPR-PI-1080 | Piping Testing (Hydrotests) | 140 | 2021-07-09 | 2021-11-25 | Стык/Jo | 0% | 1 | Стык/Jo
CN-MPR-PI-1023 | Piping Painting - Main Process Rack | 150 | 2021-07-24 | 2021-12-20 | m2/м2 | 0% | 1504 | m2/м2
CN-MPR-PI-1070 | Piping Insulation - Main Piperack North-South (process) | 160 | 2021-11-04 | 2022-04-12 | m/м | 0% | 4923 | m/м
Electrical |  | 354 | 2021-01-08 | 2022-01-31 |  | 19.65%
CN-MPR-EL-1010 | Electrical Cable Trays - Main Piperack North-South | 287 | 2021-01-08 | 2021-10-28 | m/м | 86% | 2990 | m/м
CN-MPR-EL-1000 | Electrical Junction Boxes - Main Piperack | 200 | 2021-06-11 | 2021-12-27 | ea/шт | 0% | 15975 | m/м
CN-MPR-EL-1200 | Electrical Cable Pulling - Main Piperack | 230 | 2021-06-16 | 2022-01-31 | m/м | 0% | 147 | ea/шт
CN-MPR-EL-1030 | Electrical Cable Terminations - Main Piperack North-South | 200 | 2021-06-16 | 2022-01-01 | ea/шт | 0% | 771 | ea/шт
CN-MPR-EL-1210 | Heat Tracing - Main Piperack North-South (process) | 72 | 2021-10-15 | 2021-12-25 | m/м | 0% | 8755 | m/м
CN-MPR-EL-1060 | Lighting - Main Piperack | 28 | 2021-12-22 | 2022-01-18 | ea/шт | 0% | 19 | ea/шт
Instrumentation |  | 364 | 2021-01-09 | 2022-02-12 |  | 46.1%
CN-MPR-IN-1010 | Instrument Cable Trays - Main Piperack North-South | 300 | 2021-01-09 | 2021-11-05 | m/м | 71% | 1183 | m/м
CN-MPR-IN-1080 | Instrument Cable Pulling - Main Piperack North-South | 200 | 2021-04-19 | 2021-11-12 | m/м | 95% | 4570 | m/м
CN-MPR-IN-1000 | Instrument Junction Boxes - Main Piperack | 200 | 2021-06-06 | 2021-12-22 | ea/шт | 0% | 10 | ea/шт
CN-MPR-IN-1020 | Field Instrument - Main Piperack North-South | 120 | 2021-09-03 | 2021-12-31 | ea/шт | 0% | 5 | ea/шт
CN-MPR-IN-1070 | F&G - Main Piperack | 115 | 2021-09-23 | 2022-01-15 | ea/шт | 0% | 17 | ea/шт
CN-MPR-IN-1071 | Instrument Testing - Main Piperack North-South | 60 | 2021-12-15 | 2022-02-12 | ea/шт | 0% | 16 | ea/шт
Telecom |  | 6 | 2022-02-13 | 2022-02-18 |  | 0%
CN-MPR-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Main Piperack | 6 | 2022-02-13 | 2022-02-18 | ea/шт | 0% | 22 | ea/шт
HSE |  | 5 | 2022-06-14 | 2022-06-18 |  | 0%
CN-MPR-HS-1000 | HSE Installation - Main Piperack | 5 | 2022-06-14 | 2022-06-18 | ea/шт | 0% | 1 | ea/шт
GASSEPARATIONAREA-AREA52 |  | 746 | 2020-07-13 | 2022-08-22 |  | 18.35%
GASSEPARATIONUNIT-TRAIN1 |  | 720 | 2020-07-18 | 2022-07-27 |  | 17.27%
Civil/Structural |  | 706 | 2020-07-18 | 2022-07-13 |  | 41.33%
CN-GS1-CS-1090-1 | Lean Concrete EW-PR38 | 7 | 2020-07-18 | 2020-07-20 | m3/м3 | 100% | 12 | m3/м3
CN-GS1-CS-1090 | Foundation - Rack Module - EW-PR38 | 53 | 2020-08-03 | 2021-07-26 | m3/м3 | 75% | 174.56 | m3/м3
CN-GS1-CS-1061 | Structural Steel Gas Separation Train 1 - EW-PR38 | 65 | 2020-10-21 | 2021-06-16 | tons/тн | 99.6% | 183 | tons/тн
CN-GS1-CS-1070 | Misc Structural Steel - Gas Separation Train 1 | 40 | 2021-05-26 | 2021-07-26 | m/м | 26.35% | 41 | tons/тн
CN-GS1-CS-1060 | Structural Steel GMP / Crossovers - Gas Separation Train 1 | 50 | 2021-06-17 | 2021-08-05 | tons/тн | 0% | 620 | m/м
CN-GS1-CS-1050 | E/I Supports - Gas Separation Train 1 | 6 | 2021-06-25 | 2021-06-30 | tons/тн | 0% | 2 | tons/тн
CN-GS1-CS-1150 | Backfilling - Inlet Separator Area - Train 1 | 60 | 2021-06-30 | 2021-08-28 | m3/м3 | 0% | 1585 | m3/м3
CN-GS1-CS-1080 | Fireproofing - Gas Separation Train 1 | 40 | 2022-06-04 | 2022-07-13 | m2/м2 | 0% | 748.56 | m2/м2
Mechanical |  | 135 | 2021-07-01 | 2021-11-12 |  | 0%
CN-GS1-MS-1010 | Erection - Filters Gas Separation Train 1 | 43 | 2021-07-01 | 2021-08-13 | tons/тн | 0% | 13 | tons/тн
CN-GS1-MS-1020 | Insulation - Inlet Recievers Gas Separation Train 1 | 28 | 2021-10-16 | 2021-11-12 | m2/м2 | 0% | 446 | m2/м2
Piping |  | 384 | 2020-11-03 | 2021-12-19 |  | 16.07%
CN-GS1-PI-1041 | Pipe Supports - Prefabrication Gas Separation Train 1 | 21 | 2020-11-03 | 2021-01-22 | tons/тн | 100% | 6 | tons/тн
CN-GS1-PI-1000 | Piping Erection - Gas Separation Train 1 | 160 | 2021-04-11 | 2021-09-28 | DI | 20.37% | 6 | tons/тн
CN-GS1-PI-1042 | Pipe Supports - Installation Gas Separation Train 1 | 160 | 2021-04-11 | 2021-09-18 | tons/тн | 22% | 3066 | DI
CN-GS1-PI-1010 | Piping Testing (RT, PWHT) - Gas Separation Train 1 | 160 | 2021-04-22 | 2021-10-03 | Стык/Jo | 5.93% | 1518 | Стык/Jo
CN-GS1-PI-1053 | Piping Testing (Hydrotests) | 38 | 2021-09-06 | 2021-10-13 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GS1-PI-1043 | Piping Painting - Gas Separation Train 1 | 28 | 2021-09-21 | 2021-10-18 | m2/м2 | 0% | 474 | m2/м2
CN-GS1-PI-1030 | Piping Insulation - Gas Separation Train 1 | 65 | 2021-10-16 | 2021-12-19 | m/м | 0% | 2422 | m/м
Electrical |  | 117 | 2021-09-07 | 2022-01-01 |  | 0%
CN-GS1-EL-1010 | Electrical Cable Trays - Gas Separation Train 1 | 32 | 2021-09-07 | 2021-10-08 | m/м | 0% | 949 | m/м
CN-GS1-EL-1120 | Heat Tracing - Gas Separation Train 1 | 60 | 2021-10-01 | 2021-11-29 | m/м | 0% | 9966 | m/м
CN-GS1-EL-1210 | Electrical Cable Pulling - Gas Separation Train 1 | 52 | 2021-10-02 | 2021-11-22 | m/м | 0% | 3250 | m/м
CN-GS1-EL-1020 | Electrical Junction Boxes - Gas Separation Train 1 | 15 | 2021-10-04 | 2021-10-18 | ea/шт | 0% | 173 | ea/шт
CN-GS1-EL-1040 | Electrical Cable Terminations - Gas Separation Train 1 | 36 | 2021-10-28 | 2021-12-02 | ea/шт | 0% | 70 | ea/шт
CN-GS1-EL-1030 | Lighting - Gas Separation Train 1 | 30 | 2021-12-03 | 2022-01-01 | ea/шт | 0% | 71 | ea/шт
Instrumentation |  | 149 | 2021-10-09 | 2022-03-06 |  | 0%
CN-GS1-IN-1000 | Instrument Cable Trays - Gas Separation Train 1 | 36 | 2021-10-09 | 2021-11-13 | m/м | 0% | 376 | m/м
CN-GS1-IN-1210 | Instrument Cable Pulling - Gas Separation Train 1 | 45 | 2021-10-29 | 2021-12-12 | m/м | 0% | 20240 | m/м
CN-GS1-IN-1020 | Instrument Junction Boxes - Gas Separation Train 1 | 10 | 2021-11-19 | 2021-11-28 | ea/шт | 0% | 30 | ea/шт
CN-GS1-IN-1030 | Field Instrument - Gas Separation Train 1 | 50 | 2021-11-29 | 2022-01-17 | ea/шт | 0% | 35 | ea/шт
CN-GS1-IN-1040 | Instrument Terminations - Gas Separation Train 1 | 51 | 2021-12-03 | 2022-01-22 | ea/шт | 0% | 1009 | ea/шт
CN-GS1-IN-1010 | F&G - Gas Separation Train 1 | 36 | 2021-12-19 | 2022-01-23 | ea/шт | 0% | 38 | ea/шт
CN-GS1-IN-1041 | Instrument Testing - Gas Separation Train 1 | 50 | 2022-01-16 | 2022-03-06 | ea/шт | 0% | 50 | ea/шт
Telecom |  | 5 | 2022-03-27 | 2022-03-31 |  | 0%
CN-GS1-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Gas Separation Train 1 | 5 | 2022-03-27 | 2022-03-31 | ea/шт | 0% | 2 | ea/шт
HSE |  | 14 | 2022-07-14 | 2022-07-27 |  | 0%
CN-GS1-HS-1000 | HSE Installation - Gas Separation Train 1 | 14 | 2022-07-14 | 2022-07-27 | ea/шт | 0% | 29 | ea/шт
GASSEPARATIONUNIT-TRAIN2 |  | 746 | 2020-07-13 | 2022-08-22 |  | 19.48%
Civil/Structural |  | 736 | 2020-07-13 | 2022-08-12 |  | 45.18%
CN-GS2-CS-1110-1 | Lean Concrete EW-PR39 | 7 | 2020-07-13 | 2020-11-22 | m3/м3 | 100% | 13 | m3/м3
CN-GS2-CS-1110 | Foundation - Rack Module - EW-PR39 | 38 | 2020-07-25 | 2021-07-26 | m3/м3 | 75% | 180.12 | m3/м3
CN-GS2-CS-1061 | Structural Steel Gas Separation Train 2 - EW-PR39 | 65 | 2020-11-19 | 2021-07-20 | tons/тн | 99.5% | 183 | tons/тн
CN-GS2-CS-1070 | Misc Structural Steel - Gas Separation Train 2 | 40 | 2021-05-21 | 2021-07-11 | m/м | 39.78% | 35 | tons/тн
CN-GS2-CS-1060 | Structural Steel GMP / Crossovers - Gas Separation Train 2 | 50 | 2021-07-23 | 2021-09-10 | tons/тн | 0% | 581 | m/м
CN-GS2-CS-1050 | E/I Supports - Gas Separation Train 2 | 6 | 2021-07-26 | 2021-07-31 | tons/тн | 0% | 1 | tons/тн
CN-GS2-CS-1130 | Backfilling - Inlet Separator Area - Train 2 | 60 | 2021-07-27 | 2021-09-24 | m3/м3 | 0% | 1585 | m3/м3
CN-GS2-CS-1080 | Fireproofing - Gas Separation Train 2 | 40 | 2022-07-04 | 2022-08-12 | m2/м2 | 0% | 677.74 | m2/м2
Mechanical |  | 115 | 2021-08-26 | 2021-12-18 |  | 0%
CN-GS2-MS-1010 | Erection - Filters Gas Separation Train 2 | 30 | 2021-08-26 | 2021-09-24 | tons/тн | 0% | 12 | tons/тн
CN-GS2-MS-1020 | Insulation - Inlet Recievers Gas Separation Train 2 | 22 | 2021-11-27 | 2021-12-18 | m2/м2 | 0% | 444 | m2/м2
Piping |  | 416 | 2020-11-03 | 2022-01-30 |  | 16.67%
CN-GS2-PI-1031 | Pipe Supports - Prefabrication Gas Separation Train 2 | 21 | 2020-11-03 | 2021-01-22 | tons/тн | 100% | 6 | tons/тн
CN-GS2-PI-1000 | Piping Erection - Gas Separation Train 2 | 175 | 2021-03-23 | 2021-10-30 | DI | 21.8% | 6 | tons/тн
CN-GS2-PI-1010 | Piping Testing (RT, PWHT) - Gas Separation Train 2 | 175 | 2021-04-05 | 2021-11-04 | Стык/Jo | 6% | 3114 | DI
CN-GS2-PI-1032 | Pipe Supports - Installation Gas Separation Train 2 | 175 | 2021-04-05 | 2021-10-20 | tons/тн | 25% | 1417 | Стык/Jo
CN-GS2-PI-1043 | Piping Testing (Hydrotests) | 38 | 2021-10-08 | 2021-11-14 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GS2-PI-1033 | Piping Painting - Gas Separation Train 2 | 28 | 2021-10-23 | 2021-11-19 | m2/м2 | 0% | 465 | m2/м2
CN-GS2-PI-1030 | Piping Insulation - Gas Separation Train 2 | 65 | 2021-11-27 | 2022-01-30 | m/м | 0% | 2328 | m/м
Electrical |  | 115 | 2021-10-09 | 2022-01-31 |  | 0%
CN-GS2-EL-1010 | Electrical Cable Trays - Gas Separation Train 2 | 32 | 2021-10-09 | 2021-11-09 | m/м | 0% | 949 | m/м
CN-GS2-EL-1220 | Electrical Cable Pulling - Gas Separation Train 2 | 52 | 2021-11-03 | 2021-12-24 | m/м | 0% | 200 | m/м
CN-GS2-EL-1020 | Electrical Junction Boxes - Gas Separation Train 2 | 15 | 2021-11-05 | 2021-11-19 | ea/шт | 0% | 162 | ea/шт
CN-GS2-PI-1020 | Heat Tracing - Gas Separation Train 2 | 60 | 2021-11-12 | 2022-01-10 | m/м | 0% | 4361 | m/м
CN-GS2-EL-1040 | Electrical Cable Terminations - Gas Separation Train 2 | 36 | 2021-12-14 | 2022-01-18 | ea/шт | 0% | 70 | ea/шт
CN-GS2-EL-1030 | Lighting - Gas Separation Train 2 | 28 | 2022-01-04 | 2022-01-31 | ea/шт | 0% | 69 | ea/шт
Instrumentation |  | 164 | 2021-11-13 | 2022-04-25 |  | 0%
CN-GS2-IN-1000 | Instrument Cable Trays - Gas Separation Train 2 | 36 | 2021-11-13 | 2021-12-18 | m/м | 0% | 347 | m/м
CN-GS2-IN-1220 | Instrument Cable Pulling - Gas Separation Train 2 | 45 | 2021-11-28 | 2022-01-11 | m/м | 0% | 18218 | m/м
CN-GS2-IN-1020 | Instrument Junction Boxes - Gas Separation Train 2 | 10 | 2021-12-24 | 2022-01-02 | ea/шт | 0% | 28 | ea/шт
CN-GS2-IN-1030 | Field Instrument - Gas Separation Train 2 | 50 | 2022-01-13 | 2022-03-03 | ea/шт | 0% | 32 | ea/шт
CN-GS2-IN-1040 | Instrument Terminations - Gas Separation Train 2 | 51 | 2022-01-18 | 2022-03-09 | ea/шт | 0% | 1008 | ea/шт
CN-GS2-IN-1010 | F&G - Gas Separation Train 2 | 35 | 2022-02-07 | 2022-03-13 | ea/шт | 0% | 37 | ea/шт
CN-GS2-IN-1041 | Instrument Testing - Gas Separation Train 2 | 50 | 2022-03-07 | 2022-04-25 | ea/шт | 0% | 44 | ea/шт
Telecom |  | 5 | 2022-05-07 | 2022-05-11 |  | 0%
CN-GS2-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Gas Separation Train 2 | 5 | 2022-05-07 | 2022-05-11 | ea/шт | 0% | 4 | ea/шт
HSE |  | 13 | 2022-08-10 | 2022-08-22 |  | 0%
CN-GS2-HS-1000 | HSE Installation - Gas Separation Train 2 | 13 | 2022-08-10 | 2022-08-22 | ea/шт | 0% | 25 | ea/шт
GASCOMPRESSIONAREA-AREA53 |  | 974 | 2019-10-01 | 2022-05-31 |  | 40%
GASCOMPRESSIONUNIT-STRINGA |  | 897 | 2019-10-01 | 2022-03-15 |  | 48.25%
COMPRESSORBUILDINGAREA |  | 897 | 2019-10-01 | 2022-03-15 |  | 45.99%
COMPRESSORBUILDING |  | 897 | 2019-10-01 | 2022-03-15 |  | 56.04%
Civil/Structural |  | 855 | 2019-10-01 | 2022-02-01 |  | 82.67%
CN-GCA-B-CS-1070 | Backfilling - Compressor Building Area Train A | 242 | 2019-10-01 | 2021-06-10 | m3/м3 | 96% | 11950 | m3/м3
CN-GCA-B-CS-1000 | Lean Concrete - Compressor Train A | 6 | 2019-10-15 | 2020-10-29 | m3/м3 | 100% | 36.45 | m3/м3
CN-GCA-B-CS-1010 | Foundation - Compressor Area Train A | 227 | 2019-11-05 | 2021-06-07 | m3/м3 | 99.5% | 1005.13 | m3/м3
CN-GCA-B-CS-1020 | Building Structural Steel Erection (Primary Steel) - Compressor Train A | 87 | 2020-05-14 | 2021-06-07 | tons/тн | 99.5% | 375 | tons/тн
CN-GCA-B-CS-1100 | Building Cladding - Compressor Train A | 45 | 2020-09-25 | 2021-06-09 | m2/м2 | 86.7% | 2742 | m2/м2
CN-GCA-B-CS-1050 | Building Structural Steel Erection (Secondary Steel) - Compressor Train A | 45 | 2020-10-24 | 2021-06-07 | tons/тн | 95% | 4 | tons/тн
CN-GCA-B-CS-1080 | Structural Steel GMP / Crossovers - Compressor Train A | 150 | 2020-11-21 | 2021-06-15 | tons/тн | 99.5% | 117 | tons/тн
CN-GCA-B-CS-1040 | E/I Supports - Compressor Area Train A | 35 | 2020-11-30 | 2021-06-04 | tons/тн | 99% | 32 | tons/тн
CN-GCA-B-CS-1110 | Building Internal Works - Compressor Train A | 280 | 2021-02-06 | 2021-11-18 | компл. | 75% | 1 | компл.
CN-GCA-B-CS-1060 | Misc Structural Steel - Compressor Area Train A | 30 | 2021-02-22 | 2021-06-10 | m/м | 86% | 198 | m/м
CN-GCA-B-CS-1030 | Piping Supports - Compressor Area Train A | 60 | 2021-03-03 | 2021-06-11 | tons/тн | 60% | 11 | tons/тн
CN-GCA-B-CS-1090 | Fireproofing - Compressor Area Train A | 50 | 2021-06-12 | 2021-07-31 | m2/м2 | 0% | 1273 | m2/м2
CN-GCA-B-CS-1120 | Building Finishing - Compressor Train A | 120 | 2021-10-05 | 2022-02-01 | компл. | 0% | 1 | компл.
Mechanical |  | 669 | 2020-03-27 | 2022-02-07 |  | 81.63%
CN-GCA-B-MS-1000 | Erection - Scrubber Train A | 100 | 2020-03-27 | 2021-05-07 | tons/тн | 100% | 163 | tons/тн
CN-GCA-B-MR-1000 | Erection - GTC Erection and Enclosure Train A | 100 | 2020-04-08 | 2022-01-01 | tons/тн | 99% | 413 | tons/тн
CN-GCA-B-CR-1000 | Building Crane Installation (incl. load test) - Compressor Train A | 15 | 2020-11-17 | 2021-04-20 | tons/тн | 100% | 9 | tons/тн
CN-GCA-B-HV-1000 | Building HVAC - Compressor Train A | 165 | 2021-06-02 | 2022-01-22 | компл. | 5% | 1 | компл.
CN-GCA-B-MS-1010 | Insulation - Scrubber Train A | 15 | 2022-01-24 | 2022-02-07 | m2/м2 | 0% | 117 | m2/м2
Piping |  | 596 | 2020-04-29 | 2022-01-18 |  | 29.17%
CN-GCA-B-PI-1000 | Pipe Supports - Prefabrication Compressor Train A | 39 | 2020-04-29 | 2021-01-21 | tons/тн | 100% | 6 | tons/тн
CN-GCA-B-PI-1020 | Piping Erection - Compressor Train A | 120 | 2020-09-19 | 2021-09-10 | DI | 41.3% | 2804 | DI
CN-GCA-B-PI-1030 | Piping Testing (RT, PWHT) - Compressor Train A | 85 | 2020-10-03 | 2021-09-26 | Стык/Jo | 33.25% | 1138 | Стык/Jo
CN-GCA-B-PI-1010 | Pipe Supports - Installation Compressor Train A | 150 | 2021-01-22 | 2021-09-04 | tons/тн | 44% | 6 | tons/тн
CN-GCA-B-PI-1040 | Piping Testing (Hydrotests) - Compressor Train A | 68 | 2021-09-19 | 2021-11-25 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCA-B-PI-1050 | Piping Painting - Compressor Train A | 26 | 2021-11-15 | 2021-12-10 | m2/м2 | 0% | 416 | m2/м2
CN-GCA-B-PI-1060 | Piping Insulation - Compressor Train A (process) | 45 | 2021-12-05 | 2022-01-18 | m/м | 0% | 2610 | m/м
Electrical |  | 188 | 2021-04-06 | 2021-12-24 |  | 1.2%
CN-GCA-B-EL-1000 | Electrical Cable Trays - Compressor Train A | 85 | 2021-04-06 | 2021-09-20 | m/м | 11% | 1722 | m/м
CN-GCA-B-EL-1010 | Electrical Cable Pulling - Compressor Area Train A | 60 | 2021-08-17 | 2021-10-15 | m/м | 0% | 1500 | m/м
CN-GCA-B-EL-1020 | Building Electrical (cables) - Compressor Train A | 75 | 2021-09-11 | 2021-11-24 | m/м | 0% | 12619 | m/м
CN-GCA-B-EL-1030 | Electrical Junction Boxes - Compressor Area Train A | 30 | 2021-09-26 | 2021-10-25 | ea/шт | 0% | 148 | ea/шт
CN-GCA-B-EL-1070 | Electrical Cable Terminations - Compressor Train A | 30 | 2021-10-16 | 2021-11-14 | ea/шт | 0% | 71 | ea/шт
CN-GCA-B-EL-1060 | Building Electrical (terminations) - Compressor Train A | 60 | 2021-10-21 | 2021-12-19 | ea/шт | 0% | 360 | ea/шт
CN-GCA-B-EL-1040 | Earthing & Lightening - Compressor Area Train A | 30 | 2021-11-05 | 2021-12-04 | ea/шт | 0% | 370 | ea/шт
CN-GCA-B-EL-1080 | Lighting - Compressor Area Train A | 30 | 2021-11-10 | 2021-12-09 | ea/шт | 0% | 139 | ea/шт
CN-GCA-B-EL-1050 | Heat Tracing - Compressor Train A (process) | 30 | 2021-11-25 | 2021-12-24 | m/м | 0% | 4808 | m/м
Instrumentation |  | 186 | 2021-04-06 | 2022-02-05 |  | 33.68%
CN-GCA-B-IN-1000 | Instrument Cable Trays - Compressor Train A | 50 | 2021-04-06 | 2021-09-30 | m/м | 10% | 2481 | m/м
CN-GCA-B-IN-1040 | Instrument Cable Pulling - Compressor Area Train A | 155 | 2021-05-24 | 2022-01-21 | m/м | 52.65% | 74585 | m/м
CN-GCA-B-IN-1010 | Instrument Junction Boxes - Compressor Area Train A | 30 | 2021-09-26 | 2021-10-25 | ea/шт | 0% | 71 | ea/шт
CN-GCA-B-IN-1020 | Field Instrument - Compressor Train A | 85 | 2021-10-26 | 2022-01-18 | ea/шт | 0% | 64 | ea/шт
CN-GCA-B-IN-1060 | Instrument Terminations - Compressor Train A | 80 | 2021-11-13 | 2022-01-31 | ea/шт | 0% | 1631 | ea/шт
CN-GCA-B-IN-1030 | Building Instrumentation (Cables & Tubing) - Compressor Train A | 45 | 2021-12-13 | 2022-01-26 | m/м | 0% | 2930 | m/м
CN-GCA-B-IN-1070 | F&G - Compressor Area Train A | 45 | 2021-12-23 | 2022-02-05 | ea/шт | 0% | 112 | ea/шт
CN-GCA-B-IN-1050 | Building Instrumentation (Terminations) - Compressor Train A | 15 | 2022-01-17 | 2022-01-31 | ea/шт | 0% | 33 | ea/шт
CN-GCA-B-IN-1080 | Instrument Testing - Compressor Train A | 10 | 2022-01-27 | 2022-02-05 | ea/шт | 0% | 22 | ea/шт
Telecom |  | 20 | 2022-01-31 | 2022-02-19 |  | 0%
CN-GCA-B-TE-1000 | Telecom Equipment / Trays / JBs / Terminations - Compressor Area Train A | 20 | 2022-01-31 | 2022-02-19 | m/м | 0% | 364 | m/м
HSE |  | 29 | 2022-02-15 | 2022-03-15 |  | 0%
CN-GCA-B-HS-1000 | HSE Installation - Compressor Area Train A | 29 | 2022-02-15 | 2022-03-15 | ea/шт | 0% | 89 | ea/шт
LERBUILDING |  | 647 | 2020-05-06 | 2022-02-20 |  | 16.36%
Civil/Structural |  | 493 | 2020-05-06 | 2021-09-19 |  | 84.22%
CN-GCA-L-CV-1000 | Lean Concrete - LER Building Train A | 7 | 2020-05-06 | 2020-05-07 | m3/м3 | 100% | 3.9 | m3/м3
CN-GCA-L-CV-1010 | Foundation - LER 05 TRAIN A | 17 | 2020-05-15 | 2020-06-12 | m3/м3 | 100% | 44 | m3/м3
CN-GCA-L-CV-1020 | Building Structural Steel Erection - LER Train A | 59 | 2020-08-28 | 2021-07-08 | tons/тн | 93% | 119 | tons/тн
CN-GCA-L-CV-1040 | Building Cladding - LER Train A | 26 | 2020-12-22 | 2021-01-08 | m2/м2 | 100% | 808 | m2/м2
CN-GCA-L-CV-1050 | Building Internal Works - LER Train A | 100 | 2021-02-25 | 2021-06-16 | компл. | 40% | 1 | компл.
CN-GCA-L-CV-1030 | Fireproofing - LER Building Train A | 30 | 2021-05-16 | 2021-07-31 | m2/м2 | 99.74% | 359.93 | m2/м2
CN-GCA-L-CV-1060 | Building Finishing - LER Train A | 50 | 2021-08-01 | 2021-09-19 | компл. | 0% | 1 | компл.
Mechanical |  | 45 | 2021-06-24 | 2021-08-07 |  | 0%
CN-GCA-L-HV-1000 | Building HVAC - LER Train A | 45 | 2021-06-24 | 2021-08-07 | компл. | 0% | 1 | компл.
Electrical |  | 165 | 2021-05-21 | 2021-11-27 |  | 0.51%
CN-GCA-L-EL-1010 | Electrical Cable Trays - LER Building Train A | 50 | 2021-05-21 | 2021-10-17 | m/м | 25% | 619 | m/м
CN-GCA-L-EL-1020 | Building Electrical - LER Building Train A | 140 | 2021-06-16 | 2021-11-02 | m/м | 0% | 62883 | m/м
CN-GCA-L-EL-1040 | Electrical Junction Boxes - LER Building Train A | 60 | 2021-07-06 | 2021-09-03 | ea/шт | 0% | 11 | ea/шт
CN-GCA-L-EL-1050 | Building Electrical (terminations) - LER Building Train A | 90 | 2021-08-15 | 2021-11-12 | ea/шт | 0% | 1763 | ea/шт
CN-GCA-L-EL-1060 | Electrical Equipment Installation - LER Building String A | 75 | 2021-08-25 | 2021-11-07 | tons/тн | 0% | 53 | tons/тн
CN-GCA-L-EL-1030 | Earthing & Lightening - LER Building Train A | 45 | 2021-09-29 | 2021-11-12 | ea/шт | 0% | 129 | ea/шт
CN-GCA-L-EL-1070 | Lighting - LER Building Train A | 45 | 2021-09-29 | 2021-11-12 | ea/шт | 0% | 24 | ea/шт
CN-GCA-L-EL-1000 | Heat Tracing - LER Building Train A | 35 | 2021-10-24 | 2021-11-27 | m/м | 0% | 80 | m/м
Instrumentation |  | 107 | 2021-05-21 | 2022-01-27 |  | 9.71%
CN-GCA-L-IN-1000 | Instrument Cable Trays - LER Building Train A | 30 | 2021-05-21 | 2021-11-23 | m/м | 17% | 1345 | m/м
CN-GCA-L-IN-1010 | Building Instrumentation - LER Train A | 30 | 2021-11-24 | 2021-12-23 | m/м | 0% | 2744 | m/м
CN-GCA-L-IN-1030 | Field Instrument - LER Building Train A | 15 | 2021-12-24 | 2022-01-07 | ea/шт | 0% | 13 | ea/шт
CN-GCA-L-IN-1020 | Building Instrumentation (Terminations) - LER Building | 15 | 2021-12-29 | 2022-01-12 | ea/шт | 0% | 5 | ea/шт
CN-GCA-L-IN-1040 | F&G - LER Building Train A | 15 | 2022-01-13 | 2022-01-27 | ea/шт | 0% | 29 | ea/шт
Telecom |  | 7 | 2022-01-28 | 2022-02-03 |  | 0%
CN-GCA-L-TE-1000 | Telecom Equipment / Trays / JBs / Terminations - LER Building Train A | 7 | 2022-01-28 | 2022-02-03 | m/м | 0% | 235 | m/м
HSE |  | 59 | 2021-12-24 | 2022-02-20 |  | 0%
CN-GCA-L-HS-1000 | HSE Installation - LER Building Train A | 59 | 2021-12-24 | 2022-02-20 | ea/шт | 0% | 41 | ea/шт
COMPRESSORPIPERACK/AIRCOOLER/CABLERACK |  | 882 | 2019-10-09 | 2022-03-08 |  | 50.75%
AIRCOOLER/CABLERACK |  | 719 | 2020-03-13 | 2022-03-08 |  | 47.96%
Civil/Structural |  | 476 | 2020-03-13 | 2021-07-08 |  | 68.61%
CN-GCA-C-CV-1010 | Lean Concrete - Air Coolers Train A | 15 | 2020-03-13 | 2020-06-07 | m3/м3 | 100% | 21.87 | m3/м3
CN-GCA-C-CV-1000 | Lean Concrete - NS-PR 37 A & B Train A | 4 | 2020-03-13 | 2020-06-27 | m3/м3 | 100% | 9.67 | m3/м3
CN-GCA-C-CV-1050 | Foundation - Air Cooler Train A | 56 | 2020-03-22 | 2020-11-17 | m3/м3 | 100% | 327 | m3/м3
CN-GCA-C-CV-1020 | Foundation - NS-PR 37 A & B Train A | 37 | 2020-04-04 | 2020-07-21 | m3/м3 | 100% | 175.55 | m3/м3
CN-GCA-C-CV-1030 | Structural Steel - Cable Rack Train A | 30 | 2020-08-22 | 2021-06-16 | tons/тн | 79.9% | 54 | tons/тн
CN-GCA-C-CV-1060 | Structural Steel - NS-PR 37 A & B Train A | 55 | 2021-05-18 | 2021-06-12 | tons/тн | 22.6% | 139 | tons/тн
CN-GCA-C-CV-1040 | Side Cladding - Cable Rack Train A | 26 | 2021-06-13 | 2021-07-08 | m2/м2 | 0% | 129 | m2/м2
Mechanical |  | 467 | 2020-08-29 | 2022-01-04 |  | 91.75%
CN-GCA-C-MS-1020 | Pre-Assembly and Installation of Structure - Air Coolers Train A | 90 | 2020-08-29 | 2021-06-05 | tons/тн | 88% | 200 | tons/тн
CN-GCA-C-MS-1000 | Erection of Bundles (Incl. bolt tightning) - Air Coolers Train A | 120 | 2021-03-18 | 2021-08-06 | tons/тн | 95% | 490 | tons/тн
CN-GCA-C-MS-1010 | Insulation - Air Coolers Train A | 10 | 2021-12-26 | 2022-01-04 | m2/м2 | 0% | 72 | m2/м2
Piping |  | 544 | 2020-04-30 | 2022-02-13 |  | 8.83%
CN-GCA-C-PI-1000 | Pipe Supports - Prefabrication Air Cooler Train A | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 8 | tons/тн
CN-GCA-C-PI-1020 | Piping Erection Piping - Air Cooler Train A | 180 | 2021-03-08 | 2021-11-29 | DI | 7.9% | 8 | tons/тн
CN-GCA-C-PI-1010 | Pipe Supports - Installation Air Cooler Train A | 180 | 2021-03-08 | 2021-11-19 | tons/тн | 2% | 4717 | DI
CN-GCA-C-PI-1030 | Piping Testing (RT, PWHT) - Air Cooler Train A | 180 | 2021-03-10 | 2021-12-04 | Стык/Jo | 0.28% | 1083 | Стык/Jo
CN-GCA-C-PI-1040 | Piping Testing (Hydrotests) Balance Piping - Air Cooler Train A | 39 | 2021-11-11 | 2021-12-19 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCA-C-PI-1050 | Piping Painting - Air Cooler Train A | 45 | 2021-11-16 | 2021-12-30 | m2/м2 | 0% | 534 | m2/м2
CN-GCA-C-PI-1060 | Piping Insulation - Air Cooler Train A | 50 | 2021-12-26 | 2022-02-13 | m/м | 0% | 1952 | m/м
Electrical |  | 227 | 2021-01-05 | 2022-01-19 |  | 10.46%
CN-GCA-C-EL-1000 | Electrical Cable Trays - Cable Rack Train A | 25 | 2021-01-05 | 2021-06-13 | m/м | 69% | 921 | m/м
CN-GCA-C-EL-1010 | Electrical Cable Pulling - Cable Rack Train A | 26 | 2021-06-07 | 2021-07-02 | m/м | 0% | 1500 | m/м
CN-GCA-C-EL-1020 | Electrical Cable Terminations - Cable Rack Train A | 15 | 2021-06-26 | 2021-07-10 | ea/шт | 0% | 70 | ea/шт
CN-GCA-C-EL-1040 | Electrical Cable Trays - Air Coolers Train A | 10 | 2021-10-06 | 2021-10-15 | m/м | 0% | 663 | m/м
CN-GCA-C-EL-1050 | Electrical Cable Pulling - Air Coolers Train A | 30 | 2021-10-31 | 2021-11-29 | m/м | 0% | 1500 | m/м
CN-GCA-C-EL-1060 | Electrical Junction Boxes - Air Coolers Train A | 26 | 2021-11-20 | 2021-12-15 | ea/шт | 0% | 50 | ea/шт
CN-GCA-C-EL-1070 | Earthing And Lightning - Air Coolers Train A | 15 | 2021-12-05 | 2021-12-19 | ea/шт | 0% | 370 | ea/шт
CN-GCA-C-EL-1030 | Lighting - Cable Rack Train A | 7 | 2021-12-10 | 2021-12-16 | ea/шт | 0% | 6 | ea/шт
CN-GCA-C-EL-1080 | Electrical Cable Terminations - Air Coolers Train A | 10 | 2021-12-20 | 2021-12-29 | ea/шт | 0% | 460 | m/м
CN-GCA-C-EL-1090 | Lighting - Air Coolers Train A | 25 | 2021-12-20 | 2022-01-13 | ea/шт | 0% | 70 | ea/шт
CN-GCA-C-EL-1100 | Heat Tracing - Air Coolers Train A (process) | 15 | 2021-12-26 | 2022-01-09 | m/м | 0% | 134 | ea/шт
CN-GCA-C-EL-1110 | Heat Tracing - Cable Rack Train A (process) | 15 | 2022-01-05 | 2022-01-19 | m/м | 0% | 50 | m/м
Instrumentation |  | 265 | 2021-01-05 | 2022-02-24 |  | 1.19%
CN-GCA-C-IN-1000 | Instrument Cable Trays - Cable Rack Train A | 10 | 2021-01-05 | 2021-06-13 | m/м | 82% | 100 | m/м
CN-GCA-C-IN-1020 | Instrument Cable Pulling - Cable Rack Train A | 34 | 2021-06-05 | 2021-07-08 | m/м | 0% | 6349 | m/м
CN-GCA-C-IN-1040 | Instrument Junction Box - Cable Rack Train A | 7 | 2021-07-22 | 2021-07-28 | ea/шт | 0% | 22 | ea/шт
CN-GCA-C-IN-1010 | Instrument Cable Trays - Air Coolers Train A | 15 | 2021-10-21 | 2021-11-04 | m/м | 0% | 604 | m/м
CN-GCA-C-IN-1060 | Instrument Cable Pulling - Air Coolers Train A | 55 | 2021-11-05 | 2021-12-29 | m/м | 0% | 16686 | m/м
CN-GCA-C-IN-1050 | Field Instrument - Cable Rack Train A | 15 | 2021-12-20 | 2022-01-03 | ea/шт | 0% | 23 | ea/шт
CN-GCA-C-IN-1030 | Instrument Terminations - Cable Rack Train A | 10 | 2021-12-30 | 2022-01-08 | ea/шт | 0% | 75 | ea/шт
CN-GCA-C-IN-1090 | Field Instrument - Air Coolers Train A | 25 | 2022-01-04 | 2022-01-28 | ea/шт | 0% | 11 | ea/шт
CN-GCA-C-IN-1070 | Instrument Terminations - Air Coolers Train A | 30 | 2022-01-04 | 2022-02-02 | ea/шт | 0% | 325 | ea/шт
CN-GCA-C-IN-1080 | Instrument Junction Box - Air Coolers Train A | 7 | 2022-01-12 | 2022-01-18 | ea/шт | 0% | 14 | ea/шт
CN-GCA-C-IN-1100 | Fire & Gas (F&G) Detectors - Cable Rack Train A | 15 | 2022-02-03 | 2022-02-17 | ea/шт | 0% | 5 | ea/шт
CN-GCA-C-IN-1110 | Instrument Testing - Air Coolers Train A | 7 | 2022-02-18 | 2022-02-24 | ea/шт | 0% | 18 | ea/шт
Telecom |  | 7 | 2022-02-25 | 2022-03-03 |  | 0%
CN-GCA-C-TE-1000 | Telecom Equipment / Trays / JBs / Terminations - Air Cooler / Cable Rack Train A | 7 | 2022-02-25 | 2022-03-03 | m/м | 0% | 20 | m/м
HSE |  | 7 | 2022-03-02 | 2022-03-08 |  | 0%
CN-GCA-C-HS-1000 | HSE Installation - Air Coolers / Cable Rack Train A | 7 | 2022-03-02 | 2022-03-08 | ea/шт | 0% | 9 | ea/шт
PIPERACK(EW-PR24&EW-PR25) |  | 764 | 2019-10-09 | 2021-11-10 |  | 55.84%
Civil/Structural |  | 705 | 2019-10-09 | 2021-09-12 |  | 86.11%
CN-GCA-P-CS-1000 | Lean Concrete - Module (EW-PR 24) Train A | 8 | 2019-10-09 | 2019-10-16 | m3/м3 | 100% | 7 | m3/м3
CN-GCA-P-CS-1010 | Lean Concrete - Module (EW-PR 25) Train A | 8 | 2019-10-12 | 2019-10-24 | m3/м3 | 100% | 7 | m3/м3
CN-GCA-P-CS-1020 | Foundation - Rack Module - EW-PR24 | 94 | 2019-10-19 | 2020-01-20 | m3/м3 | 100% | 187 | m3/м3
CN-GCA-P-CS-1030 | Foundation - Rack Module - EW-PR25 | 180 | 2019-10-26 | 2020-10-28 | m3/м3 | 100% | 159 | m3/м3
CN-GCA-P-CS-1040 | Structural Steel Compressor Piperack - EW-PR24 | 36 | 2020-03-03 | 2020-11-23 | tons/тн | 100% | 157 | tons/тн
CN-GCA-P-CS-1050 | Structural Steel Compressor Piperack - EW-PR25 | 45 | 2020-03-15 | 2020-12-25 | tons/тн | 100% | 181 | tons/тн
CN-GCA-P-CS-1070 | Side Cladding - Process Piperack Train A | 26 | 2021-06-13 | 2021-07-08 | m2/м2 | 0% | 125 | m2/м2
CN-GCA-P-CS-1060 | Fireproofing - Process Piperack Train A | 43 | 2021-08-01 | 2021-09-12 | m2/м2 | 0% | 220 | m2/м2
Piping |  | 534 | 2020-04-18 | 2021-10-17 |  | 52.86%
CN-GCA-P-PI-1000 | Pipe Supports - Prefabrication Process Piperack Train A | 39 | 2020-04-18 | 2021-01-22 | tons/тн | 100% | 8 | tons/тн
CN-GCA-P-PI-1020 | Piping Erection - Compressor Rack EW-PR24 | 118 | 2020-07-08 | 2021-06-09 | DI | 80.9% | 1697 | DI
CN-GCA-P-PI-1040 | Piping Erection - Compressor Rack EW-PR25 | 96 | 2020-07-10 | 2021-06-14 | DI | 80.4% | 2005 | DI
CN-GCA-P-PI-1050 | Piping Testing (RT, PWHT) - Process Piperack Train A | 60 | 2020-09-13 | 2021-06-19 | Стык/Jo | 44.57% | 792 | Стык/Jo
CN-GCA-P-PI-1010 | Pipe Supports - Installation Process Piperack Train A | 120 | 2020-10-14 | 2021-06-09 | tons/тн | 79% | 8 | tons/тн
CN-GCA-P-PI-1030 | Piping Testing (Hydrotests) Compressor Rack EW-PR24 | 60 | 2021-06-25 | 2021-08-23 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCA-P-PI-1060 | Piping Testing (Hydrotests) Compressor Rack EW-PR25 | 60 | 2021-07-10 | 2021-09-07 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCA-P-PI-1070 | Piping Painting - Piperack Train A | 45 | 2021-07-30 | 2021-09-12 | m2/м2 | 0% | 556 | m2/м2
CN-GCA-P-PI-1080 | Piping Insulation - Process Piperack Train A | 45 | 2021-09-03 | 2021-10-17 | m/м | 0% | 2193 | m/м
Electrical |  | 242 | 2021-01-16 | 2021-09-27 |  | 11%
CN-GCA-P-EL-1000 | Electrical Cable Trays - Process Piperack Train A | 100 | 2021-01-16 | 2021-06-29 | m/м | 61% | 1246 | m/м
CN-GCA-P-EL-1010 | Electrical Cable Pulling - Process Piperack Train A | 34 | 2021-06-26 | 2021-07-29 | m/м | 0% | 3000 | m/м
CN-GCA-P-EL-1020 | Electrical Cable Terminations - Process Piperack Train A | 34 | 2021-07-11 | 2021-08-13 | ea/шт | 0% | 140 | ea/шт
CN-GCA-P-EL-1040 | Electrical Junction Boxes - Process Piperack Train A | 26 | 2021-07-16 | 2021-08-10 | ea/шт | 0% | 125 | ea/шт
CN-GCA-P-EL-1030 | Lighting - Process Piperack Train A | 15 | 2021-08-14 | 2021-08-28 | ea/шт | 0% | 39 | ea/шт
CN-GCA-P-EL-1050 | Heat Tracing - Process Piperack Train A | 30 | 2021-08-29 | 2021-09-27 | m/м | 0% | 6393 | m/м
Instrumentation |  | 269 | 2021-01-16 | 2021-10-24 |  | 5.28%
CN-GCA-P-IN-1000 | Instrument Cable Trays - Piperack Train A | 100 | 2021-01-16 | 2021-04-10 | m/м | 100% | 204 | m/м
CN-GCA-P-IN-1010 | Instrument Cable Pulling - Piperack Train A | 51 | 2021-06-09 | 2021-07-29 | m/м | 0% | 5255 | m/м
CN-GCA-P-IN-1020 | Instrument Junction Box - Piperack Train A | 15 | 2021-06-19 | 2021-07-03 | ea/шт | 0% | 19 | ea/шт
CN-GCA-P-IN-1030 | Field Instrument - Piperack Train A | 26 | 2021-08-23 | 2021-09-17 | ea/шт | 0% | 7 | ea/шт
CN-GCA-P-IN-1040 | Fire & Gas (F&G) Detectors - Piperack Train A | 15 | 2021-09-12 | 2021-09-26 | ea/шт | 0% | 7 | ea/шт
CN-GCA-P-IN-1050 | Instrument Testing - Piperack Train A | 15 | 2021-10-10 | 2021-10-24 | ea/шт | 0% | 44 | ea/шт
Telecom |  | 7 | 2021-10-25 | 2021-10-31 |  | 0%
CN-GCA-P-TE-1000 | Telecom Equipment - Piperack Train A | 7 | 2021-10-25 | 2021-10-31 | ea/шт | 0% | 1 | ea/шт
HSE |  | 7 | 2021-11-04 | 2021-11-10 |  | 0%
CN-GCA-P-HS-1000 | HSE Installation - Process Piperack Train A | 7 | 2021-11-04 | 2021-11-10 | ea/шт | 0% | 1 | ea/шт
GASCOMPRESSIONUNIT-STRINGB |  | 906 | 2019-10-11 | 2022-04-14 |  | 38.57%
COMPRESSORBUILDINGAREA |  | 906 | 2019-12-01 | 2022-04-14 |  | 36.67%
COMPRESSORBUILDING |  | 906 | 2019-12-01 | 2022-04-14 |  | 44.09%
Civil/Structural |  | 792 | 2019-12-01 | 2021-12-21 |  | 82.33%
CN-GCB-CS-1349-1 | Lean Concrete - Compressor Train B | 7 | 2019-12-01 | 2020-10-25 | m3/м3 | 100% | 35.37 | m3/м3
CN-GCB-CS-1349 | Foundation - Compressor Area Train B | 209 | 2019-12-11 | 2021-06-09 | m3/м3 | 99.9% | 787.51 | m3/м3
CN-GCB-CS-1360 | Foundation - Compressor Building Train B | 91 | 2020-01-15 | 2020-08-31 | m3/м3 | 100% | 463.6 | m3/м3
CN-GCB-CS-1480 | Backfilling - Compressor Building Area - Train B | 90 | 2020-04-18 | 2021-06-26 | m3/м3 | 51.25% | 12151 | m3/м3
CN-GCB-CS-1220 | Building Structural Steel Erection (Primary Steel) - Compressor Train B | 74 | 2020-08-04 | 2021-06-13 | tons/тн | 99.5% | 350 | tons/тн
CN-GCB-CS-1260 | Building Cladding - Compressor Train B | 70 | 2020-11-04 | 2021-06-19 | m2/м2 | 99% | 2742 | m2/м2
CN-GCB-CS-1460 | Building Structural Steel Erection (Secondary Steel) - Compressor Train B | 45 | 2020-11-20 | 2021-06-13 | tons/тн | 95% | 4 | tons/тн
CN-GCB-CS-1100 | E/I Supports - Compressor Area Train B | 100 | 2021-01-11 | 2021-06-13 | tons/тн | 81% | 32 | tons/тн
CN-GCB-CS-1140 | Structural Steel GMP / Crossovers - Compressor Train B | 110 | 2021-01-13 | 2021-06-13 | tons/тн | 92.5% | 117 | tons/тн
CN-GCB-CS-1080 | Piping Supports - Compressor Area Train B | 30 | 2021-03-04 | 2021-06-11 | tons/тн | 45.2% | 1 | компл.
CN-GCB-CS-1160 | Misc Structural Steel - Compressor Area Train B | 60 | 2021-03-05 | 2021-06-16 | m/м | 81% | 11 | tons/тн
CN-GCB-CS-1270 | Building Internal Works - Compressor Train B | 240 | 2021-03-22 | 2021-12-01 | компл. | 69% | 198 | m/м
CN-GCB-CS-1170 | Fireproofing - Compressor Area Train B | 50 | 2021-08-01 | 2021-09-19 | m2/м2 | 0% | 1316.19 | m2/м2
CN-GCB-CS-1210 | Building Finishing - Compressor Train B | 120 | 2021-08-24 | 2021-12-21 | компл. | 0% | 1 | компл.
Mechanical |  | 741 | 2020-03-08 | 2022-03-24 |  | 82.14%
CN-GCB-MS-1000 | Erection - Scrubber Train B | 110 | 2020-03-08 | 2021-05-07 | tons/тн | 100% | 163 | tons/тн
CN-GCB-MR-1000 | Erection - GTC Erection and Enclosure Train B | 110 | 2020-03-08 | 2022-01-25 | tons/тн | 99.7% | 413 | tons/тн
CN-GCB-CS-1250 | Building Crane Installation (incl. load test) - Compressor Train B | 110 | 2021-01-19 | 2021-04-20 | tons/тн | 100% | 9 | tons/тн
CN-GCB-HV-1010 | Building HVAC - Compressor Train B | 165 | 2021-06-04 | 2021-12-21 | компл. | 5% | 1 | компл.
CN-GCB-MS-1010 | Insulation - Scrubber Train B | 15 | 2022-03-10 | 2022-03-24 | m2/м2 | 0% | 117 | m2/м2
Piping |  | 588 | 2020-04-30 | 2022-03-04 |  | 9.21%
CN-GCB-PI-1091 | Pipe Supports - Prefabrication Compressor Train B | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 6 | tons/тн
CN-GCB-PI-1020 | Piping Erection - Compressor Train B | 210 | 2021-03-08 | 2021-11-26 | DI | 8.5% | 6 | tons/тн
CN-GCB-PI-1060 | Piping Testing (RT, PWHT) - Compressor Train B | 210 | 2021-03-11 | 2021-12-01 | Стык/Jo | 2.47% | 2727 | DI
CN-GCB-PI-1092 | Pipe Supports - Installation Compressor Train B | 210 | 2021-03-29 | 2021-11-16 | tons/тн | 10% | 1138 | Стык/Jo
CN-GCB-PI-1120 | Piping Testing (Hydrotests) | 68 | 2021-10-25 | 2021-12-31 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCB-PI-1093 | Piping Painting - Compressor Train B | 26 | 2021-12-21 | 2022-01-15 | m2/м2 | 0% | 416 | m2/м2
CN-GCB-PI-1090 | Piping Insulation - Compressor Train B (process) | 45 | 2022-01-19 | 2022-03-04 | m/м | 0% | 2587 | m/м
Electrical |  | 214 | 2021-07-20 | 2022-02-18 |  | 0%
CN-GCB-EL-1050 | Electrical Cable Trays - Compressor Train B | 85 | 2021-07-20 | 2021-10-12 | m/м | 0% | 1623 | m/м
CN-GCB-EL-1240 | Electrical Cable Pulling - Compressor Area Train B | 60 | 2021-09-08 | 2021-11-06 | m/м | 0% | 5750 | m/м
CN-GCB-EL-1010 | Building Electrical (cables) - Compressor Train B | 75 | 2021-10-03 | 2021-12-16 | m/м | 0% | 16437 | m/м
CN-GCB-EL-1070 | Electrical Junction Boxes - Compressor Area Train B | 30 | 2021-10-18 | 2021-11-16 | ea/шт | 0% | 123 | ea/шт
CN-GCB-EL-1251 | Electrical Equipment Installation - Compressor Train B | 75 | 2021-10-28 | 2022-01-10 | tons/тн | 0% | 1 | tons/тн
CN-GCB-EL-1100 | Electrical Cable Terminations - Compressor Train B | 30 | 2021-11-07 | 2021-12-06 | ea/шт | 0% | 71 | ea/шт
CN-GCB-EL-1270 | Building Electrical (terminations) - Compressor Train B | 60 | 2021-11-12 | 2022-01-10 | ea/шт | 0% | 342 | ea/шт
CN-GCB-EL-1080 | Earthing & Lightening - Compressor Area Train B | 30 | 2021-11-27 | 2021-12-26 | ea/шт | 0% | 370 | ea/шт
CN-GCB-EL-1120 | Lighting - Compressor Area Train B | 30 | 2021-12-02 | 2021-12-31 | ea/шт | 0% | 133 | ea/шт
CN-GCB-EL-1250 | Heat Tracing - Compressor Train B (process) | 40 | 2022-01-10 | 2022-02-18 | m/м | 0% | 5000 | m/м
Instrumentation |  | 209 | 2021-09-03 | 2022-03-30 |  | 0%
CN-GCB-IN-1040 | Instrument Cable Trays - Compressor Train B | 50 | 2021-09-03 | 2021-10-22 | m/м | 0% | 2315 | m/м
CN-GCB-IN-1220 | Instrument Cable Pulling - Compressor Area Train B | 170 | 2021-09-18 | 2022-03-06 | m/м | 0% | 130481 | m/м
CN-GCB-IN-1080 | Instrument Junction Boxes - Compressor Area Train B | 30 | 2021-10-18 | 2021-11-16 | ea/шт | 0% | 76 | ea/шт
CN-GCB-IN-1110 | Field Instrument - Compressor Train B | 85 | 2021-11-17 | 2022-02-09 | ea/шт | 0% | 62 | ea/шт
CN-GCB-IN-1150 | Instrument Terminations - Compressor Train B | 80 | 2021-12-22 | 2022-03-11 | ea/шт | 0% | 3206 | ea/шт
CN-GCB-IN-1010 | Building Instrumentation (Cables & Tubing) - Compressor Train B | 45 | 2022-01-26 | 2022-03-11 | m/м | 0% | 2958 | m/м
CN-GCB-IN-1100 | F&G - Compressor Area Train B | 45 | 2022-02-09 | 2022-03-25 | ea/шт | 0% | 103 | ea/шт
CN-GCB-IN-1230 | Building Instrumentation (Terminations) - Compressor Train B | 15 | 2022-03-02 | 2022-03-16 | ea/шт | 0% | 27 | ea/шт
CN-GCB-IN-1151 | Instrument Testing - Compressor Train B | 10 | 2022-03-21 | 2022-03-30 | ea/шт | 0% | 22 | ea/шт
Telecom |  | 20 | 2022-03-16 | 2022-04-04 |  | 0%
CN-GCB-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Compressor Area Train B | 20 | 2022-03-16 | 2022-04-04 | m/м | 0% | 371 | m/м
HSE |  | 15 | 2022-03-31 | 2022-04-14 |  | 0%
CN-GCB-HS-1001 | HSE Installation - Compressor Area Train B | 15 | 2022-03-31 | 2022-04-14 | ea/шт | 0% | 88 | ea/шт
LERBUILDING |  | 682 | 2020-05-25 | 2022-04-10 |  | 11.25%
Civil/Structural |  | 519 | 2020-05-25 | 2021-10-29 |  | 61.36%
CN-GCB-CS-1340-11 | Lean Concrete - LER Building Train B | 7 | 2020-05-25 | 2020-05-30 | m3/м3 | 100% | 2 | m3/м3
CN-GCB-CS-1500 | Foundation - LER Building Train B | 22 | 2020-05-30 | 2020-07-19 | m3/м3 | 100% | 44 | m3/м3
CN-GCB-CS-1560 | Building Structural Steel Erection - LER Train B | 54 | 2020-08-31 | 2021-06-10 | tons/тн | 86% | 119 | tons/тн
CN-GCB-CS-1600 | Building Cladding - LER Train B | 17 | 2021-01-10 | 2021-01-26 | m2/м2 | 100% | 808 | m2/м2
CN-GCB-CS-1620 | Building Internal Works - LER Train B | 100 | 2021-04-29 | 2021-08-07 | компл. | 40% | 1 | компл.
CN-GCB-CS-1630 | Building Finishing - LER Train B | 50 | 2021-09-10 | 2021-10-29 | компл. | 0% | 360 | m2/м2
CN-GCB-CS-1670 | Fireproofing - LER Building Train B | 30 | 2021-09-10 | 2021-10-09 | m2/м2 | 0% | 1 | компл.
Mechanical |  | 45 | 2021-08-14 | 2021-09-27 |  | 0%
CN-GCB-HV-1020 | Building HVAC - LER Train B | 45 | 2021-08-14 | 2021-09-27 | компл. | 0% | 1 | компл.
Electrical |  | 210 | 2021-09-13 | 2022-04-10 |  | 0%
CN-GCB-EL-1290 | Electrical Cable Trays - LER Building Train B | 50 | 2021-09-13 | 2021-11-01 | m/м | 0% | 619 | m/м
CN-GCB-EL-1310 | Building Electrical - LER Train B | 140 | 2021-10-08 | 2022-02-24 | m/м | 0% | 63214 | m/м
CN-GCB-EL-1300 | Electrical Junction Boxes - LER Building Train B | 60 | 2021-10-28 | 2021-12-26 | ea/шт | 0% | 11 | ea/шт
CN-GCB-EL-1340 | Building Electrical (terminations) - LER Building | 90 | 2021-12-07 | 2022-03-06 | ea/шт | 0% | 1777 | ea/шт
CN-GCB-EL-1380 | Electrical Equipment Installation - LER Building String B | 75 | 2021-12-17 | 2022-03-01 | tons/тн | 0% | 52 | tons/тн
CN-GCB-EL-1330 | Earthing & Lightening - LER Building Train B | 45 | 2022-01-26 | 2022-03-11 | ea/шт | 0% | 129 | ea/шт
CN-GCB-EL-1370 | Heat Tracing - LER Building Train B | 35 | 2022-02-20 | 2022-03-26 | m/м | 0% | 80 | m/м
CN-GCB-EL-1350 | Lighting - LER Building Train B | 45 | 2022-02-25 | 2022-04-10 | ea/шт | 0% | 5 | ea/шт
Instrumentation |  | 95 | 2021-11-17 | 2022-02-19 |  | 0%
CN-GCB-IN-1260 | Instrument Cable Trays - LER Building Train B | 30 | 2021-11-17 | 2021-12-16 | m/м | 0% | 475 | m/м
CN-GCB-IN-1280 | Building Instrumentation - LER Train B | 30 | 2021-12-07 | 2022-01-05 | m/м | 0% | 2758 | m/м
CN-GCB-IN-1310 | Field Instrument - LER Building Train B | 15 | 2022-01-06 | 2022-01-20 | ea/шт | 0% | 36 | ea/шт
CN-GCB-IN-1300 | Building Instrumentation (Terminations) - LER Building Train B | 15 | 2022-01-11 | 2022-01-25 | ea/шт | 0% | 17 | ea/шт
CN-GCB-IN-1320 | F&G - LER Building Train B | 15 | 2022-02-05 | 2022-02-19 | ea/шт | 0% | 35 | ea/шт
Telecom |  | 7 | 2022-03-20 | 2022-03-26 |  | 0%
CN-GCB-TL-1010 | Telecom Equipment / Trays / JBs / Terminations - LER Building Train B | 7 | 2022-03-20 | 2022-03-26 | m/м | 0% | 680 | m/м
HSE |  | 60 | 2022-02-10 | 2022-04-10 |  | 0%
CN-GCB-HS-1011 | HSE Installation - LER Building Train B | 60 | 2022-02-10 | 2022-04-10 | ea/шт | 0% | 41 | ea/шт
COMPRESSORPIPERACK/AIRCOOLER/CABLERACK |  | 880 | 2019-10-11 | 2022-03-30 |  | 40.85%
AIRCOOLER/CABLERACK |  | 748 | 2020-02-27 | 2022-03-30 |  | 37.24%
Civil/Structural |  | 471 | 2020-02-27 | 2021-06-26 |  | 85.13%
CN-GCB-CS-1320-1 | Lean Concrete - Air Cooler Train B | 7 | 2020-02-27 | 2020-06-07 | m3/м3 | 100% | 22 | m3/м3
CN-GCB-CS-1330-1 | Lean Concrete - NS-PR37 C&D Train B | 7 | 2020-02-29 | 2020-10-28 | m3/м3 | 100% | 7.31 | m3/м3
CN-GCB-CS-1330 | Foundation - NS-PR37 C&D Train B | 31 | 2020-03-08 | 2020-10-29 | m3/м3 | 100% | 188 | m3/м3
CN-GCB-CS-1320 | Foundation - Air Cooler Train B | 75 | 2020-03-16 | 2020-11-19 | m3/м3 | 100% | 327 | m3/м3
CN-GCB-CS-1150 | Structural Steel - Cable Rack Train B | 30 | 2020-08-24 | 2021-06-13 | tons/тн | 90% | 67 | tons/тн
CN-GCB-CS-1131 | Structural Steel - NS-PR37 C&D Train B | 45 | 2021-03-23 | 2021-06-11 | tons/тн | 68% | 139 | tons/тн
CN-GCB-CS-1130 | Structural Steel GMP / Crossovers - Air Cooler Train B | 14 | 2021-06-13 | 2021-06-26 | tons/тн | 0% | 8 | tons/тн
Mechanical |  | 402 | 2020-12-19 | 2022-01-24 |  | 56.11%
CN-GCB-MS-1061 | Pre-Assembly and Installation of Structure - Air Coolers Train B | 80 | 2020-12-19 | 2021-06-11 | tons/тн | 90.9% | 200 | tons/тн
CN-GCB-MS-1040 | Erection of Bundles (Incl. bolt tightning) - Air Coolers Train B | 120 | 2021-03-25 | 2021-08-29 | tons/тн | 36.98% | 490 | tons/тн
CN-GCB-MS-1051 | Insulation - Air Coolers Train B | 10 | 2022-01-15 | 2022-01-24 | m2/м2 | 0% | 72 | m2/м2
Piping |  | 535 | 2020-04-30 | 2022-03-05 |  | 8.25%
CN-GCB-PI-1101 | Pipe Supports Prefabrication - Air Coolers Train B | 42 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 8 | tons/тн
CN-GCB-PI-1010 | Piping Erection Main Header - Air Coolers Train B | 180 | 2021-03-15 | 2021-12-22 | DI | 6.9% | 8 | tons/тн
CN-GCB-PI-1050 | Piping Testing (RT, PWHT) - Air Coolers Train B | 180 | 2021-04-24 | 2021-12-27 | Стык/Jo | 0.28% | 4752 | DI
CN-GCB-PI-1102 | Pipe Supports Installation - Air Coolers Train B | 180 | 2021-04-24 | 2021-12-07 | tons/тн | 3% | 1082 | Стык/Jo
CN-GCB-PI-1140 | Piping Testing (Hydrotests) - Air Coolers Train B | 39 | 2021-11-29 | 2022-01-06 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCB-PI-1103 | Piping Painting - Air Coolers Train B | 45 | 2021-12-04 | 2022-01-17 | m2/м2 | 0% | 543 | m2/м2
CN-GCB-PI-1100 | Piping Insulation - Air Coolers Train B | 50 | 2022-01-15 | 2022-03-05 | m/м | 0% | 1945 | m/м
Electrical |  | 269 | 2021-01-06 | 2022-03-15 |  | 15.02%
CN-GCB-EL-1060 | Electrical Cable Trays - Cable Rack Train B | 25 | 2021-01-06 | 2021-06-19 | m/м | 99.8% | 898 | m/м
CN-GCB-EL-1280 | Electrical Cable Pulling - Cable Rack Train B | 34 | 2021-06-20 | 2021-07-23 | m/м | 0% | 1250 | m/м
CN-GCB-EL-1090 | Electrical Cable Terminations - Cable Rack Train B | 10 | 2021-07-24 | 2021-08-02 | ea/шт | 0% | 75 | ea/шт
CN-GCB-EL-1040 | Electrical Cable Trays - Air Coolers Train B | 10 | 2021-11-30 | 2021-12-09 | m/м | 0% | 563 | m/м
CN-GCB-EL-1520 | Electrical Cable Pulling - Aircoolers Train B | 30 | 2021-12-25 | 2022-01-23 | m/м | 0% | 1250 | m/м
CN-GCB-EL-1260 | Heat Tracing - Air Coolers Train B (process) | 15 | 2022-01-13 | 2022-01-27 | m/м | 0% | 458 | m/м
CN-GCB-EL-1540 | Electrical Junction Box - Air Coolers Train B | 26 | 2022-01-14 | 2022-02-08 | ea/шт | 0% | 46 | ea/шт
CN-GCB-EL-1191 | Heat Tracing - Cable Rack Train B | 15 | 2022-01-23 | 2022-02-06 | m/м | 0% | 50 | m/м
CN-GCB-EL-1110 | Electrical Cable Terminations - Air Coolers Train B | 10 | 2022-01-24 | 2022-02-02 | ea/шт | 0% | 75 | ea/шт
CN-GCB-EL-1094 | Earthing And Lightning - Air Coolers Train B | 15 | 2022-01-29 | 2022-02-12 | ea/шт | 0% | 370 | ea/шт
CN-GCB-EL-1091 | Lighting - Air Coolers Train B | 25 | 2022-02-03 | 2022-02-27 | ea/шт | 0% | 135 | ea/шт
CN-GCB-EL-1092 | Electrical Junction Box - Cable Rack Train B | 7 | 2022-02-12 | 2022-02-18 | ea/шт | 0% | 4 | ea/шт
CN-GCB-EL-1530 | Lighting - Cable Rack Train B | 7 | 2022-03-09 | 2022-03-15 | ea/шт | 0% | 1 | ea/шт
Instrumentation |  | 283 | 2021-01-06 | 2022-03-13 |  | 2.72%
CN-GCB-IN-1060 | Instrument Cable Trays - Cable Rack Train B | 30 | 2021-01-06 | 2021-04-15 | m/м | 100% | 125 | m/м
CN-GCB-IN-1530 | Instrument Cable Pulling - Cable Rack Train B | 30 | 2021-06-04 | 2021-07-03 | m/м | 0% | 8529 | m/м
CN-GCB-IN-1132 | Instrument Junction Boxes - Cable Rack Train B | 10 | 2021-06-10 | 2021-06-19 | ea/шт | 0% | 22 | ea/шт
CN-GCB-IN-1050 | Instrument Cable Trays - Air Cooler Train B | 15 | 2021-12-10 | 2021-12-24 | m/м | 0% | 35 | m/м
CN-GCB-IN-1520 | Instrument Cable Pulling - Air Cooler Train B | 20 | 2021-12-25 | 2022-01-13 | m/м | 0% | 11 | ea/шт
CN-GCB-IN-1120 | Field Instrument - Air Cooler Train B | 26 | 2021-12-27 | 2022-01-21 | ea/шт | 0% | 2388 | m/м
CN-GCB-IN-1070 | Field Instrument - Cable Rack Train B | 7 | 2022-01-07 | 2022-01-13 | ea/шт | 0% | 22 | ea/шт
CN-GCB-C-IN-1130 | Instrument Terminations - Cable Rack Train B | 10 | 2022-01-12 | 2022-01-21 | ea/шт | 0% | 150 | ea/шт
CN-GCB-IN-1490 | Instrument Junction Boxes - Air Coolers Train B | 10 | 2022-01-24 | 2022-02-02 | ea/шт | 0% | 14 | ea/шт
CN-GCB-C-IN-1120 | Instrument Terminations - Air Coolers Train B | 30 | 2022-01-24 | 2022-02-22 | ea/шт | 0% | 650 | ea/шт
CN-GCB-IN-1133 | Fire & Gas (F&G) Detectors - Cable Rack Train B | 12 | 2022-02-23 | 2022-03-06 | ea/шт | 0% | 5 | ea/шт
CN-GCB-IN-1510 | Instrument Testing - Air Cooler Train B | 7 | 2022-03-07 | 2022-03-13 | ea/шт | 0% | 18 | ea/шт
Telecom |  | 15 | 2022-03-16 | 2022-03-30 |  | 0%
CN-GCB-TL-1100 | Telecom Equipment / Trays / JBs / Terminations - Air Cooler / Cable Rack | 15 | 2022-03-16 | 2022-03-30 | ea/шт | 0% | 20 | ea/шт
HSE |  | 10 | 2022-03-21 | 2022-03-30 |  | 0%
CN-GCB-HS-1000 | HSE Installation - Air Coolers / Cable Rack Train B | 10 | 2022-03-21 | 2022-03-30 | ea/шт | 0% | 10 | ea/шт
PIPERACK(EW-PR26;EW-PR27&PR-LS04) |  | 774 | 2019-10-11 | 2021-12-14 |  | 46.65%
Civil/Structural |  | 711 | 2019-10-11 | 2021-10-12 |  | 80.61%
CN-GCB-CS-1310-11 | Lean Concrete - Module EW-PR 26 Train B | 3 | 2019-10-11 | 2019-10-16 | m3/м3 | 100% | 4 | m3/м3
CN-GCB-CS-1410-11 | Lean Concrete - Module EW-PR 27 Train B | 3 | 2019-10-19 | 2019-10-24 | m3/м3 | 100% | 7 | m3/м3
CN-GCB-CS-1710 | Foundation - Rack Module EW-PR27 Train B | 152 | 2019-11-05 | 2020-08-10 | m3/м3 | 100% | 173 | m3/м3
CN-GCB-CS-1690 | Foundation - Rack Module EW-PR26 Train B | 148 | 2019-11-06 | 2020-04-07 | m3/м3 | 100% | 88 | m3/м3
CN-GCB-CS-1420-11 | Lean Concrete - Module PR-LS-04 Train B | 2 | 2020-03-07 | 2020-03-09 | m3/м3 | 100% | 2 | m3/м3
CN-GCB-CS-1700 | Foundation - Rack Module - PR-LS04 | 10 | 2020-03-12 | 2020-05-24 | m3/м3 | 100% | 52 | m3/м3
CN-GCB-CS-1730 | Structural Steel Compressor Piperack - EW-PR26 | 30 | 2020-04-02 | 2021-06-07 | tons/тн | 98.23% | 115 | tons/тн
CN-GCB-CS-1740 | Structural Steel Compressor Piperack - EW-PR27 | 59 | 2020-04-12 | 2021-06-07 | tons/тн | 99.82% | 186 | tons/тн
CN-GCB-CS-1760 | Structural Steel - Compressor Piperack PR-LS04 Train B | 25 | 2020-10-19 | 2020-11-01 | tons/тн | 100% | 46 | tons/тн
CN-GCB-CS-1790 | Side Cladding - Piperack Train B | 20 | 2021-07-17 | 2021-08-05 | m2/м2 | 0% | 125 | m2/м2
CN-GCA-CS-1760 | Fireproofing - Piperack Train B | 43 | 2021-08-31 | 2021-10-12 | m2/м2 | 0% | 384.5 | m2/м2
Piping |  | 493 | 2020-04-30 | 2021-11-19 |  | 38.92%
CN-GCB-PI-1230 | Pipe Supports - Prefabrication Piperack Train B | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 8 | tons/тн
CN-GCB-PI-1160 | Piping Erection - Compressor Rack EW-PR 26 | 60 | 2020-07-19 | 2021-06-27 | DI | 67.9% | 795 | DI
CN-GCB-PI-1180 | Piping Erection - Compressor Rack EW-PR 27 | 60 | 2020-07-21 | 2021-06-28 | DI | 50.5% | 2104 | DI
CN-GCB-PI-1190 | Piping Testing (RT, PWHT) - Piperack Train B | 60 | 2020-09-15 | 2021-07-05 | Стык/Jo | 37.04% | 594 | Стык/Jo
CN-GCB-PI-1240 | Pipe Supports - Installation Piperack Train B | 60 | 2020-10-21 | 2021-06-16 | tons/тн | 63% | 10 | tons/тн
CN-GCB-PI-1290 | Piping Erection - Compressor Rack PR-LS 04 | 60 | 2020-11-23 | 2021-06-25 | DI | 53% | 588 | DI
CN-GCB-PI-1260 | Piping Testing (Hydrotests) Rack EW-PR 26 | 60 | 2021-07-20 | 2021-09-17 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCB-PI-1280 | Piping Testing (Hydrotests) Rack EW-PR 27 | 60 | 2021-07-30 | 2021-09-27 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCB-PI-1300 | Piping Testing (Hydrotests) Rack PR-LS 04 | 60 | 2021-08-09 | 2021-10-07 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCB-PI-1250 | Piping Painting - Piperack Train B | 45 | 2021-08-29 | 2021-10-12 | m2/м2 | 0% | 680 | m2/м2
CN-GCB-PI-1210 | Piping Insulation - Piperack Train B | 45 | 2021-10-06 | 2021-11-19 | m/м | 0% | 2204 | m/м
Electrical |  | 272 | 2021-01-17 | 2021-10-27 |  | 12.46%
CN-GCB-EL-1410 | Electrical Cable Trays - Piperack Train B | 100 | 2021-01-17 | 2021-06-29 | m/м | 43% | 1937 | m/м
CN-GCB-EL-1440 | Electrical Cable Pulling - Piperack Train B | 43 | 2021-07-30 | 2021-09-10 | m/м | 0% | 3750 | m/м
CN-GCB-EL-1500 | Electrical Junction Box - Piperack Train B | 26 | 2021-08-19 | 2021-09-13 | ea/шт | 0% | 91 | ea/шт
CN-GCB-EL-1460 | Electrical Cable Terminations - Piperack Train B | 18 | 2021-09-11 | 2021-09-28 | ea/шт | 0% | 225 | ea/шт
CN-GCB-EL-1490 | Lighting - Piperack Train B | 34 | 2021-09-11 | 2021-10-14 | ea/шт | 0% | 52 | ea/шт
CN-GCB-EL-1420 | Heat Tracing - Piperack Train B | 27 | 2021-10-01 | 2021-10-27 | m/м | 0% | 3018 | m/м
Instrumentation |  | 277 | 2021-01-17 | 2021-11-01 |  | 5.51%
CN-GCB-IN-1360 | Instrument Cable Trays - Piperack Train B | 35 | 2021-01-17 | 2021-04-10 | m/м | 100% | 210 | m/м
CN-GCB-IN-1540 | Instrument Cable Pulling - Piperack Train B | 62 | 2021-07-30 | 2021-09-29 | m/м | 0% | 10510 | m/м
CN-GCB-IN-1430 | Instrument Junction Boxes - Piperack Train B | 15 | 2021-08-19 | 2021-09-02 | ea/шт | 0% | 6 | ea/шт
CN-GCB-IN-1390 | Field Instrument - Piperack Train B | 26 | 2021-09-17 | 2021-10-12 | ea/шт | 0% | 6 | ea/шт
CN-GCB-IN-1440 | Fire & Gas (F&G) Detectors - Piperack Train B | 15 | 2021-10-08 | 2021-10-22 | ea/шт | 0% | 7 | ea/шт
CN-GCB-IN-1420 | Instrument Testing - Piperack Train B | 15 | 2021-10-18 | 2021-11-01 | ea/шт | 0% | 23 | ea/шт
Telecom |  | 5 | 2021-11-02 | 2021-11-06 |  | 0%
CN-GCB-TL-1110 | Telecom Equipment / Trays / JBs / Terminations - Piperack Train B | 5 | 2021-11-02 | 2021-11-06 | ea/шт | 0% | 8 | ea/шт
HSE |  | 25 | 2021-11-20 | 2021-12-14 |  | 0%
CN-GCB-HS-1021 | HSE Installation - Piperack Train B | 25 | 2021-11-20 | 2021-12-14 | ea/шт | 0% | 1 | ea/шт
GASCOMPRESSIONUNIT-STRINGC |  | 943 | 2019-10-20 | 2022-05-31 |  | 33.23%
COMPRESSORBUILDINGAREA |  | 937 | 2019-12-01 | 2022-05-25 |  | 36.5%
COMPRESSORBUILDING |  | 932 | 2019-12-01 | 2022-05-20 |  | 43.94%
Civil/Structural |  | 879 | 2019-12-01 | 2022-03-28 |  | 77.19%
CN-GCC-CS-1400 | Foundation - Compressor Building Train C | 146 | 2019-12-01 | 2021-02-26 | m3/м3 | 100% | 464 | m3/м3
CN-GCC-CS-1349-1 | Lean Concrete - Compressor Building Train C | 7 | 2019-12-15 | 2020-10-24 | m3/м3 | 100% | 24 | m3/м3
CN-GCC-CS-1349 | Foundation - Compressor Area Train C | 194 | 2019-12-28 | 2021-06-29 | m3/м3 | 99.95% | 680 | m3/м3
CN-GCC-CS-1480 | Backfilling - Compressor Building Area Train C | 90 | 2020-06-12 | 2021-07-28 | m3/м3 | 40.9% | 14718 | m3/м3
CN-GCC-CS-1460 | Building Structural Steel Erection (Primary Steel) - Compressor Train C | 75 | 2020-09-16 | 2021-06-21 | tons/тн | 95% | 375 | tons/тн
CN-GCC-CS-1270 | Building Cladding - Compressor Train C | 75 | 2021-01-26 | 2021-06-10 | m2/м2 | 94.2% | 2742 | m2/м2
CN-GCC-CS-1140 | Structural Steel GMP / Crossovers - Compressor Train C | 110 | 2021-03-21 | 2021-07-20 | tons/тн | 87.65% | 117 | tons/тн
CN-GCC-CS-1200 | Building Structural Steel Erection (Secondary Steel) - Compressor Train C | 60 | 2021-04-23 | 2021-06-21 | tons/тн | 95% | 4 | tons/тн
CN-GCC-CS-1100 | E/I Supports - Compressor Area Train C | 35 | 2021-04-29 | 2021-06-13 | tons/тн | 79% | 32 | tons/тн
CN-GCC-CS-1160 | Misc Structural Steel - Compressor Area Train C | 30 | 2021-05-08 | 2021-07-01 | m/м | 87% | 10 | tons/тн
CN-GCC-CS-1080 | Piping Supports - Compressor Area Train C | 30 | 2021-06-01 | 2021-07-05 | tons/тн | 76% | 1 | компл.
CN-GCC-CS-1280 | Building Internal Works - Compressor Train C | 240 | 2021-06-07 | 2022-02-01 | компл. | 0% | 198 | m/м
CN-GCC-CS-1170 | Fireproofing - Compressor Area Train C | 50 | 2021-09-25 | 2021-11-13 | m2/м2 | 0% | 1287.19 | m2/м2
CN-GCC-CS-1190 | Building Finishing - Compressor Train C | 120 | 2021-11-29 | 2022-03-28 | компл. | 0% | 1 | компл.
Mechanical |  | 784 | 2020-03-09 | 2022-05-08 |  | 80.71%
CN-GCC-MR-1000 | Erection - GTC Erection and Enclosure Train C | 365 | 2020-03-09 | 2022-03-12 | tons/тн | 99% | 413 | tons/тн
CN-GCC-MS-1000 | Erection - Scrubber Train C | 120 | 2020-03-18 | 2021-05-07 | tons/тн | 100% | 163 | tons/тн
CN-GCC-CS-1260 | Building Crane Installation (incl. load test) - Compressor Train C | 110 | 2021-05-25 | 2021-09-21 | tons/тн | 95% | 9 | tons/тн
CN-GCC-HV-1010 | Building HVAC - Compressor Train C | 165 | 2021-10-15 | 2022-03-28 | компл. | 0% | 1 | компл.
CN-GCC-MS-1010 | Insulation - Scrubber Train C | 15 | 2022-04-24 | 2022-05-08 | m2/м2 | 0% | 117 | m2/м2
Piping |  | 603 | 2020-04-30 | 2022-04-18 |  | 8.29%
CN-GCC-PI-1091 | Pipe Supports - Prefabrication Compressor Train C | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 6 | tons/тн
CN-GCC-PI-1010 | Piping Erection - Compressor Train C | 210 | 2021-04-06 | 2022-01-05 | DI | 7.4% | 6 | tons/тн
CN-GCC-PI-1092 | Pipe Supports - Installation Compressor Train C | 210 | 2021-04-06 | 2021-12-26 | tons/тн | 1% | 2466 | DI
CN-GCC-PI-1050 | Piping Testing (RT, PWHT) - Compressor Train C | 210 | 2021-04-23 | 2022-01-10 | Стык/Jo | 0.73% | 1089 | Стык/Jo
CN-GCC-PI-1120 | Piping Testing (Hydrotests) | 68 | 2021-12-04 | 2022-02-09 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCC-PI-1093 | Piping Painting - Compressor Train C | 26 | 2022-01-30 | 2022-02-24 | m2/м2 | 0% | 396 | m2/м2
CN-GCC-PI-1090 | Piping Insulation - Compressor Train C (process) | 45 | 2022-03-05 | 2022-04-18 | m/м | 0% | 2517 | m/м
Electrical |  | 204 | 2021-08-29 | 2022-03-20 |  | 0%
CN-GCC-EL-1050 | Electrical Cable Trays - Compressor Train C | 85 | 2021-08-29 | 2021-11-21 | m/м | 0% | 1652 | m/м
CN-GCC-EL-1250 | Electrical Cable Pulling - Compressor Area Train C | 60 | 2021-10-08 | 2021-12-06 | m/м | 0% | 2750 | m/м
CN-GCC-EL-1010 | Building Electrical (cables) - Compressor Train C | 75 | 2021-11-02 | 2022-01-15 | m/м | 0% | 16719 | m/м
CN-GCC-EL-1091 | Electrical Equipment Installation - Compressor Train C | 75 | 2021-12-07 | 2022-02-19 | kg/кг | 0% | 1 | kg/кг
CN-GCC-EL-1280 | Building Electrical (terminations) - Compressor Train C | 60 | 2021-12-12 | 2022-02-09 | ea/шт | 0% | 363 | ea/шт
CN-GCC-EL-1080 | Earthing & Lightening - Compressor Area Train C | 30 | 2021-12-27 | 2022-01-25 | ea/шт | 0% | 370 | ea/шт
CN-GCC-EL-1070 | Electrical Junction Boxes - Compressor Area Train C | 30 | 2022-01-01 | 2022-01-30 | ea/шт | 0% | 188 | ea/шт
CN-GCC-EL-1090 | Electrical Cable Terminations - Compressor Train C | 30 | 2022-01-21 | 2022-02-19 | ea/шт | 0% | 141 | ea/шт
CN-GCC-EL-1120 | Lighting - Compressor Area Train C | 30 | 2022-02-15 | 2022-03-16 | ea/шт | 0% | 7495 | m/м
CN-GCC-EL-1260 | Heat Tracing - Compressor Train C (process) | 30 | 2022-02-19 | 2022-03-20 | m/м | 0% | 128 | ea/шт
Instrumentation |  | 210 | 2021-10-13 | 2022-05-10 |  | 0%
CN-GCC-IN-1040 | Instrument Cable Trays - Compressor Train C | 50 | 2021-10-13 | 2021-12-01 | m/м | 0% | 852 | m/м
CN-GCC-IN-1220 | Instrument Cable Pulling - Compressor Area Train C | 155 | 2021-11-07 | 2022-04-10 | m/м | 0% | 112518 | m/м
CN-GCC-IN-1090 | Instrument Junction Boxes - Compressor Area Train C | 30 | 2021-12-07 | 2022-01-05 | ea/шт | 0% | 77 | ea/шт
CN-GCC-IN-1110 | Field Instrument - Compressor Train C | 85 | 2022-01-06 | 2022-03-31 | ea/шт | 0% | 62 | ea/шт
CN-GCC-IN-1140 | Instrument Terminations - Compressor Train C | 80 | 2022-01-31 | 2022-04-20 | ea/шт | 0% | 3206 | ea/шт
CN-GCC-IN-1010 | Building Instrumentation (Cables & Tubing) - Compressor Train C | 45 | 2022-03-12 | 2022-04-25 | m/м | 0% | 2933 | m/м
CN-GCC-IN-1100 | F&G - Compressor Area Train C | 20 | 2022-04-11 | 2022-04-30 | ea/шт | 0% | 78 | ea/шт
CN-GCC-IN-1230 | Building Instrumentation (Terminations) - Compressor Train C | 15 | 2022-04-26 | 2022-05-10 | ea/шт | 0% | 27 | ea/шт
CN-GCC-IN-1141 | Instrument Testing - Compressor Train C | 10 | 2022-05-01 | 2022-05-10 | ea/шт | 0% | 22 | ea/шт
Telecom |  | 20 | 2022-04-26 | 2022-05-15 |  | 0%
CN-GCC-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Compressor Area Train C | 20 | 2022-04-26 | 2022-05-15 | m/м | 0% | 433 | m/м
HSE |  | 10 | 2022-05-11 | 2022-05-20 |  | 0%
CN-GCC-HS-1001 | HSE Installation - Compressor Area Train C | 10 | 2022-05-11 | 2022-05-20 | ea/шт | 0% | 91 | ea/шт
LERBUILDING |  | 742 | 2020-05-01 | 2022-05-25 |  | 12.22%
Civil/Structural |  | 609 | 2020-05-01 | 2022-01-12 |  | 66.13%
CN-GCC-CS-1310-11 | Lean Concrete - LER Building Train C | 7 | 2020-05-01 | 2020-05-06 | m3/м3 | 100% | 2 | m3/м3
CN-GCC-CS-1500 | Foundation - LER Building Train C | 26 | 2020-06-16 | 2020-07-28 | m3/м3 | 100% | 44 | m3/м3
CN-GCC-CS-1560 | Building Structural Steel Erection - LER Train C | 31 | 2020-11-01 | 2021-06-13 | tons/тн | 85% | 119 | tons/тн
CN-GCC-CS-1600 | Building Cladding - LER Train C | 26 | 2021-01-23 | 2021-02-06 | m2/м2 | 100% | 808 | m2/м2
CN-GCC-CS-1620 | Building Internal Works - LER Train C | 100 | 2021-05-12 | 2021-09-06 | компл. | 5% | 1 | компл.
CN-GCC-CS-1580 | Fireproofing - LER Building Train C | 30 | 2021-06-03 | 2021-12-03 | m2/м2 | 43.57% | 360.3 | m2/м2
CN-GCC-CS-1630 | Building Finishing - LER Train C | 50 | 2021-11-24 | 2022-01-12 | компл. | 0% | 1 | компл.
Mechanical |  | 45 | 2021-11-19 | 2022-01-02 |  | 0%
CN-GCC-HV-1020 | Building HVAC - LER Train C | 45 | 2021-11-19 | 2022-01-02 | компл. | 0% | 1 | компл.
Electrical |  | 215 | 2021-10-23 | 2022-05-25 |  | 0%
CN-GCC-EL-1420 | Electrical Cable Trays - LER Building Train C | 50 | 2021-10-23 | 2021-12-11 | m/м | 0% | 419 | m/м
CN-GCC-EL-1340 | Building Electrical - LER Train C | 140 | 2021-11-17 | 2022-04-05 | m/м | 0% | 61469 | m/м
CN-GCC-EL-1350 | Building Electrical (terminations) - LER Building Train C | 90 | 2022-01-21 | 2022-04-20 | ea/шт | 0% | 1740 | ea/шт
CN-GCC-EL-1320 | Electrical Junction Boxes - LER Building Train C | 60 | 2022-01-26 | 2022-03-26 | ea/шт | 0% | 11 | ea/шт
CN-GCC-EL-1400 | Electrical Equipment Installation - LER Building Train C | 75 | 2022-01-26 | 2022-04-10 | kg/кг | 0% | 52 | kg/кг
CN-GCC-EL-1360 | Earthing & Lightening - LER Building Train C | 45 | 2022-03-02 | 2022-04-15 | ea/шт | 0% | 129 | ea/шт
CN-GCC-EL-1410 | Heat Tracing - LER Building Train C | 35 | 2022-04-01 | 2022-05-05 | m/м | 0% | 80 | m/м
CN-GCC-EL-1380 | Lighting - LER Building Train C | 45 | 2022-04-11 | 2022-05-25 | ea/шт | 0% | 28 | ea/шт
Instrumentation |  | 85 | 2021-12-27 | 2022-03-21 |  | 0%
CN-GCC-IN-1360 | Instrument Cable Trays - LER Building Train C | 30 | 2021-12-27 | 2022-01-25 | m/м | 0% | 175 | m/м
CN-GCC-IN-1280 | Building Instrumentation - LER Train C | 30 | 2022-01-16 | 2022-02-14 | m/м | 0% | 2761 | m/м
CN-GCC-IN-1290 | Field Instrument - LER Building Train C | 15 | 2022-02-15 | 2022-03-01 | ea/шт | 0% | 36 | ea/шт
CN-GCC-IN-1310 | Building Instrumentation (Terminations) - LER Building Train C | 15 | 2022-02-20 | 2022-03-06 | ea/шт | 0% | 36 | ea/шт
CN-GCC-IN-1320 | F&G - LER Building Train C | 15 | 2022-03-07 | 2022-03-21 | ea/шт | 0% | 35 | ea/шт
Telecom |  | 7 | 2022-04-29 | 2022-05-05 |  | 0%
CN-GCC-TL-1010 | Telecom Equipment / Trays / JBs / Terminations - LER Building Train C | 7 | 2022-04-29 | 2022-05-05 | m/м | 0% | 510 | m/м
HSE |  | 50 | 2022-04-06 | 2022-05-25 |  | 0%
CN-GCC-HS-1011 | HSE Installation - LER Building Train C | 50 | 2022-04-06 | 2022-05-25 | ea/шт | 0% | 41 | ea/шт
COMPRESSORPIPERACK/AIRCOOLER/CABLERACK |  | 934 | 2019-10-20 | 2022-05-31 |  | 29.08%
AIRCOOLER/CABLERACK |  | 789 | 2020-03-31 | 2022-05-31 |  | 19.95%
Civil/Structural |  | 464 | 2020-03-31 | 2021-07-24 |  | 81.1%
CN-GCC-CS-1390-1 | Lean Concrete - NS-PR 37 E & F | 7 | 2020-03-31 | 2021-06-04 | m3/м3 | 80% | 8 | m3/м3
CN-GCC-CS-1330-1 | Lean Concrete - Air Cooler Train C | 7 | 2020-04-05 | 2020-07-27 | m3/м3 | 100% | 22 | m3/м3
CN-GCC-CS-1390 | Foundation - NS-PR 37 E & F | 32 | 2020-04-12 | 2021-04-24 | m3/м3 | 100% | 160.89 | m3/м3
CN-GCC-CS-1330 | Foundation - Air Cooler Train C | 75 | 2020-08-11 | 2021-06-06 | m3/м3 | 99% | 327 | m3/м3
CN-GCC-CS-1151 | Structural Steel - Cable Rack Train C | 30 | 2020-12-22 | 2021-06-17 | tons/тн | 83% | 33 | tons/тн
CN-GCC-CS-1131 | Structural Steel - NS-PR 37 E & F | 45 | 2021-05-20 | 2021-07-24 | tons/тн | 50.25% | 139 | tons/тн
Mechanical |  | 360 | 2021-03-25 | 2022-03-20 |  | 17.53%
CN-GCC-MS-1061 | Pre-Assembly and Installation of Structure - Air Coolers Train C | 80 | 2021-03-25 | 2021-06-24 | tons/тн | 48.8% | 200 | tons/тн
CN-GCC-MS-1040 | Erection of Bundles (Incl. bolt tightning) - Assembly of Air Coolers Train C | 120 | 2021-06-12 | 2021-10-09 | tons/тн | 0% | 490 | tons/тн
CN-GCC-MS-1051 | Insulation - Air Coolers Train C | 10 | 2022-03-11 | 2022-03-20 | m2/м2 | 0% | 72 | m2/м2
Piping |  | 522 | 2020-04-30 | 2022-04-29 |  | 8.16%
CN-GCC-PI-1101 | Pipe Supports - Prefabrication Air Coolers / Cable Rack Train C | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 8 | tons/тн
CN-GCC-PI-1020 | Piping Erection Main Header - Air Coolers Train C | 180 | 2021-03-18 | 2022-02-17 | DI | 6.8% | 8 | tons/тн
CN-GCC-PI-1060 | Piping Testing (RT, PWHT) - Air Coolers Train C | 180 | 2021-04-23 | 2022-02-27 | Стык/Jo | 0.55% | 4901 | DI
CN-GCC-PI-1102 | Pipe Supports - Installation Air Coolers / Cable Rack Train C | 180 | 2021-04-23 | 2022-02-09 | tons/тн | 3% | 1082 | Стык/Jo
CN-GCC-PI-1130 | Piping Testing (Hydrotests) - Air Coolers Train C | 39 | 2022-02-19 | 2022-03-29 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCC-PI-1103 | Piping Painting - Piperack / Air Coolers / Cable Rack Train C | 45 | 2022-02-24 | 2022-04-09 | m2/м2 | 0% | 543 | m2/м2
CN-GCC-PI-1100 | Piping Insulation - Air Coolers Train C (process) | 50 | 2022-03-11 | 2022-04-29 | m/м | 0% | 2014 | m/м
Electrical |  | 136 | 2021-04-25 | 2022-05-19 |  | 2.82%
CN-GCC-EL-1060 | Electrical Cable Trays - Cable Rack Train C | 25 | 2021-04-25 | 2022-01-30 | m/м | 25% | 563 | m/м
CN-GCC-EL-1550 | Electrical Cable Trays - Air Cooler Train C | 10 | 2022-01-04 | 2022-01-13 | m/м | 0% | 750 | m/м
CN-GCC-EL-1290 | Electrical Cable Pulling - Cable Rack Train C | 26 | 2022-01-31 | 2022-02-25 | m/м | 0% | 1250 | m/м
CN-GCC-EL-1560 | Electrical Cable Pulling - Air Cooler Train C | 26 | 2022-02-03 | 2022-02-28 | m/м | 0% | 1250 | m/м
CN-GCC-EL-1112 | Electrical Junction Boxes - Cable Rack Train C | 26 | 2022-02-20 | 2022-03-17 | ea/шт | 0% | 48 | ea/шт
CN-GCC-EL-1580 | Electrical Junction Boxes - Air Coolers Train C | 26 | 2022-02-23 | 2022-03-20 | ea/шт | 0% | 3 | ea/шт
CN-GCC-EL-1570 | Earthning And Lightning - Air Cooler Train C | 15 | 2022-03-01 | 2022-03-15 | ea/шт | 0% | 370 | ea/шт
CN-GCC-EL-1111 | Lighting - Cable Rack Train C | 34 | 2022-03-19 | 2022-04-21 | ea/шт | 0% | 2 | ea/шт
CN-GCC-EL-1110 | Electrical Cable Terminations - Cable Rack Train C | 10 | 2022-03-28 | 2022-04-06 | ea/шт | 0% | 75 | компл.
CN-GCC-EL-1100 | Electrical Cable Terminations - Air Coolers Train C | 15 | 2022-03-31 | 2022-04-14 | компл. | 0% | 75 | ea/шт
CN-GCC-EL-1270 | Heat Tracing - Air Cooler Train C (process) | 15 | 2022-04-10 | 2022-04-24 | m/м | 0% | 458 | m/м
CN-GCC-EL-1540 | Heat Tracing - Cable Rack Train C (process) | 15 | 2022-04-20 | 2022-05-04 | m/м | 0% | 100 | m/м
CN-GCC-EL-1590 | Lighting - Air Coolers Train C | 15 | 2022-05-05 | 2022-05-19 | ea/шт | 0% | 135 | ea/шт
Instrumentation |  | 112 | 2021-04-29 | 2022-05-22 |  | 0.36%
CN-GCC-IN-1060 | Instrument Cable Trays - Cable Rack Train C | 10 | 2021-04-29 | 2022-02-26 | m/м | 18% | 35 | m/м
CN-GCC-IN-1050 | Instrument Cable Trays - Air Cooler Train C | 15 | 2022-01-31 | 2022-02-14 | m/м | 0% | 125 | m/м
CN-GCC-IN-1460 | Instrument Cable Pulling - Air Cooler Train C | 43 | 2022-02-20 | 2022-04-03 | m/м | 0% | 16000 | m/м
CN-GCC-IN-1470 | Instrument Cable Pulling - Cable Rack Train C | 52 | 2022-03-04 | 2022-04-24 | m/м | 0% | 6000 | m/м
CN-GCC-IN-1122 | Instrument Junction Boxes - Air Cooler Train C | 26 | 2022-03-12 | 2022-04-06 | ea/шт | 0% | 11 | ea/шт
CN-GCC-IN-1130 | Field Instrument - Air Cooler Train C | 34 | 2022-03-21 | 2022-04-23 | ea/шт | 0% | 11 | ea/шт
CN-GCC-IN-1480 | Instrument Junction Boxes - Cable Rack Train C | 7 | 2022-03-24 | 2022-03-30 | ea/шт | 0% | 11 | ea/шт
CN-GCC-IN-1070 | Field Instrument - Cable Rack Train C | 15 | 2022-03-30 | 2022-04-13 | ea/шт | 0% | 13 | ea/шт
CN-GCC-IN-1490 | Instrument Cable Terminations - Air Cooler Train C | 30 | 2022-03-30 | 2022-04-28 | ea/шт | 0% | 325 | ea/шт
CN-GCC-IN-1500 | Instrument Cable Terminations - Cable Rack Train C | 14 | 2022-04-16 | 2022-04-29 | ea/шт | 0% | 75 | ea/шт
CN-GCC-IN-1123 | Fire & Gas (F&G) Detectors - Cable Rack Train C | 15 | 2022-05-01 | 2022-05-15 | ea/шт | 0% | 4 | ea/шт
CN-GCC-IN-1121 | Instrument Testing - Air Cooler Train C | 7 | 2022-05-16 | 2022-05-22 | ea/шт | 0% | 18 | ea/шт
Telecom |  | 8 | 2022-05-24 | 2022-05-31 |  | 0%
CN-GCA-TL-1120 | Telecom Equipment - Air Cooler / Cable Rack Train C | 8 | 2022-05-24 | 2022-05-31 | ea/шт | 0% | 20 | ea/шт
HSE |  | 10 | 2022-05-22 | 2022-05-31 |  | 0%
CN-GCC-HS-1000 | HSE Installation - Air Coolers / Cable Rack Train C | 10 | 2022-05-22 | 2022-05-31 | ea/шт | 0% | 9 | ea/шт
PIPERACK(EW-PR28&EW-PR29) |  | 793 | 2019-10-20 | 2022-01-10 |  | 49.51%
Civil/Structural |  | 748 | 2019-10-20 | 2021-11-26 |  | 79.59%
CN-GCC-CS-1390-11 | Lean Concrete - EW-PR 28 Train C | 7 | 2019-10-20 | 2019-11-07 | m3/м3 | 100% | 8 | m3/м3
CN-GCC-CS-1670 | Foundation - Module EW-PR 28 Train C | 153 | 2019-11-06 | 2020-10-27 | m3/м3 | 100% | 230 | m3/м3
CN-GCC-CS-1330-11 | Lean Concrete - EW-PR 29 Train C | 7 | 2019-11-12 | 2019-12-15 | m3/м3 | 100% | 8 | m3/м3
CN-GCC-CS-1640 | Foundation - Module EW-PR 29 Train C | 149 | 2019-11-15 | 2020-07-26 | m3/м3 | 100% | 155 | m3/м3
CN-GCC-CS-1700 | Structural Steel - Module EW-PR 29 Train C | 59 | 2020-03-30 | 2021-04-29 | tons/тн | 100% | 188 | tons/тн
CN-GCC-CS-1710 | Structural Steel - Module EW-PR 28 Train C | 30 | 2020-04-13 | 2021-06-04 | tons/тн | 98.22% | 119 | tons/тн
CN-GCB-CS-1800 | Side Cladding - Piperack Train C | 20 | 2021-08-06 | 2021-08-25 | m2/м2 | 0% | 125 | m2/м2
CN-GCC-CS-1720 | Fireproofing - Piperack Train C | 45 | 2021-10-13 | 2021-11-26 | m2/м2 | 0% | 339.17 | m2/м2
Piping |  | 556 | 2020-04-30 | 2021-12-16 |  | 37.41%
CN-GCC-PI-1230 | Pipe Supports - Prefabrication Piperack Train C | 39 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 6 | tons/тн
CN-GCC-PI-1170 | Piping Erection - Compressor Rack EW-PR 28 | 60 | 2020-08-26 | 2021-06-29 | DI | 54.5% | 618 | DI
CN-GCC-PI-1180 | Piping Erection - Compressor Rack EW-PR 29 | 60 | 2020-08-27 | 2021-07-04 | DI | 55.5% | 1719 | DI
CN-GCC-PI-1190 | Piping Testing (RT, PWHT) - Piperack Train C | 60 | 2020-09-16 | 2021-07-14 | Стык/Jo | 31.03% | 593 | Стык/Jo
CN-GCC-PI-1240 | Pipe Supports - Installation Piperack Train C | 80 | 2021-01-22 | 2021-06-28 | tons/тн | 59% | 6 | tons/тн
CN-GCC-PI-1270 | Piping Testing (Hydrotests) - Compressor Rack EW-PR 28 | 39 | 2021-08-14 | 2021-09-21 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCC-PI-1280 | Piping Testing (Hydrotests) - Compressor Rack EW-PR 29 | 39 | 2021-09-03 | 2021-10-11 | Стык/Jo | 0% | 1 | Стык/Jo
CN-GCC-PI-1250 | Piping Painting - Piperack Train C | 45 | 2021-09-12 | 2021-10-26 | m2/м2 | 0% | 415 | m2/м2
CN-GCC-PI-1210 | Piping Insulation - Piperack Train C | 45 | 2021-11-02 | 2021-12-16 | m/м | 0% | 1581 | m/м
Electrical |  | 302 | 2021-01-18 | 2021-11-26 |  | 8.86%
CN-GCC-EL-1430 | Electrical Cable Trays - Piperack Train C | 100 | 2021-01-18 | 2021-07-19 | m/м | 46% | 956 | m/м
CN-GCC-EL-1460 | Electrical Cable Pulling - Piperack Train C | 34 | 2021-09-11 | 2021-10-14 | m/м | 0% | 2500 | m/м
CN-GCC-EL-1520 | Electrical Junction Boxes - Piperack Train C | 26 | 2021-10-01 | 2021-10-26 | ea/шт | 0% | 81 | ea/шт
CN-GCC-EL-1480 | Electrical Cable Terminations - Piperack Train C | 34 | 2021-10-13 | 2021-11-15 | ea/шт | 0% | 140 | ea/шт
CN-GCC-EL-1530 | Lighting - Piperack Train C | 15 | 2021-10-27 | 2021-11-10 | ea/шт | 0% | 23 | ea/шт
CN-GCC-EL-1450 | Heat Tracing - Piperack Train C | 30 | 2021-10-28 | 2021-11-26 | m/м | 0% | 3536 | m/м
Instrumentation |  | 322 | 2021-01-21 | 2021-12-17 |  | 7.7%
CN-GCC-IN-1370 | Instrument Cable Trays - Piperack Train C | 35 | 2021-01-21 | 2021-04-10 | m/м | 100% | 210 | m/м
CN-GCC-IN-1510 | Instrument Cable Pulling - Piperack Train C | 51 | 2021-09-08 | 2021-10-28 | m/м | 0% | 5255 | m/м
CN-GCC-IN-1440 | Instrument Junction Boxes - Piperack Train C | 15 | 2021-09-28 | 2021-10-12 | ea/шт | 0% | 9 | ea/шт
CN-GCC-IN-1400 | Field Instrument - Piperack Train C | 26 | 2021-10-18 | 2021-11-12 | ea/шт | 0% | 4 | ea/шт
CN-GCC-IN-1450 | Fire & Gas (F&G) Detectors - Piperack Train C | 15 | 2021-11-18 | 2021-12-02 | ea/шт | 0% | 6 | ea/шт
CN-GCC-IN-1430 | Instrument Testing - Piperack Train C | 15 | 2021-12-03 | 2021-12-17 | ea/шт | 0% | 23 | ea/шт
Telecom |  | 5 | 2021-12-18 | 2021-12-22 |  | 0%
CN-GCA-TL-1130 | Telecom Equipment - Piperack Train C | 5 | 2021-12-18 | 2021-12-22 | компл. | 0% | 6 | компл.
HSE |  | 9 | 2022-01-02 | 2022-01-10 |  | 0%
CN-GCC-HS-1021 | HSE Installation - Piperack Train C | 9 | 2022-01-02 | 2022-01-10 | ea/шт | 0% | 1 | ea/шт
TRANSFORMERSUBSTATION(B-911) |  | 724 | 2020-02-12 | 2022-02-20 |  | 20.71%
Civil/Structural |  | 694 | 2020-02-12 | 2022-01-21 |  | 86.6%
CN-TS1-CS-1010-1 | Lean Concrete - Transformer Substation (B-911) | 12 | 2020-02-12 | 2020-02-21 | m3/м3 | 100% | 10 | m3/м3
CN-TS1-CS-1010 | Foundation - Transformer Substation (B-911) | 58 | 2020-02-23 | 2020-05-15 | m3/м3 | 100% | 226.88 | m3/м3
CN-TS1-CS-1030 | Building Structural Steel Erection - Transformer Substation (B-911) | 73 | 2020-05-07 | 2021-06-04 | tons/тн | 99.4% | 324 | tons/тн
CN-TS1-CS-1050 | Building Cladding - Transformer Substation (B-911) | 45 | 2020-08-29 | 2020-10-09 | m2/м2 | 100% | 1518 | m2/м2
CN-TS1-CS-1060 | Building Internal Works - Transformer Substation (B-911) | 190 | 2020-11-23 | 2021-07-14 | компл. | 65% | 1 | компл.
CN-TS1-CS-1040 | Fireproofing - Transformer Substation (B-911) | 45 | 2021-04-10 | 2021-08-23 | m2/м2 | 65.36% | 829.14 | m2/м2
CN-TS1-CS-1020 | Building Finishing - Transformer Substation (B-911) | 100 | 2021-10-14 | 2022-01-21 | компл. | 0% | 1 | компл.
Mechanical |  | 90 | 2021-05-23 | 2022-01-06 |  | 9%
CN-TS1-HV-1000 | Building HVAC - Transformer Substation (B-911) | 90 | 2021-05-23 | 2022-01-06 | компл. | 9% | 1 | компл.
Electrical |  | 285 | 2021-04-18 | 2022-01-25 |  | 1.91%
CN-TS1-EL-2000 | Electrical Cable Trays - Transformer Substation (B-911) | 90 | 2021-04-18 | 2021-07-15 | m/м | 49% | 3172 | m/м
CN-TS1-EL-2010 | Electrical Cable Pulling - Transformer Substation (B-911) | 180 | 2021-06-04 | 2021-11-30 | m/м | 0% | 117814 | m/м
CN-TS1-EL-1000 | Building Switchboards, Transformers and Other Electrical Equipment Erection - Transformer Substation (B-911) | 75 | 2021-07-05 | 2021-09-17 | tons/тн | 0% | 113 | tons/тн
CN-TS1-EL-1010 | Building Electrical Cables Work - Transformer Substation (B-911) | 75 | 2021-08-14 | 2021-10-27 | m/м | 0% | 10410 | m/м
CN-TS1-EL-1002 | Electrical Junction Boxes - Transformer Substation (B-911) | 22 | 2021-09-13 | 2021-10-04 | ea/шт | 0% | 18 | ea/шт
CN-TS1-EL-2030 | Electrical Cable Terminations- Transformer Substation (B-911) | 83 | 2021-09-16 | 2021-12-07 | ea/шт | 0% | 2708 | ea/шт
CN-TS1-EL-1020 | Building Electrical Terminations - Transformer Substation (B-911) | 22 | 2021-10-16 | 2021-11-06 | ea/шт | 0% | 478 | ea/шт
CN-TS1-EL-1001 | Lightning Fixtures - Transformer Substation (B-911) | 22 | 2021-11-23 | 2021-12-14 | ea/шт | 0% | 79 | ea/шт
CN-TS1-EL-1003 | Earthning And Lightning - Transformer Substation (B-911) | 30 | 2021-11-23 | 2021-12-22 | ea/шт | 0% | 354 | ea/шт
CN-TS1-EL-1004 | Heat tracing - Transformer Substation (B-911) | 25 | 2021-12-23 | 2022-01-16 | m/м | 0% | 250 | m/м
CN-TS1-EL-2020 | Electrical Heat Tracing - Transformer Substation (B-911) | 15 | 2022-01-11 | 2022-01-25 | m/м | 0% | 250 | m/м
Instrumetation |  | 229 | 2021-03-25 | 2021-12-02 |  | 33.47%
CN-TS1-IN-2010 | Instrument Cable Pulling - Transformer Substation (B-911) | 130 | 2021-03-25 | 2021-10-03 | m/м | 40% | 550 | m/м
CN-TS1-IN-2000 | Instrument Cable Trays - Transformer Substation (B-911) | 30 | 2021-04-18 | 2021-06-14 | m/м | 36% | 31006 | m/м
CN-TS1-IN-1000 | Building Instrumentation Equipment Erection - Transformer Substation (B-911) | 10 | 2021-09-18 | 2021-09-27 | ea/шт | 0% | 2 | ea/шт
CN-TS1-IN-1012 | Other Instruments - Transformer Substation (B-911) | 15 | 2021-09-23 | 2021-10-07 | ea/шт | 0% | 81 | ea/шт
CN-TS1-IN-1013 | Instrument Junction Boxes - Transformer Substaion (B-911) | 10 | 2021-09-28 | 2021-10-07 | ea/шт | 0% | 19 | ea/шт
CN-TS1-IN-1020 | Building Instrumentation Terminations - Transformer Substation (B-911) | 20 | 2021-10-29 | 2021-11-17 | ea/шт | 0% | 129 | ea/шт
CN-TS1-IN-1011 | Fire & Gas (F&G) Detectors - Transformer Substation (B-911) | 15 | 2021-11-18 | 2021-12-02 | ea/шт | 0% | 56 | ea/шт
Telecom |  | 11 | 2021-12-10 | 2021-12-20 |  | 0%
CN-TS1-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Transformer Substation (B-911) | 11 | 2021-12-10 | 2021-12-20 | m/м | 0% | 579 | m/м
HSE |  | 30 | 2022-01-22 | 2022-02-20 |  | 0%
CN-TS1-HS-1000 | HSE Installation - Transformer Substation (B-911) | 30 | 2022-01-22 | 2022-02-20 | ea/шт | 0% | 46 | ea/шт
TRANSFORMERSUBSTATION(B-912) |  | 832 | 2020-02-07 | 2022-06-08 |  | 17.95%
Civil/Structural |  | 814 | 2020-02-07 | 2022-05-21 |  | 76.19%
CN-TS2-CS-1010-1 | Lean Concrete - Transformer Substation (B-912) | 12 | 2020-02-07 | 2020-02-16 | m3/м3 | 100% | 9 | m3/м3
CN-TS2-CS-1010 | Foundation - Transformer Substation (B-912) | 67 | 2020-02-15 | 2020-08-29 | m3/м3 | 100% | 204.06 | m3/м3
CN-TS2-CS-1030 | Building Structural Steel Erection - Transformer Substation (B-912) | 83 | 2020-09-04 | 2021-06-11 | tons/тн | 99% | 268 | tons/тн
CN-TS2-CS-1050 | Building Cladding - Transformer Substation (B-912) | 60 | 2020-10-25 | 2020-11-25 | m2/м2 | 100% | 1518 | m2/м2
CN-TS2-CS-1060 | Building Internal Works - Transformer Substation (B-912) | 170 | 2021-01-05 | 2021-09-22 | компл. | 65% | 1 | компл.
CN-TS2-CS-1040 | Fireproofing - Transformer Substation (B-912) | 45 | 2021-12-09 | 2022-01-22 | m2/м2 | 0% | 745.35 | m2/м2
CN-TS2-CS-1020 | Building Finishing - Transformer Substation (B-912) | 100 | 2022-02-11 | 2022-05-21 | компл. | 0% | 1 | компл.
Mechanical |  | 85 | 2022-02-21 | 2022-05-16 |  | 0%
CN-TS2-HV-1000 | Building HVAC - Transformer Substation (B-912) | 85 | 2022-02-21 | 2022-05-16 | компл. | 0% | 1 | компл.
Electrical |  | 263 | 2021-04-26 | 2022-02-19 |  | 1.06%
CN-TS2-EL-2000 | Electrical Cable Trays - Transformer Substation (B-912) | 62 | 2021-04-26 | 2021-08-16 | m/м | 25% | 2363 | m/м
CN-TS2-EL-2010 | Electrical Cable Pulling - Transformer Substation (B-912) | 150 | 2021-06-27 | 2021-11-23 | m/м | 0% | 146555 | m/м
CN-TS2-EL-1000 | Building Switchboards, Transformers and Other Electrical Equipment Erection - Transformer Substation (B-912) | 75 | 2021-09-01 | 2021-11-14 | tons/тн | 0% | 74 | tons/тн
CN-TS2-EL-2030 | Electrical Cable Terminations- Transformer Substation (B-912) | 70 | 2021-10-25 | 2022-01-02 | ea/шт | 0% | 4140 | ea/шт
CN-TS2-EL-1010 | Building Electrical Cables Work - Transformer Substation (B-912) | 50 | 2021-11-04 | 2021-12-23 | m/м | 0% | 15390 | m/м
CN-TS2-EL-2013 | Earthing And Lighing - Transformer Substation (B-912) | 30 | 2021-12-04 | 2022-01-02 | ea/шт | 0% | 298 | ea/шт
CN-TS2-EL-2012 | Electrical Junction Boxes - Transformer Substation (B-912) | 22 | 2021-12-07 | 2021-12-28 | ea/шт | 0% | 17 | ea/шт
CN-TS2-EL-1020 | Building Electrical Terminations - Transformer Substation (B-912) | 34 | 2021-12-15 | 2022-01-17 | ea/шт | 0% | 620 | ea/шт
CN-TS2-EL-2011 | Lightning fixtures - Transformer substation (B-912) | 23 | 2021-12-16 | 2022-01-07 | ea/шт | 0% | 64 | ea/шт
CN-TS2-EL-2020 | Electrical Heat Tracing - Transformer Substation (B-912) | 25 | 2022-01-26 | 2022-02-19 | m/м | 0% | 250 | m/м
Instrumetation |  | 202 | 2021-04-28 | 2022-03-02 |  | 0.97%
CN-TS2-IN-2000 | Instrument Cable Trays - Transformer Substation (B-912) | 30 | 2021-04-28 | 2021-09-25 | m/м | 30% | 356 | m/м
CN-TS2-IN-2010 | Instrument Cable Pulling - Transformer Substation (B-912) | 130 | 2021-09-07 | 2022-01-14 | m/м | 0% | 36360 | m/м
CN-TS2-IN-1010 | Building Instrument Cable Works - Transformer Substation (B-912) | 34 | 2021-12-24 | 2022-01-26 | m/м | 0% | 3286 | m/м
CN-TS2-IN-1000 | Building Instrumentation Equipment Erection - Transformer Substation (B-912) | 12 | 2022-01-13 | 2022-01-24 | ea/шт | 0% | 114 | ea/шт
CN-TS2-IN-1012 | Instrument Junction Boxes - Transformer Substaion (B-912) | 10 | 2022-01-25 | 2022-02-03 | ea/шт | 0% | 23 | ea/шт
CN-TS2-IN-1020 | Building Instrumentation Terminations - Transformer Substation (B-912) | 12 | 2022-01-30 | 2022-02-10 | ea/шт | 0% | 128 | ea/шт
CN-TS2-IN-1011 | Fire & Gas (F&G) Detectors - Transformer Substation (B-912) | 6 | 2022-02-25 | 2022-03-02 | ea/шт | 0% | 58 | ea/шт
Telecom |  | 8 | 2022-03-03 | 2022-03-10 |  | 0%
CN-TS2-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Transformer Substation (B-912) | 8 | 2022-03-03 | 2022-03-10 | m/м | 0% | 427 | m/м
HSE |  | 18 | 2022-05-22 | 2022-06-08 |  | 0%
CN-TS2-HS-1000 | HSE Installation - Transformer Substation (B-912) | 18 | 2022-05-22 | 2022-06-08 | ea/шт | 0% | 49 | ea/шт
HPFLARE&CLOSEDDRAINAREA-AREA55 |  | 754 | 2020-01-13 | 2022-03-26 |  | 45.95%
Civil/Structural |  | 671 | 2020-01-13 | 2022-01-02 |  | 77.78%
CN-HPF-CS-1120-1 | Lean Concrete - HP FLARE STACK A-62901 | 5 | 2020-01-13 | 2020-10-10 | m3/м3 | 100% | 5 | m3/м3
CN-HPF-CS-1160-1 | Lean Concrete - Pipe rack near Flare KOD area (EW-PR21 / EW-PR22) | 5 | 2020-01-29 | 2020-06-24 | m3/м3 | 100% | 6 | m3/м3
CN-HPF-CS-1160 | Foundation - Pipe rack near Flare KOD area (EW-PR21 / EW-PR22 & GMP 11,30,31) ) | 66 | 2020-02-02 | 2021-06-11 | m3/м3 | 97.1% | 332.88 | m3/м3
CN-HPF-CS-1120 | Foundation - HP FLARE STACK A-62901 | 89 | 2020-02-11 | 2020-10-11 | m3/м3 | 100% | 269 | m3/м3
CN-HPF-CS-1210 | Backfilling - HP Flare Area | 120 | 2020-09-22 | 2020-12-11 | m3/м3 | 100% | 3817 | m3/м3
CN-HPF-CS-1180-1 | Lean Concrete - HP FLARE KNOCK-OUT DRUM PUMP AND SHELTER | 5 | 2020-12-15 | 2021-03-11 | m3/м3 | 100% | 4 | m3/м3
CN-HPF-CS-1180 | Foundation - HP FLARE KNOCK-OUT DRUM PUMP AND SHELTER | 25 | 2020-12-20 | 2021-06-04 | m3/м3 | 79.23% | 59.2 | m3/м3
CN-HPF-CS-1091 | Structural Steel Flare - Supports & EW-PR22 | 30 | 2021-02-25 | 2021-05-14 | tons/тн | 100% | 29 | tons/тн
CN-HPF-CS-1092 | Structural Steel Flare - Supports & EW-PR21 | 30 | 2021-03-06 | 2021-06-05 | tons/тн | 98.25% | 31 | tons/тн
CN-HPF-CS-1114 | Structural Steel (Primary) - Shelter Building | 30 | 2021-03-13 | 2021-06-10 | tons/тн | 99% | 25 | tons/тн
CN-HPF-CS-1050 | Piping Supports - HP Flare Area | 34 | 2021-03-16 | 2021-06-17 | tons/тн | 99% | 31 | tons/тн
CN-HPF-CS-1090 | Structural Steel GMP / Crossovers - Flare KOD | 30 | 2021-03-31 | 2021-06-05 | tons/тн | 98% | 60 | tons/тн
CN-HPF-CS-1130 | Foundation - Misc. foundations | 5 | 2021-06-05 | 2021-06-09 | ea/шт | 0% | 3 | ea/шт
CN-HPF-CS-1100 | Misc Structural Steel - HP Flare Area | 5 | 2021-06-09 | 2021-06-13 | m/м | 0% | 1 | tons/тн
CN-HPF-CS-1060 | E/I Supports - HP Flare Area | 5 | 2021-06-11 | 2021-06-15 | tons/тн | 0% | 183 | m2/м2
CN-HPF-CS-1111 | Building Cladding - Shelter | 25 | 2021-06-11 | 2021-07-05 | m2/м2 | 0% | 148 | m/м
CN-HPF-CS-1112 | Building Internal Works - Shelter Building | 50 | 2021-06-11 | 2021-07-30 | компл. | 0% | 1 | компл.
CN-HPF-CS-1113 | Building Finishing Works - Shelter Building | 50 | 2021-07-31 | 2021-09-18 | компл. | 0% | 1 | компл.
CN-HPF-CS-1110 | Fireproofing - HP Flare Area | 37 | 2021-11-27 | 2022-01-02 | m2/м2 | 0% | 302.83 | m2/м2
Mechanical |  | 231 | 2020-10-12 | 2021-06-17 |  | 85.35%
CN-HPF-MS-1020 | Erection - Flare Stack (Including ground assembly) | 77 | 2020-10-12 | 2021-05-12 | tons/тн | 100% | 57 | tons/тн
CN-HPF-MR-1011 | Insulation - Flare Stack | 60 | 2021-03-13 | 2021-06-08 | m2/м2 | 79.3% | 967 | m2/м2
CN-HPF-MR-1000 | Erection - Flare KOD Pumps | 7 | 2021-06-11 | 2021-06-17 | tons/тн | 0% | 4 | tons/тн
Piping |  | 404 | 2020-04-30 | 2021-12-16 |  | 30.62%
CN-HPF-EL-1161 | Pipe Supports - Prefabrication HP Flare Area | 5 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 5 | tons/тн
CN-HPF-PI-1010 | Piping Erection - HP Flare | 45 | 2021-04-24 | 2021-08-04 | DI | 51.58% | 5 | tons/тн
CN-HPF-EL-1162 | Pipe Supports - Installation HP Flare Area | 45 | 2021-04-24 | 2021-07-25 | tons/тн | 40% | 1085 | DI
CN-HPF-PI-1030 | Piping Testing (RT, PWHT) - HP Flare | 30 | 2021-04-25 | 2021-08-09 | Стык/Jo | 4.34% | 1198 | DI
CN-HPF-PI-1000 | Piping Erection - Flare KOD | 75 | 2021-05-04 | 2021-08-29 | DI | 58.84% | 673 | Стык/Jo
CN-HPF-PI-1020 | Piping Testing (RT, PWHT) - Flare KOD | 74 | 2021-05-10 | 2021-09-13 | Стык/Jo | 3.12% | 369 | Стык/Jo
CN-HPF-PI-1080 | Piping Testing (Hydrotests) Flare KOD | 25 | 2021-08-27 | 2021-09-20 | Стык/Jo | 0% | 1 | Стык/Jo
CN-HPF-PI-1090 | Piping Testing (Hydrotests) HP Flare | 15 | 2021-09-06 | 2021-09-20 | Стык/Jo | 0% | 1 | Стык/Jo
CN-HPF-EL-1280 | Piping Painting - Flare KOD | 40 | 2021-09-11 | 2021-10-20 | m2/м2 | 0% | 268 | m2/м2
CN-HPF-EL-1163 | Piping Painting - HP Flare Area | 6 | 2021-10-15 | 2021-10-20 | m2/м2 | 0% | 207 | m2/м2
CN-HPF-PI-1050 | Piping Insulation - HP Flare | 10 | 2021-10-31 | 2021-11-09 | m/м | 0% | 1492 | m/м
CN-HPF-EL-1160 | Piping Insulation - Flare KOD | 37 | 2021-11-10 | 2021-12-16 | m/м | 0% | 1322 | m/м
Electrical |  | 119 | 2021-08-25 | 2021-12-21 |  | 0%
CN-HPF-EL-1020 | Electrical Cable Trays - HP Flare | 20 | 2021-08-25 | 2021-09-13 | m/м | 0% | 40 | m/м
CN-HPF-EL-1000 | Electrical Cable Trays - Flare KOD | 25 | 2021-09-14 | 2021-10-08 | m/м | 0% | 771 | m/м
CN-HPF-EL-1260 | Electrical Cable Pulling - HP Flare Area | 75 | 2021-09-14 | 2021-11-27 | m/м | 0% | 1250 | m/м
CN-HPF-EL-1270 | Electrical Cable Pulling - Flare KOD | 20 | 2021-10-04 | 2021-10-23 | m/м | 0% | 4350 | m/м
CN-HPF-PI-1070 | Heat Tracing - HP Flare | 17 | 2021-10-09 | 2021-10-25 | m/м | 0% | 2500 | m/м
CN-HPF-EL-1140 | Heat Tracing - Flare KOD | 30 | 2021-10-26 | 2021-11-24 | m/м | 0% | 9150 | m/м
CN-HPF-EL-1050 | Electrical Cable Terminations - Flare KOD | 15 | 2021-10-26 | 2021-11-09 | ea/шт | 0% | 300 | ea/шт
CN-HPF-EL-1010 | Electrical Junction Boxes - HP Flare Area | 23 | 2021-11-10 | 2021-12-02 | ea/шт | 0% | 97 | ea/шт
CN-HPF-EL-1060 | Electrical Cable Terminations - HP Flare | 40 | 2021-11-12 | 2021-12-21 | ea/шт | 0% | 70 | ea/шт
CN-HPF-EL-1040 | Lighting - HP Flare Area | 32 | 2021-11-20 | 2021-12-21 | ea/шт | 0% | 49 | ea/шт
Instrumetation |  | 184 | 2021-09-04 | 2022-03-06 |  | 0%
CN-HPF-IN-1020 | Instrument Cable Trays - HP Flare | 10 | 2021-09-04 | 2021-09-13 | m/м | 0% | 98 | m/м
CN-HPF-IN-1000 | Instrument Cable Trays - Flare KOD | 15 | 2021-10-09 | 2021-10-23 | m/м | 0% | 227 | m/м
CN-HPF-IN-1220 | Instrument Cable Pulling - HP Flare | 124 | 2021-10-19 | 2022-02-19 | m/м | 0% | 12272 | m/м
CN-HPF-IN-1050 | Field Instrument - HP Flare | 8 | 2021-11-20 | 2021-11-27 | ea/шт | 0% | 22 | ea/шт
CN-HPF-IN-1070 | Instrument Terminations - Flare KOD | 60 | 2022-01-06 | 2022-03-06 | ea/шт | 0% | 1000 | ea/шт
CN-HPF-IN-1040 | Field Instrument - Flare KOD | 28 | 2022-01-23 | 2022-02-19 | ea/шт | 0% | 25 | ea/шт
CN-HPF-IN-1030 | F&G - HP Flare Area | 18 | 2022-02-02 | 2022-02-19 | ea/шт | 0% | 35 | ea/шт
CN-HPF-IN-1010 | Instrument Junction Boxes - HP Flare Area | 5 | 2022-02-15 | 2022-02-19 | ea/шт | 0% | 20 | ea/шт
CN-HPF-IN-1060 | Instrument Terminations - HP Flare | 12 | 2022-02-23 | 2022-03-06 | ea/шт | 0% | 112 | ea/шт
CN-HPF-IN-1071 | Instrument Testing - Flare KOD | 10 | 2022-02-25 | 2022-03-06 | ea/шт | 0% | 3 | ea/шт
Telecom |  | 15 | 2022-03-07 | 2022-03-21 |  | 0%
CN-HPF-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - HP Flare Area | 15 | 2022-03-07 | 2022-03-21 | ea/шт | 0% | 46 | ea/шт
HSE |  | 13 | 2022-03-14 | 2022-03-26 |  | 0%
CN-HPF-HS-1000 | HSE Installation - HP Flare Area | 13 | 2022-03-14 | 2022-03-26 | ea/шт | 0% | 36 | ea/шт
UTILITIESFACILITIES-AREA56 |  | 911 | 2019-12-16 | 2022-07-17 |  | 49.89%
INSTRUMENTAIRANDNITROGEN |  | 737 | 2019-12-16 | 2022-01-24 |  | 54.43%
Civil/Structural |  | 550 | 2019-12-16 | 2021-07-21 |  | 83.03%
CN-INA-CS-1121-1 | Lean Concrete - Rack Module - Cable Rack PR 17,19,20,30,31 | 5 | 2019-12-16 | 2020-08-26 | m3/м3 | 100% | 8 | m3/м3
CN-INA-CS-1121 | Foundation - Rack Module - Cable Rack PR 17,19,20,30,31 | 25 | 2019-12-26 | 2020-10-22 | m3/м3 | 100% | 149 | m3/м3
CN-INA-CS-1122-1 | Lean Concrete - Instrument & Nitrogen Area | 7 | 2020-02-02 | 2020-10-18 | m3/м3 | 100% | 9 | m3/м3
CN-INA-CS-1122 | Foundation - Instrument & Nitrogen Area | 79 | 2020-06-19 | 2021-06-06 | m3/м3 | 96% | 360.66 | m3/м3
CN-INA-CS-1210 | Backfilling - Instrument Air & Nitrogen Area | 37 | 2020-07-01 | 2021-06-19 | m3/м3 | 94% | 10883 | m3/м3
CN-INA-CS-1191 | Structural Steel - Cable Rack PR 19,20,30,31 | 88 | 2020-07-09 | 2020-11-25 | tons/тн | 100% | 139 | tons/тн
CN-INA-CS-1090 | Structural Steel GMP / Crossovers - Instrument Air and Nitrogen | 30 | 2021-06-07 | 2021-07-06 | tons/тн | 0% | 42 | tons/тн
CN-INA-CS-1050 | Piping Supports - Instrument Air and Nitrogen Area | 14 | 2021-06-07 | 2021-06-20 | tons/тн | 0% | 14 | tons/тн
CN-INA-CS-1060 | E/I Supports - Instrument Air and Nitrogen Area | 36 | 2021-06-16 | 2021-07-21 | tons/тн | 0% | 1 | tons/тн
Mechanical |  | 431 | 2020-09-18 | 2021-11-29 |  | 71.37%
CN-INA-MS-1000 | Erection - Vessels / Shelter | 32 | 2020-09-18 | 2021-06-08 | tons/тн | 100% | 85 | tons/тн
CN-INA-MR-1010 | Erection - Instrument Air / Nitrogen Package | 30 | 2020-10-30 | 2021-06-13 | tons/тн | 100% | 80 | tons/тн
CN-INA-MS-1010 | Insulation - Vessels | 34 | 2021-10-27 | 2021-11-29 | m2/м2 | 0% | 441 | m2/м2
Piping |  | 368 | 2020-04-29 | 2021-11-19 |  | 25.14%
CN-INA-PI-1071 | Pipe Supports - Prefabrication Utilities | 3 | 2020-04-29 | 2021-01-22 | tons/тн | 100% | 2 | tons/тн
CN-INA-PI-1000 | Piping Erection - Instrument Air and Nitrogen | 30 | 2021-03-10 | 2021-09-10 | DI | 20.5% | 2 | tons/тн
CN-INA-PI-1030 | Piping Testing (RT, PWHT) - Instrument Air and Nitrogen | 14 | 2021-03-10 | 2021-09-13 | Стык/Jo | 4.31% | 293 | DI
CN-INA-PI-1010 | Piping Erection - Cable Rack Instrument Air and Nitrogen | 45 | 2021-03-15 | 2021-08-11 | DI | 52.5% | 144 | Стык/Jo
CN-INA-PI-1020 | Piping Testing (RT, PWHT) - Cable Rack | 14 | 2021-03-15 | 2021-08-14 | Стык/Jo | 16.67% | 625 | DI
CN-INA-PI-1072 | Pipe Supports - Installation Utilities | 5 | 2021-04-10 | 2021-06-11 | tons/тн | 35% | 464 | Стык/Jo
CN-INA-PI-1093 | Piping Testing (Hydrotests) Instrument Air and Nitrogen | 14 | 2021-09-23 | 2021-10-06 | Стык/Jo | 0% | 1 | Стык/Jo
CN-INA-PI-1083 | Piping Testing (Hydrotests) Cable Rack Instrument Air and Nitrogen | 14 | 2021-10-03 | 2021-10-16 | Стык/Jo | 0% | 1 | Стык/Jo
CN-INA-PI-1073 | Piping Painting - Utilities | 14 | 2021-10-06 | 2021-10-19 | m2/м2 | 0% | 136 | m2/м2
CN-INA-EL-1160 | Piping Insulation - Cable Rack | 14 | 2021-11-01 | 2021-11-14 | m/м | 0% | 486 | m/м
CN-INA-PI-1070 | Piping Insulation - Instrument Air and Nitrogen | 14 | 2021-11-06 | 2021-11-19 | m/м | 0% | 466 | m/м
Electrical |  | 358 | 2020-11-18 | 2021-11-19 |  | 21.51%
CN-INA-EL-1020 | Electrical Cable Trays - Instrument Air and Nitrogen Area - Cable Rack | 38 | 2020-11-18 | 2021-04-10 | m/м | 100% | 893 | m/м
CN-INA-EL-1280 | Electrical Cable Pulling - Instrument Air and Nitrogen Area - Cable Rack | 30 | 2021-06-05 | 2021-07-04 | m/м | 0% | 1500 | m/м
CN-INA-EL-1010 | Electrical Cable Trays - Instrument Air and Nitrogen | 14 | 2021-07-22 | 2021-08-04 | m/м | 0% | 106 | m/м
CN-INA-EL-1270 | Electrical Cable Pulling - Instrument Air and Nitrogen Area | 45 | 2021-08-05 | 2021-09-18 | m/м | 0% | 2100 | m/м
CN-INA-EL-1000 | Electrical Junction Boxes - Instrument Air and Nitrogen Area | 40 | 2021-08-20 | 2021-09-28 | ea/шт | 0% | 55 | ea/шт
CN-INA-EL-1060 | Electrical Cable Terminations - Instrument Air and Nitrogen | 40 | 2021-08-24 | 2021-10-02 | ea/шт | 0% | 75 | ea/шт
CN-INA-EL-1050 | Lighting - Instrument Air and Nitrogen Area | 49 | 2021-09-04 | 2021-10-22 | ea/шт | 0% | 40 | ea/шт
CN-INA-EL-1030 | Electrical Cable Terminations - Instrument Air and Nitrogen Cable Rack | 40 | 2021-09-07 | 2021-10-16 | ea/шт | 0% | 77 | ea/шт
CN-INA-EL-1140 | Heat Tracing - Cable Rack | 7 | 2021-10-25 | 2021-10-31 | m/м | 0% | 100 | m/м
CN-INA-PI-1050 | Heat Tracing - Instrument Air and Nitrogen | 7 | 2021-11-13 | 2021-11-19 | m/м | 0% | 1000 | m/м
Instrumetation |  | 372 | 2020-11-20 | 2021-12-03 |  | 23.59%
CN-INA-IN-1020 | Instrument Cable Trays - Instrument Air and Nitrogen Cable Rack | 40 | 2020-11-20 | 2021-04-10 | m/м | 100% | 908 | m/м
CN-INA-IN-1230 | Instrument Cable Pulling - Instrument Air and Nitrogen Area - Cable Rack | 30 | 2021-04-22 | 2021-07-04 | m/м | 95% | 2224 | m/м
CN-INA-IN-1010 | Instrument Cable Trays - Instrument Air and Nitrogen | 15 | 2021-08-05 | 2021-08-19 | m/м | 0% | 21 | m/м
CN-INA-IN-1220 | Instrument Cable Pulling - Instrument Air and Nitrogen Area | 60 | 2021-08-20 | 2021-10-18 | m/м | 0% | 17350 | m/м
CN-INA-IN-1050 | Field Instrument - Instrument Air and Nitrogen | 30 | 2021-09-22 | 2021-10-21 | ea/шт | 0% | 27 | ea/шт
CN-INA-IN-1030 | F&G - Instrument Air and Nitrogen Area | 21 | 2021-10-08 | 2021-10-28 | ea/шт | 0% | 10 | ea/шт
CN-INA-IN-1040 | Field Instrument - Cable Rack | 21 | 2021-10-11 | 2021-10-31 | ea/шт | 0% | 11 | ea/шт
CN-INA-IN-1000 | Instrument Junction Boxes - Instrument Air and Nitrogen Area | 21 | 2021-11-01 | 2021-11-21 | ea/шт | 0% | 9 | ea/шт
CN-INA-IN-1070 | Instrument Terminations - Instrument Air and Nitrogen | 21 | 2021-11-06 | 2021-11-26 | ea/шт | 0% | 257 | ea/шт
CN-INA-IN-1031 | Instrument Testing - Instrument Air and Nitrogen Area | 7 | 2021-11-27 | 2021-12-03 | ea/шт | 0% | 8 | ea/шт
Telecom |  | 30 | 2021-12-04 | 2022-01-02 |  | 0%
CN-INA-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Instrument Air and Nitrogen Area | 30 | 2021-12-04 | 2022-01-02 | ea/шт | 0% | 30 | ea/шт
HSE |  | 21 | 2022-01-04 | 2022-01-24 |  | 0%
CN-INA-HS-1000 | HSE Installation - Instrument Air and Nitrogen Area | 21 | 2022-01-04 | 2022-01-24 | ea/шт | 0% | 17 | ea/шт
EDGAREA |  | 637 | 2019-12-26 | 2022-02-11 |  | 66.08%
Civil/Structural |  | 374 | 2019-12-26 | 2021-06-09 |  | 91.63%
CN-EDG-CS-1150-1 | Lean Concrete- Rack Module - CR 08,09 & PR 32,33 | 3 | 2019-12-26 | 2020-06-22 | m3/м3 | 100% | 3.46 | m3/м3
CN-EDG-CS-1150 | Foundation - Rack Module - CR 08,09 & PR 32,33 | 10 | 2020-01-03 | 2020-08-28 | m3/м3 | 100% | 92 | m3/м3
CN-EDG-CS-1170 | Structural Steel EW-PR 32,33 | 45 | 2020-07-19 | 2020-10-28 | tons/тн | 100% | 103 | tons/тн
CN-EDG-CS-1160-1 | Lean Concrete - EMERGENCY DIESEL GENERATOR PACKAGE G-40901 | 6 | 2020-10-07 | 2020-12-06 | m3/м3 | 100% | 4 | m3/м3
CN-EDG-CS-1160 | Foundation - EMERGENCY DIESEL GENERATOR PACKAGE G-40901 | 35 | 2020-10-12 | 2021-05-07 | m3/м3 | 100% | 108.29 | m3/м3
CN-EDG-CS-1080 | Structural Steel EDG | 60 | 2021-03-03 | 2021-06-09 | tons/тн | 70.2% | 69 | tons/тн
Mechanical |  | 45 | 2021-05-25 | 2021-07-18 |  | 73.11%
CN-EDG-MR-1000 | Erection - EDG | 45 | 2021-05-25 | 2021-07-18 | tons/тн | 73.11% | 122 | tons/тн
Piping |  | 392 | 2020-04-29 | 2021-12-17 |  | 19.49%
CN-EDG-PI-1071 | Pipe Supports - Prefabrication EDG | 3 | 2020-04-29 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-EDG-PI-1000 | Piping Erection - Cable Rack EDG | 10 | 2021-03-29 | 2021-07-22 | DI | 50.73% | 1 | tons/тн
CN-EDG-PI-1020 | Piping Testing (RT, PWHT) - Cable Rack | 7 | 2021-03-29 | 2021-07-27 | Стык/Jo | 23.81% | 104 | DI
CN-EDG-PI-1072 | Pipe Supports - Installation EDG | 7 | 2021-04-11 | 2021-06-16 | tons/тн | 49% | 21 | Стык/Jo
CN-EDG-PI-1083 | Piping Testing (Hydrotests) Cable Rack EDG | 7 | 2021-07-26 | 2021-08-01 | Стык/Jo | 0% | 1 | Стык/Jo
CN-EDG-PI-1010 | Piping Erection - EDG | 10 | 2021-11-24 | 2021-12-03 | DI | 0% | 367 | DI
CN-EDG-PI-1030 | Piping Testing (RT, PWHT) - EDG | 10 | 2021-11-25 | 2021-12-04 | Стык/Jo | 0% | 160 | Стык/Jo
CN-EDG-PI-1093 | Piping Testing (Hydrotests) EDG | 10 | 2021-11-29 | 2021-12-08 | Стык/Jo | 0% | 1 | Стык/Jo
CN-EDG-PI-1073 | Piping Painting - EDG | 7 | 2021-12-03 | 2021-12-09 | m2/м2 | 0% | 50 | m2/м2
CN-EDG-PI-1070 | Piping Insulation - EDG | 7 | 2021-12-04 | 2021-12-10 | m/м | 0% | 187 | m/м
CN-EDG-PI-1050 | Piping Insulation - Cable Rack | 7 | 2021-12-11 | 2021-12-17 | m/м | 0% | 165 | m/м
Electrical |  | 427 | 2020-11-23 | 2022-02-10 |  | 29.68%
CN-EDG-EL-1020 | Electrical Cable Trays EDG - Cable Rack | 40 | 2020-11-23 | 2021-06-05 | m/м | 94% | 1265 | m/м
CN-EDG-EL-1290 | Electrical Cable Pulling - EDG Area - Cable Rack | 15 | 2021-06-06 | 2021-06-20 | m/м | 0% | 1500 | m/м
CN-EDG-EL-1030 | Electrical Cable Terminations - EDG Cable Rack | 10 | 2021-06-11 | 2021-06-20 | ea/шт | 0% | 75 | ea/шт
CN-EDG-EL-1140 | Heat Tracing - Cable Rack | 5 | 2021-07-23 | 2021-07-27 | m/м | 0% | 100 | m/м
CN-EDG-EL-1010 | Electrical Cable Trays - EDG | 5 | 2021-12-04 | 2021-12-08 | m/м | 0% | 54 | m/м
CN-EDG-EL-1160 | Heat Tracing - EDG | 7 | 2021-12-11 | 2021-12-17 | m/м | 0% | 200 | m/м
CN-EDG-EL-1280 | Electrical Cable Pulling - EDG Area | 25 | 2021-12-14 | 2022-01-07 | m/м | 0% | 2000 | m/м
CN-EDG-EL-1000 | Electrical Junction Boxes - EDG Area | 30 | 2021-12-19 | 2022-01-17 | ea/шт | 0% | 6 | ea/шт
CN-EDG-EL-1060 | Electrical Cable Terminations - EDG | 11 | 2022-01-11 | 2022-01-21 | ea/шт | 0% | 76 | ea/шт
CN-EDG-EL-1040 | Earthing & Lightening - EDG Area | 5 | 2022-01-22 | 2022-01-26 | ea/шт | 0% | 3 | ea/шт
CN-EDG-EL-1050 | Lighting - EDG Area | 6 | 2022-02-05 | 2022-02-10 | ea/шт | 0% | 28 | ea/шт
Instrumetation |  | 431 | 2020-11-23 | 2022-02-01 |  | 50.49%
CN-EDG-IN-1020 | Instrument Cable Trays - EDG Cable Rack | 45 | 2020-11-23 | 2021-06-05 | m/м | 98% | 1379 | m/м
CN-EDG-IN-1230 | Instrument Cable Pulling - EDG Cable Rack | 15 | 2021-04-21 | 2021-06-20 | m/м | 95% | 1171 | m/м
CN-EDG-IN-1040 | Field Instrument - Cable Rack | 5 | 2021-08-12 | 2021-08-16 | ea/шт | 0% | 7 | ea/шт
CN-EDG-IN-1220 | Instrument Cable Pulling - EDG Area | 30 | 2021-12-24 | 2022-01-22 | m/м | 0% | 6766 | m/м
CN-EDG-IN-1000 | Instrument Junction Boxes - EDG Area | 5 | 2022-01-03 | 2022-01-07 | ea/шт | 0% | 6 | ea/шт
CN-EDG-IN-1050 | Field Instrument - EDG | 5 | 2022-01-08 | 2022-01-12 | ea/шт | 0% | 2 | ea/шт
CN-EDG-IN-1030 | F&G - EDG Area | 12 | 2022-01-14 | 2022-01-25 | ea/шт | 0% | 12 | ea/шт
CN-EDG-IN-1070 | Instrument Terminations - EDG | 5 | 2022-01-23 | 2022-01-27 | ea/шт | 0% | 53 | ea/шт
CN-EDG-IN-1080 | Instrument Testing - EDG | 5 | 2022-01-28 | 2022-02-01 | ea/шт | 0% | 4 | ea/шт
Telecom |  | 7 | 2022-02-02 | 2022-02-08 |  | 0%
CN-EDG-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - EDG Area | 7 | 2022-02-02 | 2022-02-08 | ea/шт | 0% | 300 | ea/шт
HSE |  | 10 | 2022-02-02 | 2022-02-11 |  | 0%
CN-EDG-HSE-1000 | HSE Installation - EDG Area | 10 | 2022-02-02 | 2022-02-11 | ea/шт | 0% | 18 | ea/шт
MAINTENANCEBUILDING |  | 626 | 2020-04-30 | 2022-07-17 |  | 31.68%
Civil/Structural |  | 614 | 2020-10-17 | 2022-07-05 |  | 57.24%
CN-MNB-CS-1010-1 | Lean Concrete - Maintenance Building | 7 | 2020-10-17 | 2020-10-19 | m3/м3 | 100% | 5 | m3/м3
CN-MNB-CS-1010 | Foundation - Maintenance Building | 45 | 2020-10-20 | 2021-03-11 | m3/м3 | 100% | 165.61 | m3/м3
CN-MNB-CS-1030 | Building Structural Steel Erection - Maintenance Building | 90 | 2021-02-11 | 2021-06-16 | tons/тн | 86% | 191 | tons/тн
CN-MNB-CS-1280 | Building Cladding - Maintenance Building | 60 | 2021-03-23 | 2021-05-14 | m2/м2 | 100% | 1773 | m2/м2
CN-MNB-CS-1290 | Building Internal Works - Maintenance Building | 100 | 2021-06-04 | 2021-09-11 | компл. | 0% | 1 | компл.
CN-MNB-CS-1040 | Fireproofing - Maintenance Building | 40 | 2022-01-13 | 2022-02-21 | m2/м2 | 0% | 335.82 | m2/м2
CN-MNB-CS-1020 | Building Finishing - Maintenance Building | 50 | 2022-05-17 | 2022-07-05 | компл. | 0% | 1 | компл.
Mechanical |  | 423 | 2021-05-07 | 2022-06-30 |  | 15.76%
CN-MNB-CS-1270 | Building Crane Installation (incl. load test) - Maintenance Building | 30 | 2021-05-07 | 2021-05-07 | tons/тн | 100% | 6 | tons/тн
CN-MNB-HV-1000 | Building HVAC - Maintenance Building | 45 | 2022-05-17 | 2022-06-30 | компл. | 0% | 1 | компл.
Piping |  | 310 | 2020-04-30 | 2021-12-08 |  | 4.24%
CN-MNB-PI-1071 | Pipe Supports - Prefabrication Maintenance Building | 7 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-MNB-PI-1072 | Pipe Supports - Installation Maintenance Building | 35 | 2021-08-09 | 2021-09-12 | tons/тн | 0% | 1 | tons/тн
CN-MNB-PI-1010 | Piping Erection - Maintenance Building | 45 | 2021-08-29 | 2021-10-12 | DI | 0% | 223 | DI
CN-MNB-PI-1030 | Piping Testing (RT, PWHT) - Maintenance Building | 25 | 2021-09-23 | 2021-10-17 | Стык/Jo | 0% | 234 | Стык/Jo
CN-MNB-PI-1083 | Piping Testing (Hydrotests) | 25 | 2021-09-28 | 2021-10-22 | Стык/Jo | 0% | 1 | Стык/Jo
CN-MNB-PI-1073 | Piping Painting - Maintenance Building | 25 | 2021-10-03 | 2021-10-27 | m2/м2 | 0% | 18 | m2/м2
CN-MNB-PI-1070 | Piping Insulation - Maintenance Building | 25 | 2021-11-14 | 2021-12-08 | m/м | 0% | 249 | m/м
Electrical |  | 119 | 2021-09-23 | 2022-01-19 |  | 0%
CN-MNB-EL-2000 | Electrical Cable Trays - Maintenance Building | 25 | 2021-09-23 | 2021-10-17 | m/м | 0% | 521 | m/м
CN-MNB-EL-2010 | Electrical Cable Pulling - Maintenance Building | 75 | 2021-09-28 | 2021-12-11 | m/м | 0% | 7219 | m/м
CN-MNB-EL-2070 | Electrical Junction Boxes Maintenance building | 30 | 2021-10-19 | 2021-11-17 | ea/шт | 0% | 40 | ea/шт
CN-MNB-EL-2020 | Electrical Heat Tracing - Maintenance Building | 20 | 2021-11-04 | 2021-11-23 | m/м | 0% | 400 | m/м
CN-MNB-EL-2040 | Electrical Equipment installation - Maintenance Building | 15 | 2021-11-27 | 2021-12-11 | tons/тн | 0% | 2 | tons/тн
CN-MNB-EL-1010 | Building Electrical (terminations) - Maintenance Building | 15 | 2021-12-04 | 2021-12-18 | ea/шт | 0% | 118 | ea/шт
CN-MNB-EL-2030 | Electrical Cable Terminations- Maintenance Building | 15 | 2021-12-11 | 2021-12-25 | ea/шт | 0% | 145 | ea/шт
CN-MNB-EL-2060 | Earthing and Lightning - Maintenance Building | 10 | 2021-12-19 | 2021-12-28 | ea/шт | 0% | 147 | ea/шт
CN-MNB-EL-2050 | Lighting - Maintenance Building | 25 | 2021-12-26 | 2022-01-19 | ea/шт | 0% | 64 | ea/шт
Instrumetation |  | 136 | 2021-10-28 | 2022-03-12 |  | 0%
CN-MNB-IN-2000 | Instrument Cable Trays - Maintenance Building | 45 | 2021-10-28 | 2021-12-11 | m/м | 0% | 383 | m/м
CN-MNB-IN-2010 | Instrument Cable Pulling - Maintenance Building | 90 | 2021-11-17 | 2022-02-14 | m/м | 0% | 11646 | m/м
CN-MNB-IN-2020 | Field Instruments - Maintenance Building | 40 | 2021-12-01 | 2022-01-09 | ea/шт | 0% | 24 | ea/шт
CN-MNB-IN-2050 | Instrument Junction Boxes - Maintencance Building | 14 | 2021-12-01 | 2021-12-14 | ea/шт | 0% | 16 | ea/шт
CN-MNB-IN-2030 | F&G - Maintencance Building | 37 | 2022-01-24 | 2022-03-01 | ea/шт | 0% | 37 | ea/шт
CN-MNB-IN-1010 | Building Instrumentation (termination) - Maintenance Building | 20 | 2022-02-10 | 2022-03-01 | ea/шт | 0% | 167 | ea/шт
CN-MNB-IN-2040 | Instrument Testing - Maintencance Building | 24 | 2022-02-17 | 2022-03-12 | ea/шт | 0% | 24 | ea/шт
Telecom |  | 5 | 2022-03-02 | 2022-03-06 |  | 0%
CN-MNB-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Maintenance Building | 5 | 2022-03-02 | 2022-03-06 | m/м | 0% | 283 | m/м
HSE |  | 12 | 2022-07-06 | 2022-07-17 |  | 0%
CN-MNB-HS-1000 | HSE Installation - Maintenance Building | 12 | 2022-07-06 | 2022-07-17 | ea/шт | 0% | 35 | ea/шт
FIELDAUXILLARYROOM-AREA57 |  | 903 | 2020-01-04 | 2022-04-21 |  | 28.81%
Civil/Structural |  | 778 | 2020-01-04 | 2021-12-17 |  | 86.38%
CN-FAR-CS-1330 | Backfilling - FAR Building Area | 143 | 2020-01-04 | 2021-07-08 | m3/м3 | 94% | 13714 | m3/м3
CN-FAR-CS-1390 | Foundation - FAR Building (NOT PRESENTED IN BoQ) | 116 | 2020-01-28 | 2020-10-20 | m3/м3 | 100% | 128.11 | m3/м3
CN-FAR-CS-1180-1 | Lean Concrete - Rack Module Far Building Area CR 10-15 | 7 | 2020-02-01 | 2020-07-02 | m3/м3 | 100% | 5 | m3/м3
CN-FAR-CS-1360 | Building Structural Steel- FAR Building Area | 183 | 2020-02-01 | 2021-06-16 | tons/тн | 99.99% | 954 | tons/тн
CN-FAR-CS-1190-1 | Lean Concrete - FAR Building Area PR 34-36 | 10 | 2020-02-05 | 2020-02-10 | m3/м3 | 100% | 8 | m3/м3
CN-FAR-CS-1180 | Foundation - Rack Module FAR Building Area CR 10-15 | 41 | 2020-02-06 | 2020-11-22 | m3/м3 | 100% | 75.14 | m3/м3
CN-FAR-CS-1190 | Foundation - Misc Foundations FAR Building Area PR 34-36 | 15 | 2020-02-20 | 2020-06-15 | m3/м3 | 100% | 84 | m3/м3
CN-FAR-CS-1140 | Building Cladding - FAR Building | 60 | 2020-07-16 | 2021-04-12 | m2/м2 | 100% | 6925 | m2/м2
CN-FAR-CS-1150 | Building Internal Works - FAR Building (Grade slab & Curb Walls) | 95 | 2020-07-17 | 2021-08-18 | компл. | 80% | 1 | компл.
CN-FAR-CS-1350 | Structural Steel Piperack - FAR Building Area PR 34-36 | 30 | 2020-09-02 | 2020-11-20 | tons/тн | 100% | 95 | tons/тн
CN-FAR-CS-1380 | Structural Steel Cable Rack - FAR Building Area CR 10-15 | 45 | 2020-10-11 | 2021-06-09 | tons/тн | 99.6% | 95 | tons/тн
CN-FAR-CS-1100 | Fireproofing - FAR Building Area | 195 | 2020-10-17 | 2021-06-11 | m2/м2 | 99.9% | 2014 | m2/м2
CN-FAR-CS-1070 | E/I Supports - FAR Building Area | 80 | 2020-12-16 | 2021-06-11 | tons/тн | 28% | 1 | tons/тн
CN-FAR-CS-1370 | Misc Structural Steel - FAR Building Area | 30 | 2021-03-02 | 2021-06-14 | tons/тн | 49% | 2 | tons/тн
CN-FAR-CS-1340 | Secondary Pipe Supports - FAR Building Area | 15 | 2021-06-07 | 2021-06-21 | tons/тн | 0% | 8 | tons/тн
CN-FAR-CS-1110 | Building Finishing - FAR Building | 120 | 2021-08-20 | 2021-12-17 | компл. | 0% | 1 | компл.
Mechanical |  | 205 | 2021-04-22 | 2021-12-12 |  | 26%
CN-FAR-HV-1000 | Building HVAC - FAR Building | 205 | 2021-04-22 | 2021-12-12 | компл. | 26% | 1 | компл.
Piping |  | 500 | 2020-04-30 | 2021-12-26 |  | 30.48%
CN-FAR-PI-1031 | Pipe Supports - Prefabrication FAR Building | 15 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-FAR-PI-1000 | Piping Erection - Cable Rack FAR | 30 | 2021-03-06 | 2021-08-13 | DI | 47.5% | 1 | tons/тн
CN-FAR-PI-1010 | Piping Testing (RT, PWHT) - FAR Cable Rack | 7 | 2021-03-06 | 2021-08-18 | Стык/Jo | 87.1% | 457 | DI
CN-FAR-PI-1032 | Pipe Supports - Installation FAR Building | 25 | 2021-03-06 | 2021-07-19 | tons/тн | 48% | 31 | Стык/Jo
CN-FAR-PI-1043 | Piping Testing (Hydrotests) | 7 | 2021-09-01 | 2021-09-07 | Стык/Jo | 0% | 1 | Стык/Jo
CN-FAR-PI-1033 | Piping Painting - FAR Building | 7 | 2021-09-06 | 2021-09-12 | m2/м2 | 0% | 48 | m2/м2
CN-FAR-PI-1030 | Piping Insulation - FAR Cable Rack | 20 | 2021-12-07 | 2021-12-26 | m/м | 0% | 569 | m/м
Electrical |  | 485 | 2020-12-18 | 2022-04-21 |  | 5.01%
CN-FAR-EL-1020 | Electrical Cable Trays - FAR Cable Rack | 90 | 2020-12-18 | 2021-04-10 | m/м | 100% | 738 | m/м
CN-FAR-EL-1300 | Electrical Cable Trays - FAR Building | 90 | 2021-03-13 | 2021-07-07 | m/м | 49.65% | 9550 | m/м
CN-FAR-EL-1000 | Building Switchboards, Transformers and Other Electrical Equipment Erection - FAR Building | 255 | 2021-04-22 | 2022-02-17 | ea/шт | 18% | 6459 | m/м
CN-FAR-EL-1060 | Building Electrical Cables Work - FAR Building | 318 | 2021-06-08 | 2022-04-21 | m/м | 0% | 503066 | m/м
CN-FAR-EL-1290 | Electrical Cable Pulling - FAR Building Area | 90 | 2021-06-12 | 2021-09-09 | m/м | 0% | 295 | ea/шт
CN-FAR-EL-1040 | Electrical Cable Terminations - FAR Cable Rack | 56 | 2021-06-19 | 2021-08-13 | ea/шт | 0% | 11452 | ea/шт
CN-FAR-EL-1070 | Building Electrical Terminations - FAR Building | 292 | 2021-06-22 | 2022-04-09 | ea/шт | 0% | 140 | ea/шт
CN-FAR-EL-1010 | Electrical Junction Boxes - FAR Building Area | 65 | 2021-06-25 | 2021-08-28 | ea/шт | 0% | 81 | ea/шт
CN-FAR-EL-1030 | Earthing & Lightening - FAR Building Area | 150 | 2021-06-30 | 2021-11-26 | ea/шт | 0% | 840 | ea/шт
CN-FAR-EL-1050 | Lighting - FAR Building Area | 100 | 2021-07-05 | 2021-10-12 | ea/шт | 0% | 344 | ea/шт
CN-FAR-EL-1120 | Heat Tracing - FAR Cable Rack | 55 | 2021-10-03 | 2021-11-26 | m/м | 0% | 1300 | m/м
Instrumetation |  | 402 | 2020-12-12 | 2022-02-02 |  | 48.61%
CN-FAR-IN-1020 | Instrument Cable Trays - FAR Cable Rack | 150 | 2020-12-12 | 2021-06-11 | m/м | 99.9% | 2573 | m/м
CN-FAR-IN-1230 | Instrument Cable Trays - FAR Building | 80 | 2021-03-14 | 2021-06-30 | m/м | 33.36% | 2535 | m/м
CN-FAR-IN-1220 | Instrument Cable Pulling - FAR Building Area | 140 | 2021-04-20 | 2021-09-20 | m/м | 95% | 43087 | m/м
CN-FAR-IN-1000 | Building ICSS & Instrument Equipment Erection - FAR Building | 90 | 2021-06-26 | 2021-09-23 | ea/шт | 0% | 104 | ea/шт
CN-FAR-IN-1060 | Building Instrumentation Cables Work - FAR Building | 210 | 2021-07-03 | 2022-01-28 | m/м | 0% | 11829 | m/м
CN-FAR-IN-1070 | Building Instrumentation Terminations - FAR Building | 200 | 2021-07-18 | 2022-02-02 | ea/шт | 0% | 102 | ea/шт
CN-FAR-IN-1010 | Instrument Junction Boxes - FAR Building Area | 76 | 2021-08-21 | 2021-11-04 | ea/шт | 0% | 56 | ea/шт
CN-FAR-IN-1030 | Field Instrument - FAR Cable Rack | 70 | 2021-09-26 | 2021-12-04 | ea/шт | 0% | 249 | ea/шт
CN-FAR-IN-1040 | F&G - FAR Building Area | 65 | 2021-10-31 | 2022-01-03 | ea/шт | 0% | 128 | ea/шт
CN-FAR-IN-1050 | Instrument Terminations - FAR Cable Rack | 67 | 2021-11-28 | 2022-02-02 | ea/шт | 0% | 371 | ea/шт
Telecom |  | 210 | 2021-08-10 | 2022-03-07 |  | 0%
CN-FAR-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - FAR Building Area | 210 | 2021-08-10 | 2022-03-07 | m/м | 0% | 55250 | m/м
HSE |  | 250 | 2021-06-21 | 2022-02-25 |  | 0%
CN-FAR-HS-1000 | HSE Installation - FAR Building | 250 | 2021-06-21 | 2022-02-25 | ea/шт | 0% | 188 | ea/шт
OPENDRAINAREA-AREA58 |  | 561 | 2019-12-28 | 2022-02-10 |  | 53.35%
Civil/Structural |  | 520 | 2019-12-28 | 2021-12-31 |  | 86.41%
CN-ODA-CS-1170-1 | Lean Concrete - Rack Module - PR 41 | 2 | 2019-12-28 | 2020-06-14 | m3/м3 | 100% | 2 | m3/м3
CN-ODA-CS-1170 | Foundation - Rack Module - PR 41 & CPI Separator | 20 | 2020-02-29 | 2021-06-10 | m3/м3 | 56.36% | 28.84 | m3/м3
CN-ODA-CS-1140 | Concrete Drain Tanks - Excavation / Dewatering System Open Drain | 30 | 2020-07-24 | 2020-10-25 | m3/м3 | 100% | 11804 | m3/м3
CN-ODA-CS-1080 | Concrete Drain Tanks - Base Slab Rebar / Walls Rebar / Internal Walls Rebar / Shuttering / Concreting Open Drain | 150 | 2020-08-23 | 2021-07-09 | m3/м3 | 99.7% | 1622 | m3/м3
CN-ODA-CS-1090 | Structural Steel Open Drain - PR 41 | 9 | 2020-10-13 | 2020-11-26 | tons/тн | 100% | 18 | tons/тн
CN-ODA-CS-1160 | Foundation - Control Room | 7 | 2021-06-11 | 2021-06-17 | m3/м3 | 0% | 2 | m3/м3
CN-ODA-CS-1160-1 | Lean Concrete - Control Room | 5 | 2021-06-11 | 2021-06-15 | m3/м3 | 0% | 27 | m3/м3
CN-ODA-CS-1150-1 | Lean Concrete - Drain Pumping Station | 5 | 2021-07-05 | 2021-07-09 | m3/м3 | 0% | 1 | m3/м3
CN-ODA-CS-1141 | Backfilling - Open Drain Area | 20 | 2021-07-10 | 2021-07-29 | m3/м3 | 0% | 1117 | m3/м3
CN-ODA-CS-1150 | Foundation - Drain Pumping Station | 7 | 2021-07-15 | 2021-07-21 | m3/м3 | 0% | 6 | m3/м3
CN-ODA-CS-1114 | Structural Steel - Shelter | 10 | 2021-07-25 | 2021-08-03 | tons/тн | 0% | 23 | tons/тн
CN-ODA-CS-1050 | Piping Supports - Open Drain Area | 10 | 2021-08-04 | 2021-08-13 | tons/тн | 0% | 19 | tons/тн
CN-ODA-CS-1111 | Building Cladding - Shelter | 19 | 2021-08-04 | 2021-08-22 | m2/м2 | 0% | 235 | m2/м2
CN-ODA-CS-1112 | Building Internal - Shelter | 15 | 2021-08-04 | 2021-08-18 | компл. | 0% | 1 | компл.
CN-ODA-CS-1060 | E/I Supports - Open Drain Area | 8 | 2021-09-05 | 2021-09-12 | tons/тн | 0% | 1 | tons/тн
CN-ODA-CS-1113 | Building Finishing- Shelter | 15 | 2021-12-17 | 2021-12-31 | компл. | 0% | 1 | компл.
Mechanical |  | 118 | 2021-08-21 | 2021-12-16 |  | 0%
CN-ODA-MR-1000 | Erection - Open Drain Pumps (incl. Shetler) | 20 | 2021-08-21 | 2021-09-09 | tons/тн | 0% | 4 | tons/тн
CN-ODA-MR-1001 | Erection Tank For Package - Open Drain Area | 5 | 2021-09-10 | 2021-09-14 | tons/тн | 0% | 1 | tons/тн
CN-ODA-MR-1003 | Final Water Treatment Package - Open Drain Area | 10 | 2021-09-15 | 2021-09-24 | tons/тн | 0% | 3 | tons/тн
CN-ODA-MR-1004 | Static Equipment Internals - Open Drain Area | 5 | 2021-09-15 | 2021-09-19 | tons/тн | 0% | 1 | tons/тн
CN-ODA-MR-1002 | Storm, Melt Water and Industrial Water Treatment Package - Open Drain Area | 15 | 2021-09-20 | 2021-10-04 | tons/тн | 0% | 11 | tons/тн
CN-ODA-MR-1005 | Static Equipment Insulation - Open Drain Area | 20 | 2021-11-27 | 2021-12-16 | m2/м2 | 0% | 105 | m2/м2
Piping |  | 239 | 2020-04-30 | 2021-12-16 |  | 7.4%
CN-ODA-PI-1071 | Pipe Supports - Prefabrication Open Drain Area | 5 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-ODA-PI-1020 | Piping Erection - Open Drain | 30 | 2021-04-26 | 2021-10-17 | DI | 6% | 1 | tons/тн
CN-ODA-PI-1072 | Pipe Supports - Installation Open Drain Area | 5 | 2021-04-26 | 2021-09-12 | tons/тн | 5% | 444 | DI
CN-ODA-PI-1000 | Piping Erection - Cable Rack Open Drain | 5 | 2021-10-05 | 2021-10-09 | DI | 0% | 8 | DI
CN-ODA-PI-1040 | Piping Testing (RT, PWHT) - Open Drain | 17 | 2021-10-06 | 2021-10-22 | Стык/Jo | 0% | 71 | Стык/Jo
CN-ODA-PI-1093 | Piping Testing (Hydrotests) Open Drain | 10 | 2021-10-12 | 2021-10-21 | Стык/Jo | 0% | 1 | Стык/Jo
CN-ODA-PI-1010 | Piping Testing (RT, PWHT) - Cable Rack | 10 | 2021-11-14 | 2021-11-23 | Стык/Jo | 0% | 6 | Стык/Jo
CN-ODA-PI-1073 | Piping Painting - Open Drain Area | 15 | 2021-11-20 | 2021-12-04 | m2/м2 | 0% | 71 | m2/м2
CN-ODA-PI-1083 | Piping Testing (Hydrotests) Cable Rack Open Drain | 10 | 2021-11-20 | 2021-11-29 | Стык/Jo | 0% | 1 | Стык/Jo
CN-ODA-EL-1160 | Piping Insulation - Cable Rack | 13 | 2021-11-27 | 2021-12-09 | m/м | 0% | 10 | m/м
CN-ODA-PI-1070 | Piping Insulation - Open Drain | 20 | 2021-11-27 | 2021-12-16 | m/м | 0% | 380 | m/м
Electrical |  | 69 | 2021-11-07 | 2022-01-14 |  | 0%
CN-ODA-EL-1001 | Electrical Cable Trays - Open Drain Area | 13 | 2021-11-07 | 2021-11-19 | m/м | 0% | 323 | m/м
CN-ODA-EL-1000 | Electrical Cable Trays - Open Drain Cable Rack | 5 | 2021-11-12 | 2021-11-16 | m/м | 0% | 124 | m/м
CN-ODA-EL-1300 | Electrical Cable Pulling - Open Drain Area | 54 | 2021-11-12 | 2022-01-04 | m/м | 0% | 4600 | m/м
CN-ODA-EL-1020 | Electrical Junction Boxes - Open Drain Area | 15 | 2021-12-02 | 2021-12-16 | ea/шт | 0% | 30 | ea/шт
CN-ODA-PI-1050 | Heat Tracing - Open Drain Area | 5 | 2021-12-05 | 2021-12-09 | m/м | 0% | 460 | m/м
CN-ODA-EL-1030 | Electrical Cable Terminations - Open Drain Cable Rack | 35 | 2021-12-06 | 2022-01-09 | ea/шт | 0% | 70 | ea/шт
CN-ODA-EL-1040 | Lighting - Open Drain Area | 36 | 2021-12-10 | 2022-01-14 | ea/шт | 0% | 38 | ea/шт
CN-ODA-EL-1031 | Electrical Cable Terminations - Open Drain Area | 35 | 2021-12-10 | 2022-01-13 | ea/шт | 0% | 150 | ea/шт
Instrumetation |  | 62 | 2021-12-10 | 2022-02-09 |  | 0%
CN-ODA-IN-1000 | Instrument Cable Trays - Open Drain Cable Rack | 5 | 2021-12-10 | 2021-12-14 | m/м | 0% | 32 | m/м
CN-ODA-IN-1220 | Instrument Cable Pulling - Open Drain Area | 30 | 2021-12-15 | 2022-01-13 | m/м | 0% | 6236 | m/м
CN-ODA-IN-1030 | Field Instrument - Cable Rack | 5 | 2022-01-09 | 2022-01-13 | ea/шт | 0% | 12 | ea/шт
CN-ODA-IN-1050 | Field Instrument - Open Drain | 25 | 2022-01-11 | 2022-02-04 | ea/шт | 0% | 12 | ea/шт
CN-ODA-IN-1041 | Instrument Terminations -Open Drain Area | 30 | 2022-01-11 | 2022-02-09 | ea/шт | 0% | 1141 | ea/шт
CN-ODA-IN-1010 | F&G - Open Drain Area | 11 | 2022-01-18 | 2022-01-28 | ea/шт | 0% | 11 | ea/шт
CN-ODA-IN-1020 | Instrument Junction Boxes - Open Drain Area | 7 | 2022-01-24 | 2022-01-30 | ea/шт | 0% | 14 | ea/шт
Telecom |  | 7 | 2022-01-22 | 2022-01-28 |  | 0%
CN-ODA-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Open Drain Area | 7 | 2022-01-22 | 2022-01-28 | ea/шт | 0% | 14 | ea/шт
HSE |  | 13 | 2022-01-29 | 2022-02-10 |  | 0%
CN-ODA-HS-1000 | HSE Installation - Open Drain Area | 13 | 2022-01-29 | 2022-02-10 | ea/шт | 0% | 22 | ea/шт
FUEL&SEALGASAREA-AREA59 |  | 723 | 2019-12-16 | 2022-01-16 |  | 33.33%
Civil/Structural |  | 607 | 2019-12-16 | 2021-09-22 |  | 65.63%
CN-FSG-CS-1091-1 | Lean Concrete- Fuel And Seal Gas Area - PR18 / GMP 26 | 3 | 2019-12-16 | 2020-06-25 | m3/м3 | 100% | 3 | m3/м3
CN-FSG-CS-1091 | Foundation - Fuel And Seal Gas Area - PR18 / GMP 26 | 102 | 2020-01-26 | 2021-06-07 | m3/м3 | 95.91% | 117.84 | m3/м3
CN-FSG-CS-1061 | Structural Steel Fuel & Seal Gas - Piperack NS-PR17 / NS-PR18 | 45 | 2020-08-15 | 2020-10-26 | tons/тн | 100% | 87 | tons/тн
CN-FSG-CS-1101 | Structural Steel Fuel & Seal Gas - Piperack NS-PR43 | 30 | 2020-12-05 | 2020-12-21 | tons/тн | 100% | 41 | tons/тн
CN-FSG-CS-1060 | Structural Steel GMP / Crossovers - Fuel & Seal Gas | 21 | 2021-01-09 | 2021-06-19 | tons/тн | 91% | 25 | tons/тн
CN-FSG-CS-1030 | Piping Supports - Fuel & Seal Gas | 7 | 2021-06-09 | 2021-06-15 | tons/тн | 0% | 6 | tons/тн
CN-FSG-CS-1061-1 | Fireproofing - Fuel And Seal Gas Area [Newly Added] | 30 | 2021-08-24 | 2021-09-22 | m2/м2 | 0% | 205.13 | m2/м2
Mechanical |  | 142 | 2021-06-20 | 2021-11-08 |  | 0%
CN-FSG-MS-1000 | Erection - Electric Heater | 12 | 2021-06-20 | 2021-07-01 | tons/тн | 0% | 7 | tons/тн
CN-FSG-MS-1001 | Insulation - Electric Heater | 16 | 2021-10-24 | 2021-11-08 | m2/м2 | 0% | 29 | m2/м2
Piping |  | 367 | 2020-04-30 | 2021-12-09 |  | 26.32%
CN-FSG-PI-1021 | Pipe Supports - Prefabrication Fuel & Seal Gas | 15 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 3 | tons/тн
CN-FSG-PI-1000 | Piping Erection - Fuel & Seal Gas | 40 | 2021-03-13 | 2021-09-17 | DI | 41.32% | 3 | tons/тн
CN-FSG-PI-1010 | Piping Testing (RT, PWHT) - Fuel & Seal Gas | 37 | 2021-04-05 | 2021-10-17 | Стык/Jo | 14.34% | 1652 | DI
CN-FSG-PI-1022 | Pipe Supports - Installation Fuel & Seal Gas | 34 | 2021-04-06 | 2021-08-27 | tons/тн | 40% | 837 | Стык/Jo
CN-FSG-PI-1033 | Piping Testing (Hydrotests) | 37 | 2021-09-16 | 2021-10-22 | Стык/Jo | 0% | 1 | Стык/Jo
CN-FSG-PI-1023 | Piping Painting - Fuel & Seal Gas | 20 | 2021-10-11 | 2021-10-30 | m2/м2 | 0% | 198 | m2/м2
CN-FSG-PI-1020 | Piping Insulation - Fuel & Seal Gas | 50 | 2021-10-21 | 2021-12-09 | m/м | 0% | 1857 | m/м
Electrical |  | 318 | 2020-12-23 | 2021-12-12 |  | 17.26%
CN-FSG-EL-1320 | Electrical Cable Trays - Fuel & Seal Gas - Cable Rack | 72 | 2020-12-23 | 2021-06-10 | m/м | 86% | 522 | m/м
CN-FSG-EL-1330 | Electrical Cable Pulling - Fuel & Seal Gas - Cable Rack | 34 | 2021-06-04 | 2021-07-07 | m/м | 0% | 1200 | m/м
CN-FSG-EL-1010 | Electrical Cable Trays - Fuel & Seal Gas | 35 | 2021-10-13 | 2021-11-16 | m/м | 0% | 174 | m/м
CN-FSG-EL-1310 | Electrical Cable Pulling - Fuel & Seal Gas | 34 | 2021-10-30 | 2021-12-02 | m/м | 0% | 400 | m/м
CN-FSG-EL-1130 | Heat Tracing - Fuel & Seal Gas | 20 | 2021-11-10 | 2021-11-29 | m/м | 0% | 1144 | m/м
CN-FSG-EL-1020 | Electrical Junction Boxes - Fuel & Seal Gas | 21 | 2021-11-16 | 2021-12-06 | ea/шт | 0% | 53 | ea/шт
CN-FSG-EL-1040 | Electrical Cable Terminations - Fuel & Seal Gas | 16 | 2021-11-24 | 2021-12-09 | ea/шт | 0% | 150 | ea/шт
CN-FSG-EL-1030 | Lighting - Fuel & Seal Gas | 12 | 2021-12-01 | 2021-12-12 | ea/шт | 0% | 22 | ea/шт
Instrumetation |  | 353 | 2020-12-23 | 2022-01-16 |  | 19.38%
CN-FSG-IN-1230 | Instrument Cable Trays - Fuel & Seal Gas - Cable Rack | 60 | 2020-12-23 | 2021-06-08 | m/м | 95% | 701 | m/м
CN-FSG-IN-1240 | Instrument Cable Pulling - Fuel & Seal Gas - Cable Rack | 40 | 2021-04-19 | 2021-07-07 | m/м | 95% | 7424 | m/м
CN-FSG-IN-1000 | Instrument Cable Trays - Fuel & Seal Gas | 60 | 2021-10-21 | 2021-12-19 | m/м | 0% | 234 | m/м
CN-FSG-IN-1220 | Instrument Cable Pulling - Fuel & Seal Gas | 60 | 2021-10-31 | 2021-12-29 | m/м | 0% | 22239 | m/м
CN-FSG-IN-1020 | Instrument Junction Boxes - Fuel & Seal Gas | 20 | 2021-11-30 | 2021-12-19 | ea/шт | 0% | 29 | ea/шт
CN-FSG-IN-1030 | Field Instrument - Fuel & Seal Gas | 30 | 2021-11-30 | 2021-12-29 | ea/шт | 0% | 49 | ea/шт
CN-FSG-IN-1040 | Instrument Terminations - Fuel & Seal Gas | 30 | 2021-12-05 | 2022-01-03 | ea/шт | 0% | 1500 | ea/шт
CN-FSG-IN-1010 | F&G - Fuel & Seal Gas | 9 | 2021-12-26 | 2022-01-03 | ea/шт | 0% | 9 | ea/шт
CN-FSG-IN-1041 | Instrument Testing - Fuel & Seal Gas | 13 | 2022-01-04 | 2022-01-16 | ea/шт | 0% | 24 | ea/шт
Telecom |  | 7 | 2022-01-10 | 2022-01-16 |  | 0%
CN-FSG-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Fuel & Seal Gas | 7 | 2022-01-10 | 2022-01-16 | ea/шт | 0% | 14 | ea/шт
HSE |  | 10 | 2022-01-07 | 2022-01-16 |  | 0%
CN-FSG-HS-1000 | HSE Installation - Fuel & Seal Gas | 10 | 2022-01-07 | 2022-01-16 | ea/шт | 0% | 12 | ea/шт
HEATTRANSFERFLUIDAREA-AREA60 |  | 639 | 2020-04-30 | 2022-02-26 |  | 28.58%
Civil/Structural |  | 454 | 2020-05-14 | 2021-08-25 |  | 64.64%
RackModule-CR-01 |  | 125 | 2020-05-14 | 2020-10-16 |  | 100%
CN-HTF-CS-1130-1 | Lean Concrete - Rack Module - CR-01 | 3 | 2020-05-14 | 2020-05-15 | m3/м3 | 100% | 2 | m3/м3
CN-HTF-CS-1130 | Foundation - Rack Module - CR-01 | 6 | 2020-05-31 | 2020-07-02 | m3/м3 | 100% | 38 | m3/м3
CN-HTF-CS-1061 | Structural Steel HTF - CR-01 | 34 | 2020-08-18 | 2020-10-16 | tons/тн | 100% | 87 | tons/тн
HeatTransferFluidCirculationandManagementPackage |  | 433 | 2020-06-02 | 2021-08-25 |  | 47.86%
CN-HTF-CS-1100-1 | Lean Concrete - Heat Transfer Fluid Circulation and Management Package and Shelter | 5 | 2020-06-02 | 2020-09-29 | m3/м3 | 100% | 6 | m3/м3
CN-HTF-CS-1100 | Foundation - Heat Transfer Fluid Circulation and Management Package and Shelter | 30 | 2020-06-12 | 2021-06-07 | m3/м3 | 84.86% | 148.06 | m3/м3
CN-HTF-CS-1084 | Structural Steel (Primary) - Shelter Heat Transfer Fluid | 30 | 2021-04-07 | 2021-06-09 | tons/тн | 95% | 42 | tons/тн
CN-HTF-CS-1081 | Building Cladding - Shelter Heat Transfer Fluid | 26 | 2021-06-06 | 2021-07-01 | m2/м2 | 0% | 283 | m2/м2
CN-HTF-CS-1060 | Structural Steel GMP / Crossovers - Heat Transfer Fluid | 15 | 2021-06-10 | 2021-06-24 | tons/тн | 0% | 30 | tons/тн
CN-HTF-CS-1040 | E/I Supports - Heat Transfer Fluid | 15 | 2021-06-25 | 2021-07-09 | tons/тн | 0% | 1 | tons/тн
CN-HTF-CS-1082 | Building Internals - Shelter Heat Transfer Fluid | 7 | 2021-06-30 | 2021-07-06 | компл. | 0% | 1 | компл.
CN-HTF-CS-1030 | Piping Supports - Heat Transfer Fluid | 25 | 2021-07-10 | 2021-08-03 | tons/тн | 0% | 6 | tons/тн
CN-HTF-CS-1083 | Building Finishing - Shelter Heat Transfer Fluid | 30 | 2021-07-27 | 2021-08-25 | компл. | 0% | 1 | компл.
Mechanical |  | 384 | 2020-10-25 | 2021-12-01 |  | 21.88%
CN-HTF-MS-1020 | Erection - HTF Tank | 24 | 2020-10-25 | 2020-10-26 | tons/тн | 100% | 15 | tons/тн
CN-HTF-MS-1000 | Erection - HTF Expansion Vessel (incl. Building) | 34 | 2020-11-26 | 2021-07-04 | tons/тн | 78.13% | 32 | tons/тн
CN-HTF-MS-1030 | Erection - HTF Air Cooler | 14 | 2021-06-26 | 2021-07-09 | tons/тн | 0% | 20 | tons/тн
CN-HTF-MS-1031 | Static Equipment Installation - Heat Transfer Fluid | 20 | 2021-07-01 | 2021-07-20 | tons/тн | 0% | 2 | tons/тн
CN-HTF-MR-1000 | Erection - HTF Pumps | 30 | 2021-07-31 | 2021-08-29 | tons/тн | 0% | 3 | tons/тн
CN-HTF-MS-1010 | Insulation - HTF Equipment Insulation | 55 | 2021-10-08 | 2021-12-01 | m2/м2 | 0% | 217 | m2/м2
Piping |  | 458 | 2020-04-30 | 2021-12-01 |  | 11.42%
CN-HTF-MS-1032 | Pipe Supports - Prefabrication Heat Transfer Fluid | 20 | 2020-04-30 | 2021-01-22 | tons/тн | 100% | 1 | tons/тн
CN-HTF-MS-1033 | Pipe Supports - Installation Heat Transfer Fluid | 23 | 2021-05-17 | 2021-08-11 | tons/тн | 10% | 1 | tons/тн
CN-HTF-PI-1000 | Piping Erection - Heat Transfer Fluid | 54 | 2021-05-17 | 2021-10-01 | DI | 16.56% | 1124 | DI
CN-HTF-PI-1010 | Piping Testing (RT, PWHT) - Heat Transfer Fluid | 54 | 2021-08-19 | 2021-10-11 | Стык/Jo | 0% | 840 | Стык/Jo
CN-HTF-PI-1041 | Piping Testing (Hydrotests) | 54 | 2021-09-03 | 2021-10-26 | Стык/Jo | 0% | 1 | Стык/Jo
CN-HTF-PI-1031 | Piping Painting - Heat Transfer Fluid | 40 | 2021-09-28 | 2021-11-06 | m2/м2 | 0% | 119 | m2/м2
CN-HTF-PI-1030 | Piping Insulation - Heat Transfer Fluid | 40 | 2021-10-23 | 2021-12-01 | m/м | 0% | 847 | m/м
Electrical |  | 354 | 2021-01-02 | 2022-01-17 |  | 16.29%
CN-HTF-EL-1330 | Electrical Cable Trays - Heat Transfer Fluid - Cable Rack | 47 | 2021-01-02 | 2021-01-04 | m/м | 100% | 331 | m/м
CN-HTF-EL-1020 | Electrical Cable Trays - Heat Transfer Fluid | 47 | 2021-04-03 | 2021-12-07 | m/м | 41% | 1250 | m/м
CN-HTF-EL-1340 | Electrical Cable Pulling - Heat Transfer Fluid - Cable Rack | 30 | 2021-06-06 | 2021-07-05 | m/м | 0% | 404 | m/м
CN-HTF-EL-1320 | Electrical Cable Pulling - Heat Transfer Fluid | 45 | 2021-11-06 | 2021-12-20 | m/м | 0% | 1400 | m/м
CN-HTF-EL-1010 | Electrical Junction Boxes - Heat Transfer Fluid | 29 | 2021-11-26 | 2021-12-24 | ea/шт | 0% | 28 | ea/шт
CN-HTF-EL-1040 | Electrical Cable Terminations - Heat Transfer Fluid | 50 | 2021-11-26 | 2022-01-14 | ea/шт | 0% | 220 | ea/шт
CN-HTF-EL-1120 | Heat Tracing - Heat Transfer Fluid | 30 | 2021-11-30 | 2021-12-29 | m/м | 0% | 1600 | m/м
CN-HTF-EL-1030 | Lighting - Heat Transfer Fluid | 35 | 2021-12-14 | 2022-01-17 | ea/шт | 0% | 31 | ea/шт
Instrumetation |  | 376 | 2021-01-03 | 2022-02-10 |  | 1.37%
CN-HTF-IN-1230 | Instrument Cable Trays - Heat Transfer Fluid - Cable Rack | 10 | 2021-01-03 | 2021-01-04 | m/м | 100% | 10 | m/м
CN-HTF-IN-1010 | Instrument Cable Trays - Heat Transfer Fluid | 10 | 2021-04-03 | 2021-12-15 | m/м | 92% | 1227 | m/м
CN-HTF-IN-1240 | Instrument Cable Pulling - Heat Transfer Fluid - Cable Rack | 15 | 2021-06-08 | 2021-06-22 | m/м | 0% | 42 | m/м
CN-HTF-IN-1220 | Instrument Cable Pulling - Heat Transfer Fluid | 30 | 2021-12-13 | 2022-01-11 | m/м | 0% | 6181 | m/м
CN-HTF-IN-1020 | Instrument Junction Boxes - Heat Transfer Fluid | 10 | 2021-12-18 | 2021-12-27 | ea/шт | 0% | 8 | ea/шт
CN-HTF-IN-1030 | Field Instrument - Heat Transfer Fluid | 25 | 2021-12-28 | 2022-01-21 | ea/шт | 0% | 24 | ea/шт
CN-HTF-IN-1040 | Instrument Terminations - Heat Transfer Fluid | 19 | 2022-01-08 | 2022-01-26 | ea/шт | 0% | 1001 | ea/шт
CN-HTF-IN-1041 | Instrument Testing - Heat Transfer Fluid | 10 | 2022-02-01 | 2022-02-10 | ea/шт | 0% | 6 | ea/шт
Telecom |  | 5 | 2022-02-11 | 2022-02-15 |  | 0%
CN-HTF-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - Heat Transfer Fluid | 5 | 2022-02-11 | 2022-02-15 | ea/шт | 0% | 6 | ea/шт
HSE |  | 6 | 2022-02-21 | 2022-02-26 |  | 0%
CN-HTF-HS-1000 | HSE Installation - Heat Transfer Fluid | 6 | 2022-02-21 | 2022-02-26 | ea/шт | 0% | 9 | ea/шт
BATTERYLIMITSTATION |  | 589 | 2020-08-03 | 2022-04-01 |  | 44.53%
COMMON |  | 589 | 2020-08-03 | 2022-04-01 |  | 47.48%
Civil |  | 400 | 2021-02-19 | 2022-04-01 |  | 15.01%
CN-CMN-CS-1000-2-10 | Dismaintling/Demolishing works | 20 | 2021-02-19 | 2021-04-09 | компл. | 100% | 1 | компл.
CN-CMN-EL-1000-1-10 | Cable Trenches | 60 | 2021-10-19 | 2021-12-17 | m3/м3 | 0% | 229 | m3/м3
CN-CMN-CS-1020-5-10 | Duct Banks - Common Area | 20 | 2021-11-03 | 2021-11-22 | m3/м3 | 0% | 5 | m3/м3
CN-CMN-CS-1020-2-10 | Slope protection - Common Area | 90 | 2021-12-08 | 2022-03-07 | m2/м2 | 0% | 870 | m2/м2
CN-CMN-CS-1260-10 | Install Permanent Roads - Common Area | 70 | 2021-12-28 | 2022-03-07 | m/м | 0% | 107 | m/м
CN-CMN-CS-1250-10-1 | Fencing Works - Common Area | 60 | 2022-01-27 | 2022-03-27 | m/м | 0% | 714 | m/м
CN-CMN-CS-1250-10-2 | Gates - Common Area | 30 | 2022-03-03 | 2022-04-01 | ea/шт | 0% | 2 | ea/шт
Piping |  | 406 | 2020-08-03 | 2021-09-30 |  | 63.18%
CN-BLS-CS-1180-13 | AOC Drenage Tie-In | 73 | 2021-02-22 | 2021-06-06 | IM | 99% | 212 | IM
CN-CMN-PI-1110-3-50 | Buried Pipe Trenches HDPE - Excavation UG - LS-01 section | 7 | 2021-06-23 | 2021-06-29 | m3/м3 | 0% | 485 | m3/м3
CN-CMN-PI-1110-3-30 | Fabrication / Installation of Pipe HDPE - UG - LS-01 section | 7 | 2021-06-30 | 2021-07-06 | IM | 0% | 326 | IM
CN-CMN-PI-1110-3-60 | Buried Pipe Trenches HDPE - Backfilling UG - LS-01 section | 7 | 2021-07-05 | 2021-07-11 | m3/м3 | 0% | 485 | m3/м3
CN-CMN-PI-1110-3-00 | Buried Pipe Trenches HDPE - Excavation UG | 30 | 2021-07-28 | 2021-08-26 | m3/м3 | 0% | 2754 | m3/м3
CN-CMN-PI-1110-3-20 | Fabrication / Installation of Pipe HDPE - UG | 30 | 2021-08-02 | 2021-08-31 | IM | 0% | 2064 | IM
CN-CMN-PI-1110-3-40 | Buried Pipe Trenches HDPE - Backfilling UG | 35 | 2021-08-27 | 2021-09-30 | m3/м3 | 0% | 2754 | m3/м3
UGPiping |  | 174 | 2020-08-03 | 2021-01-20 |  | 100%
CN-CMN-PI-1110-3-10 | Prefabrication Drainage System / Pits - UG | 57 | 2020-08-03 | 2020-08-20 | ea/шт | 100% | 4 | ea/шт
CN-CMN-PI-1110-2-80 | Buried Pipe Trenches - Excavation UG | 15 | 2020-08-21 | 2020-10-10 | m3/м3 | 100% | 1522 | m3/м3
CN-CMN-PI-1100-2-61 | Erection Drainage System / Pits - UG | 20 | 2020-08-28 | 2020-10-29 | ea/шт | 100% | 4 | ea/шт
CN-CMN-PI-1110-2-81 | Piping Erection - UG | 45 | 2020-09-27 | 2021-01-03 | DI | 100% | 82 | DI
CN-CMN-PI-1110-2-82 | Piping Painting - UG | 63 | 2020-10-02 | 2021-01-06 | m2/м2 | 100% | 221 | m2/м2
CN-CMN-PI-1110-2-50 | Buried Pipe Trenches - Backfilling UG | 35 | 2020-10-04 | 2021-01-20 | m3/м3 | 100% | 1522 | m3/м3
CN-CMN-PI-1110-2-91 | Piping Testing (Hydrotest, Flushing, Blowing,...) - UG | 6 | 2021-01-06 | 2021-01-12 | Стык/Jo | 100% | 1 | Стык/Jo
MAINPROCESSRACK |  | 560 | 2020-08-12 | 2022-03-14 |  | 25.82%
Civil |  | 408 | 2020-08-12 | 2021-10-27 |  | 82.03%
CN-MPR-CS-1410 | Backfilling EW-PR | 120 | 2021-03-19 | 2021-10-27 | m3/м3 | 38% | 23127 | m3/м3
RackModule-EW-PR08 |  | 90 | 2020-08-12 | 2020-11-14 |  | 100%
CN-MPR-CS-1330-1 | Lean Concrete EW-PR08 | 7 | 2020-08-12 | 2020-08-13 | m3/м3 | 100% | 2 | m3/м3
CN-MPR-CS-1330 | Foundation - Rack Module - EW-PR08 | 23 | 2020-08-18 | 2020-10-13 | m3/м3 | 100% | 52 | m3/м3
CN-MPR-CS-1124 | Primary Structural Steel - Main Pipe Rack - EW-PR08 | 18 | 2020-11-10 | 2020-11-14 | tons/тн | 100% | 20.22 | tons/тн
RackModule-EW-PR07 |  | 112 | 2020-08-15 | 2020-11-12 |  | 100%
CN-MPR-CS-1320-1 | Lean Concrete EW-PR07 | 7 | 2020-08-15 | 2020-08-16 | m3/м3 | 100% | 3 | m3/м3
CN-MPR-CS-1320 | Foundation - Rack Module - EW-PR07 | 23 | 2020-08-21 | 2020-10-19 | m3/м3 | 100% | 79 | m3/м3
CN-MPR-CS-1123 | Primary Structural Steel - Main Pipe Rack - EW-PR07 | 25 | 2020-11-04 | 2020-11-12 | tons/тн | 100% | 32.44 | tons/тн
RackModule-EW-PR06 |  | 117 | 2020-08-25 | 2020-12-02 |  | 100%
CN-MPR-CS-1290-1 | Lean Concrete EW-PR06 | 7 | 2020-08-25 | 2020-08-27 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1290 | Foundation - Rack Module - EW-PR06 | 23 | 2020-08-28 | 2020-10-21 | m3/м3 | 100% | 83 | m3/м3
CN-MPR-CS-1121 | Primary Structural Steel - Main Pipe Rack - EW-PR06 | 30 | 2020-11-26 | 2020-12-02 | tons/тн | 100% | 28.39 | tons/тн
RackModule-EW-PR05 |  | 156 | 2020-08-27 | 2021-06-04 |  | 92.45%
CN-MPR-CS-1280-1 | Lean Concrete EW-PR05 | 7 | 2020-08-27 | 2020-09-25 | m3/м3 | 100% | 3 | m3/м3
CN-MPR-CS-1280 | Foundation - Rack Module - EW-PR05 | 33 | 2020-09-06 | 2020-10-19 | m3/м3 | 100% | 62.43 | m3/м3
CN-MPR-CS-1120 | Primary Structural Steel - Main Pipe Rack - EW-PR05 | 6 | 2021-01-10 | 2021-06-04 | tons/тн | 82% | 34.75 | tons/тн
RackModule-EW-PR04 |  | 190 | 2020-09-08 | 2021-03-26 |  | 100%
CN-MPR-CS-1270-1 | Lean Concrete EW-PR04 | 10 | 2020-09-08 | 2020-09-27 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1270 | Foundation - Rack Module - EW-PR04 | 38 | 2020-09-25 | 2021-01-05 | m3/м3 | 100% | 114 | m3/м3
CN-MPR-CS-1084 | Primary Structural Steel - Main Pipe Rack - EW-PR04 | 25 | 2021-02-13 | 2021-03-26 | tons/тн | 100% | 31 | tons/тн
RackModule-EW-PR03 |  | 90 | 2020-09-06 | 2021-03-25 |  | 100%
CN-MPR-CS-1250-1 | Lean Concrete EW-PR03 | 7 | 2020-09-06 | 2020-09-08 | m3/м3 | 100% | 2 | m3/м3
CN-MPR-CS-1250 | Foundation - Rack Module - EW-PR03 | 23 | 2020-09-21 | 2020-11-25 | m3/м3 | 100% | 43 | m3/м3
CN-MPR-CS-1082 | Primary Structural Steel - Main Pipe Rack - EW-PR03 | 22 | 2020-12-03 | 2021-03-25 | tons/тн | 100% | 31.78 | tons/тн
RackModule-EW-LS01 |  | 223 | 2020-09-23 | 2021-03-18 |  | 100%
CN-MPR-CS-1260-1 | Lean Concrete EW-LS01 | 7 | 2020-09-23 | 2020-09-25 | m3/м3 | 100% | 4 | m3/м3
CN-MPR-CS-1260 | Foundation - Rack Module - EW-LS01 | 42 | 2020-09-29 | 2020-12-31 | m3/м3 | 100% | 96 | m3/м3
CN-MPR-CS-1083 | Primary Structural Steel - Main Pipe Rack - EW-LS01 | 30 | 2021-03-13 | 2021-03-18 | tons/тн | 100% | 26.66 | tons/тн
RackModule-EW-PR02 |  | 146 | 2020-09-05 | 2021-01-26 |  | 100%
CN-MPR-CS-1240-1 | Lean Concrete EW-PR02 | 6 | 2020-09-05 | 2020-10-07 | m3/м3 | 100% | 3 | m3/м3
CN-MPR-CS-1240 | Foundation - Rack Module - EW-PR02 | 23 | 2020-09-18 | 2020-12-24 | m3/м3 | 100% | 63 | m3/м3
CN-MPR-CS-1081 | Primary Structural Steel - Main Pipe Rack - EW-PR02 | 20 | 2021-01-15 | 2021-01-26 | tons/тн | 100% | 26.33 | tons/тн
RackModule-EW-PR01 |  | 289 | 2020-09-16 | 2021-07-23 |  | 80.43%
CN-MPR-CS-1230-1 | Lean Concrete EW-PR01 | 7 | 2020-09-16 | 2020-09-18 | m3/м3 | 100% | 11.41 | m3/м3
CN-MPR-CS-1230 | Foundation - Rack Module - EW-PR01 | 21 | 2020-09-25 | 2020-12-19 | m3/м3 | 100% | 137 | m3/м3
CN-MPR-CS-1080 | Primary Structural Steel - Main Pipe Rack - EW-PR01 | 30 | 2021-04-20 | 2021-07-23 | tons/тн | 38% | 35.54 | tons/тн
Misc.Foundations |  | 20 | 2021-07-24 | 2021-08-12 |  | 0%
CN-MPR-CS-1980 | Structural Support - EW-PR | 4 | 2021-07-24 | 2021-07-27 | tons/тн | 0% | 10.2 | tons/тн
CN-MPR-CS-1970 | Misc Structural Steel - EW-PR | 4 | 2021-08-09 | 2021-08-12 | m/м | 0% | 23.64 | m/м
Piping |  | 516 | 2020-08-30 | 2022-02-22 |  | 7.69%
CN-MPR-PI-1110 | Pipe Support Fabrication - EW-PR | 50 | 2020-08-30 | 2021-01-22 | tons/тн | 100% | 19 | tons/тн
CN-MPR-PI-1100 | Piping Erection - EW-PR | 120 | 2021-05-26 | 2021-11-14 | DI | 6.9% | 19 | tons/тн
CN-MPR-PI-1110-1 | Pipe Support Installation - EW-PR | 113 | 2021-07-08 | 2021-10-28 | tons/тн | 0% | 4397 | DI
CN-MPR-PI-1040-1 | Piping Testing (RT, PWHT) - EW-PR | 120 | 2021-07-23 | 2021-11-19 | Стык/Jo | 0% | 381 | Стык/Jo
CN-MPR-PI-1040 | Piping Testing (Hydrotest, Flushing, Blowing,...) - EW-PR | 67 | 2021-10-14 | 2021-12-19 | Стык/Jo | 0% | 1 | Стык/Jo
CN-MPR-PI-1060 | Piping Painting - EW-PR | 60 | 2021-11-10 | 2022-01-08 | m2/м2 | 0% | 104 | m2/м2
CN-MPR-PI-1080-1 | Piping Insulation - EW-PR | 60 | 2021-12-25 | 2022-02-22 | m/м | 0% | 2692 | m/м
Electrical |  | 115 | 2021-09-26 | 2022-01-18 |  | 0%
CN-MPR-EL-1040 | Electrical Cable Trays - EW-PR | 80 | 2021-09-26 | 2021-12-14 | m/м | 0% | 1064.63 | m/м
CN-MPR-EL-1230-1 | Electrical Cable Pulling - EW-PR | 50 | 2021-10-11 | 2021-11-29 | m/м | 0% | 3059 | m/м
CN-MPR-EL-1240-2 | Electrical Junction Boxes - EW-PR | 45 | 2021-10-16 | 2021-11-29 | ea/шт | 0% | 15 | ea/шт
CN-MPR-EL-1020 | Electrical Cable Terminations - EW-PR | 46 | 2021-10-30 | 2021-12-14 | ea/шт | 0% | 391 | ea/шт
CN-MPR-EL-1250 | Electrical Equipment Installation - EW-PR | 30 | 2021-11-05 | 2021-12-04 | tons/тн | 0% | 2 | tons/тн
CN-MPR-EL-1020-1 | Lighting - EW-PR | 27 | 2021-11-13 | 2021-12-09 | m/м | 0% | 10 | m/м
CN-MPR-EL-1150 | Earthing & Lightening - EW-PR | 20 | 2021-12-05 | 2021-12-24 | ea/шт | 0% | 4 | ea/шт
CN-MPR-EL-1220 | Heat Tracing - EW-PR | 30 | 2021-12-20 | 2022-01-18 | m/м | 0% | 893 | m/м
Instrumentation |  | 130 | 2021-10-16 | 2022-02-22 |  | 0%
CN-MPR-IN-1040-1 | Instrument Cable Trays - EW-PR | 60 | 2021-10-16 | 2021-12-14 | m/м | 0% | 619 | m/м
CN-MPR-IN-1040-2 | Instrument Cable Pulling - EW-PR | 80 | 2021-11-05 | 2022-01-23 | m/м | 0% | 15730 | m/м
CN-MPR-IN-1060-1 | Instrument Junction Boxes - EW-PR | 10 | 2021-11-20 | 2021-11-29 | ea/шт | 0% | 1 | ea/шт
CN-MPR-IN-1030 | Field Instrument - EW-PR | 65 | 2021-11-30 | 2022-02-02 | ea/шт | 0% | 5 | ea/шт
CN-MPR-IN-1060 | Instrument Cable Terminations - EW-PR | 60 | 2021-12-15 | 2022-02-12 | ea/шт | 0% | 126 | ea/шт
CN-MPR-IN-1030-1 | F&G - EW-PR | 35 | 2022-01-19 | 2022-02-22 | ea/шт | 0% | 2 | ea/шт
Telecom |  | 10 | 2022-02-28 | 2022-03-09 |  | 0%
CN-MPR-TL-1110 | Telecom Equipment / Trays / JBs / Terminations - EW-PR | 10 | 2022-02-28 | 2022-03-09 | ea/шт | 0% | 36 | ea/шт
HSE |  | 5 | 2022-03-10 | 2022-03-14 |  | 0%
CN-MPR-HS-1130 | HSE Installation - EW-PR | 5 | 2022-03-10 | 2022-03-14 | ea/шт | 0% | 10 | ea/шт
BATTERYLIMITPLATFORM |  | 244 | 2020-08-30 | 2021-06-30 |  | 73.5%
SOUTH&NORTHTOWER |  | 244 | 2020-08-30 | 2021-06-30 |  | 73.5%
Civil |  | 242 | 2020-10-10 | 2021-06-29 |  | 84.86%
CN-BLS-CS-1090-C10-1 | Lean Concrete - South Tower | 7 | 2020-10-10 | 2020-12-25 | m3/м3 | 100% | 45 | m3/м3
CN-BLS-CS-1090-C10 | Foundation - South Tower | 70 | 2020-10-13 | 2020-12-31 | m3/м3 | 100% | 464 | m3/м3
CN-BLS-CS-1120-C10 | Backfilling - South Tower | 52 | 2020-12-21 | 2021-05-20 | m3/м3 | 100% | 2500 | m3/м3
CN-BLS-CS-1060 | Primary Structural Steel - South Tower | 86 | 2020-12-29 | 2021-04-28 | tons/тн | 100% | 255.6 | tons/тн
CN-BLS-CS-1070-1 | Gratings/ Stair Treads - South Tower | 20 | 2021-02-22 | 2021-04-26 | m2/м2 | 100% | 729.6 | m2/м2
CN-BLS-CS-1070 | Misc Structural Steel - South Tower | 20 | 2021-03-05 | 2021-03-31 | m/м | 100% | 450.82 | m/м
CN-BLS-CS-1040 | EIT Supports - South Tower | 25 | 2021-03-05 | 2021-04-26 | tons/тн | 100% | 1 | tons/тн
CN-BLS-CS-1040-1 | Structural Supports / Interconnection - North Tower | 25 | 2021-03-05 | 2021-05-16 | tons/тн | 100% | 12.14 | tons/тн
CN-BLS-CS-1062 | Structural Steel GMP / Crossovers - South Tower | 4 | 2021-03-19 | 2021-03-25 | tons/тн | 100% | 2.62 | tons/тн
CN-CMN-CS-1020-7-1 | Paving (Grade Slab) - North Tower | 28 | 2021-04-02 | 2021-04-26 | m2/м2 | 100% | 518 | m2/м2
CN-BLS-CS-1080 | Building Cladding - South Tower | 10 | 2021-05-17 | 2021-06-13 | m2/м2 | 78.63% | 136.11 | m/м
CN-BLS-CS-1061-C12 | Fire Proofing - North Tower | 26 | 2021-05-25 | 2021-06-29 | m2/м2 | 28.36% | 252 | m2/м2
CN-CMN-CS-1020-81 | Rectangular Open Drain - North Tower | 24 | 2021-06-05 | 2021-06-28 | m/м | 0% | 208 | m2/м2
Piping |  | 195 | 2020-08-30 | 2021-06-30 |  | 76.59%
CN-BLS-PI-1070 | Pipe Support Fabrication - South & North Tower | 30 | 2020-08-30 | 2021-01-22 | tons/тн | 100% | 5 | tons/тн
CN-BLS-PI-1000 | Piping Erection - South & North Tower | 108 | 2020-12-07 | 2021-06-09 | DI | 99% | 2371 | DI
CN-BLS-PI-1010-1 | Piping Testing (RT, PWHT) - South & North Tower | 55 | 2020-12-26 | 2021-06-17 | Стык/Jo | 94% | 244 | Стык/Jo
CN-BLS-PI-1070-1 | Pipe Support Installation - South & North Tower | 62 | 2021-01-14 | 2021-05-21 | tons/тн | 100% | 5 | tons/тн
CN-BLS-PI-1060 | Piping Erection - Gas Return Spools | 86 | 2021-01-17 | 2021-06-08 | DI | 91.2% | 144 | DI
CN-BLS-PI-1010-11 | Piping Testing (RT, PWHT) - Gas Return Spools | 15 | 2021-04-08 | 2021-06-17 | Стык/Jo | 85% | 10 | Стык/Jo
CN-BLS-PI-1030-1 | Piping Painting - South & North Tower | 33 | 2021-04-22 | 2021-06-22 | m2/м2 | 45% | 1 | Стык/Jo
CN-BLS-PI-1030-11 | Piping Painting - Gas Return Spools | 20 | 2021-04-22 | 2021-06-22 | m2/м2 | 45% | 1 | Стык/Jo
CN-BLS-PI-1010 | Piping Testing (Hydrotest, Flushing, Blowing,...) - South & North Tower | 45 | 2021-04-23 | 2021-06-15 | Стык/Jo | 60% | 47 | m2/м2
CN-BLS-PI-1010-12 | Piping Testing (Hydrotest, Flushing, Blowing,...) - Gas Return Spools | 16 | 2021-04-23 | 2021-06-15 | Стык/Jo | 30% | 67 | m2/м2
CN-BLS-PI-1030 | Piping Insulation - South & North Tower | 26 | 2021-06-05 | 2021-06-30 | m/м | 0% | 1130 | m/м
CN-BLS-PI-1130-12 | Piping Insulation - Gas Return Spools | 20 | 2021-06-10 | 2021-06-29 | m/м | 0% | 33 | m/м
Electrical |  | 81 | 2021-04-02 | 2021-06-25 |  | 31.36%
CN-BLS-EL-1010 | Electrical Cable Trays - South & North Tower | 12 | 2021-04-02 | 2021-06-05 | m/м | 86% | 642.99 | m/м
CN-BLS-EL-1330 | Electrical Cable Pulling - South & North Tower | 17 | 2021-05-07 | 2021-06-13 | m/м | 37% | 1500 | m/м
CN-BLS-EL-1030-1 | Electrical Equipment Installation - South & North Tower | 7 | 2021-05-25 | 2021-05-27 | ea/шт | 100% | 12 | ea/шт
CN-BLS-EL-1040 | Lighting - South & North Tower | 15 | 2021-05-25 | 2021-06-18 | ea/шт | 65.02% | 18 | ea/шт
CN-BLS-EL-1000 | Electrical Junction Boxes - South & North Tower | 5 | 2021-06-02 | 2021-06-08 | ea/шт | 66.67% | 7878 | m/м
CN-BLS-EL-1120 | Heat Tracing - South & North Tower | 21 | 2021-06-05 | 2021-06-25 | m/м | 0% | 524 | ea/шт
CN-BLS-EL-1020-2 | Earthing & Lightening - South & North Tower | 17 | 2021-06-06 | 2021-06-22 | ea/шт | 0% | 5 | ea/шт
CN-BLS-EL-1030 | Electrical Cable Terminations - South & North Tower | 6 | 2021-06-06 | 2021-06-11 | ea/шт | 0% | 59 | ea/шт
Instrumentation |  | 72 | 2021-04-02 | 2021-06-18 |  | 28.89%
CN-BLS-IN-1010 | Instrument Cable Trays - South & North Tower | 10 | 2021-04-02 | 2021-05-06 | m/м | 100% | 124 | m/м
CN-BLS-IN-1220 | Instrument Cable Pulling - South & North Tower | 8 | 2021-05-15 | 2021-05-20 | m/м | 100% | 27 | ea/шт
CN-BLS-IN-1000 | Instrument Junction Boxes - South & North Tower | 6 | 2021-05-16 | 2021-05-20 | ea/шт | 100% | 2910 | m/м
CN-BLS-IN-1040 | Instrument Cable Terminations - South & North Tower | 5 | 2021-05-26 | 2021-06-08 | ea/шт | 75% | 25 | ea/шт
CN-BLS-IN-1020 | Field Instrument - South & North Tower | 5 | 2021-06-09 | 2021-06-13 | ea/шт | 0% | 144 | ea/шт
CN-BLS-IN-1030 | F&G - South & North Tower | 5 | 2021-06-14 | 2021-06-18 | ea/шт | 0% | 27 | ea/шт
Telecom |  | 26 | 2021-06-05 | 2021-06-30 |  | 0%
CN-BLS-TL-1000 | Telecom Equipment / Trays / JBs / Terminations - South & North Tower | 26 | 2021-06-05 | 2021-06-30 | ea/шт | 0% | 22 | ea/шт
HSE |  | 25 | 2021-06-06 | 2021-06-30 |  | 0%
CN-BLS-HS-1110 | HSE Installation - South & North Tower | 25 | 2021-06-06 | 2021-06-30 | ea/шт | 0% | 22 | ea/шт