## FOUNDATIONS U
MAIN CONCRETE [m3]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 3135.2534 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.3 | 535 | 249 | 665 | 726 | 296.4007 | 294.8527 | 317.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 20369.0788 |  | 0 | 0 | 0 | 40.09 | 1003 | 1959 | 3030 | 3004 | 2798 | 2804 | 1646 | 1497 | 709.8823 | 827.1065 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 2024.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 1005.8 | 611.7 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 10271.9362 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 1473.5 | 1701.9188 | 1564.6433 | 1403.5408 | 1438.1958 | 941.4365 | 329.8704 | 553.2492 | 26.6229 | 2.1552 | 3.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 35800.7683 |  | 0 | 0 | 0 | 40.09 | 1003 | 1959 | 3030 | 3055.3 | 3333 | 3053 | 2311 | 2223 | 2153.283 | 3601.2591 | 3682.3188 | 1657.6433 | 1403.5408 | 1438.1958 | 941.4365 | 329.8704 | 553.2492 | 26.6229 | 2.1552 | 3.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 40.09 | 1043.09 | 3002.09 | 6032.09 | 9087.39 | 12420.39 | 15473.39 | 17784.39 | 20007.39 | 22160.673 | 25761.9322 | 29444.2509 | 31101.8942 | 32505.435 | 33943.6309 | 34885.0673 | 35214.9377 | 35768.187 | 35794.8099 | 35796.9651 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683 | 35800.7683
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Sheet12 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01
KEY QT: FD FOUNDATION |  |  | 21.04.21 A | 2022-12-29 | 26669.6 | 26669.7 | 13440.9 | 13228.8 | 49.6% | 13440.9 | At Completion Units | 37.4 | 281.6 | 1366.8 | 1411.8 | 992.2 | 1826.4 | 3258.2 | 2358.6 | 1695.8 | 3348.2 | 3193.3 | 3765.4 | 1531.8 | 688.7 | 440.1 | 260.2 | 147.4 | 21 | 1.7 | 3 | 40.2
Area Tag Kingisepp-2: 1 Ammonia |  |  | 26.08.21 A | 2022-04-20 | 3636 | 3636 | 2527 | 1109 | 30.5% | 2527 | At Completion Units | 2021-09-01: 57.8; 2021-10-01: 367.5; 2021-11-01: 359.9; 2021-12-01: 323.8; 2022-01-01: 1100.4; 2022-02-01: 877.5; 2022-03-01: 456.2; 2022-04-01: 93
Area Tag Kingisepp-2: 2 Urea |  |  | 21.04.21 A | 2022-12-29 | 23033.6 | 23033.7 | 10913.9 | 12119.8 | 52.62% | 10913.9 | At Completion Units | 37.4 | 281.6 | 1366.8 | 1411.8 | 992.2 | 1768.5 | 2890.7 | 1998.8 | 1372 | 2247.9 | 2315.8 | 3309.2 | 1438.8 | 688.7 | 440.1 | 260.2 | 147.4 | 21 | 1.7 | 3 | 40.2
KEY QT: EL ELEVATION |  |  | 23.06.21 A | 2023-02-01 | 6503.7 | 6531.7 | 6190.8 | 340.8 | 5.22% | 6190.8 | At Completion Units |  |  | 7.3 | 37.9 | 36.7 | 23 | 57.7 | 107 | 38.8 | 1255.1 | 1786 | 1396.1 | 457.1 | 603.5 | 302.5 |  | 289 |  |  |  |  | 106.9 | 27
Area Tag Kingisepp-2: 1 Ammonia |  |  | 25.10.21 A | 2022-03-30 | 396 | 396 | 367.9 | 28.1 | 7.09% | 367.9 | At Completion Units | 2021-10-01: 2.9; 2021-11-01: 12.4; 2021-12-01: 12.8; 2022-01-01: 84.1; 2022-02-01: 128.3; 2022-03-01: 155.5
Area Tag Kingisepp-2: 2 Urea |  |  | 23.06.21 A | 2023-02-01 | 6107.7 | 6135.7 | 5822.9 | 312.8 | 5.1% | 5822.9 | At Completion Units |  |  | 7.3 | 37.9 | 36.7 | 23 | 54.8 | 94.6 | 26 | 1171 | 1657.7 | 1240.5 | 457.1 | 603.5 | 302.5 |  | 289 |  |  |  |  | 106.9 | 27
[12 empty] | 0 | 0 | 0 | 0 | 0 | 57.8 | 370.4 | 372.3 | 336.6 | 1184.5 | 1005.8 | 611.7 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 37.4 | 281.6 | 1374.1 | 1449.7 | 1028.9 | 1791.5 | 2945.5 | 2093.4 | 1398 | 3418.9 | 3973.5 | 4549.7 | 1895.9 | 1292.2 | 742.6 | 260.2 | 436.4 | 21 | 1.7 | 3 | 40.2
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
KEY QT: ST MAIN STEEL STRUCTURE |  |  | 01.08.21 A | 2023-05-08 | 21632 | 21632 | 19478.6 | 2153.4 | 9.95% | 19478.6 | At Completion Units | 34 | 179.3 | 396.2 | 603.7 | 940.2 | 756.3 | 838.4 | 1664.9 | 2007.8 | 2176.9 | 2337.5 | 2140.7 | 2050.4 | 1743.6 | 1364.8 | 854.7 | 654.1 | 419.3 | 216.6 | 155 | 80.6 | 17
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2023-03-03 | 12602.7 | 12602.7 | 11186.7 | 1415.9 | 11.24% | 11186.7 | At Completion Units |  | 7.8 | 220.7 | 453.8 | 733.7 | 498.7 | 573.8 | 1055.8 | 1261.7 | 1522.9 | 1503.9 | 1287.2 | 1128 | 905.1 | 676.6 | 345.7 | 239.6 | 137.8 | 49.6 | 0.4
Area Tag Kingisepp-2: 2 Urea |  |  | 01.08.21 A | 2023-05-08 | 9029.3 | 9029.3 | 8291.9 | 737.5 | 8.17% | 8291.9 | At Completion Units | 34 | 171.5 | 175.5 | 150 | 206.6 | 257.6 | 264.6 | 609.1 | 746.1 | 654 | 833.6 | 853.5 | 922.4 | 838.5 | 688.2 | 509 | 414.5 | 281.5 | 167 | 154.7 | 80.6 | 17
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: LBP PIPING LB PREFAB |  |  | 22.10.21 A | 2023-01-04 | 318199.5 | 318199.5 | 314234.3 | 3965.2 | 1.25% | 314234.3 | At Completion Units | 542.2 | 1652.6 | 1770.5 | 33043.4 | 29890.6 | 33220.1 | 32075.6 | 33930.8 | 31381.3 | 29033.2 | 22370.2 | 21477.4 | 20761.5 | 14604.1 | 12444 | 2.1
Area Tag Kingisepp-2: 1 Ammonia |  |  | 22.10.21 A | 2023-01-04 | 215928.3 | 215928.3 | 211963.1 | 3965.2 | 1.84% | 211963.1 | At Completion Units | 542.2 | 1652.6 | 1770.5 | 23255.8 | 21050.3 | 23432.6 | 22676.7 | 24233.8 | 22477.9 | 20320.6 | 13657.6 | 13045.8 | 13120.9 | 7723.9 | 6964.9 | 2.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-01-01 | 2022-12-31 | 102271.2 | 102271.2 | 102271.2 | 0 | 0% | 102271.2 | At Completion Units | 2022-01-01: 9787.5; 2022-02-01: 8840.3; 2022-03-01: 9787.5; 2022-04-01: 9398.8; 2022-05-01: 9697.1; 2022-06-01: 8903.4; 2022-07-01: 8712.6; 2022-08-01: 8712.6; 2022-09-01: 8431.5; 2022-10-01: 7640.6; 2022-11-01: 6880.2; 2022-12-01: 5479.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-02-23 | 2023-07-07 | 259751 | 259751 | 259751 | 0 | 0% | 259751 | At Completion Units |  |  |  |  | 665.4 | 3437.8 | 3326.9 | 6368.7 | 9960.3 | 15446 | 24443.3 | 30674.7 | 33688.8 | 33046.1 | 28891 | 25273.1 | 19099.7 | 10750.1 | 7647.7 | 4798 | 1914.2 | 319.3
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-02-23 | 2023-04-16 | 180275 | 180275 | 180275 | 0 | 0% | 180275 | At Completion Units |  |  |  |  | 665.4 | 3437.8 | 3326.9 | 5427.9 | 7931.6 | 12791.9 | 19895.4 | 23230.6 | 24983 | 24035.4 | 20756.2 | 16782.1 | 12134.7 | 3481.7 | 1394.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-14 | 2023-07-07 | 79476 | 79476 | 79476 | 0 | 0% | 79476 | At Completion Units | [7 empty] | 940.8 | 2028.7 | 2654.1 | 4547.8 | 7444.1 | 8705.8 | 9010.6 | 8134.8 | 8491.1 | 6965 | 7268.4 | 6253.3 | 4798 | 1914.2 | 319.3
[12 empty] | 542.2 | 1652.6 | 1770.5 | 23255.8 | 21715.7 | 26870.4 | 26003.6 | 29661.7 | 30409.5 | 33112.5 | 33553 | 36276.4 | 38103.9 | 31759.3 | 27721.1 | 16784.2 | 12134.7 | 3481.7 | 1394.4 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 9787.5 | 8840.3 | 9787.5 | 9398.8 | 10637.9 | 10932.1 | 11366.7 | 13260.4 | 15875.6 | 16346.4 | 15890.8 | 13613.9 | 8491.1 | 6965 | 7268.4 | 6253.3 | 4798 | 1914.2 | 319.3
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: EC ELECTRICAL CABLES |  |  | 2022-05-18 | 2023-07-14 | 744840.9 | 744840.9 | 744840.9 | 0 | 0% | 744840.9 | At Completion Units | 3660.8 | 23340.6 | 69031.5 | 70740.8 | 74020.7 | 82199.5 | 82055.4 | 68926.6 | 70473.7 | 55158.5 | 43296.7 | 42222.5 | 33911 | 19883.7 | 5919.1
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-01 | 2023-06-02 | 441690.9 | 441690.9 | 441690.9 | 0 | 0% | 441690.9 | At Completion Units |  | 5706.8 | 33465 | 45552.6 | 64263.3 | 76030.2 | 71886.4 | 50273.9 | 35519 | 20273.8 | 13476.9 | 15729.1 | 8946.8 | 567.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-18 | 2023-07-14 | 303150 | 303150 | 303150 | 0 | 0% | 303150 | At Completion Units | 3660.8 | 17633.8 | 35566.5 | 25188.2 | 9757.3 | 6169.4 | 10169 | 18652.7 | 34954.7 | 34884.6 | 29819.8 | 26493.3 | 24964.2 | 19316.6 | 5919.1
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01
KEY QT: FD FOUNDATION |  |  | 21.04.21 A | 2022-12-29 | 26669.6 | 26669.7 | 13440.9 | 13228.8 | 49.6% | 13440.9 | At Completion Units | 37.4 | 281.6 | 1366.8 | 1411.8 | 992.2 | 1826.4 | 3258.2 | 2358.6 | 1695.8 | 3348.2 | 3193.3 | 3765.4 | 1531.8 | 688.7 | 440.1 | 260.2 | 147.4 | 21 | 1.7 | 3 | 40.2
KEY QT: EL ELEVATION |  |  | 23.06.21 A | 2023-02-01 | 6503.7 | 6531.7 | 6190.8 | 340.8 | 5.22% | 6190.8 | At Completion Units |  |  | 7.3 | 37.9 | 36.7 | 23 | 57.7 | 107 | 38.8 | 1255.1 | 1786 | 1396.1 | 457.1 | 603.5 | 302.5 |  | 289 |  |  |  |  | 106.9 | 27
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: IC INSTRUMENT CABLES |  |  | 2022-06-11 | 2023-07-27 | 1116824 | 1116824 | 1116824 | 0 | 0% | 1116824 | At Completion Units | 14414.6 | 43237.9 | 51068.5 | 45585 | 71123.1 | 68204.4 | 126925 | 148530.2 | 155319.4 | 182506.2 | 99850.7 | 61971.4 | 32994.7 | 15092.9
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-11 | 2023-06-02 | 746102.1 | 746102.1 | 746102.1 | 0 | 0% | 746102.1 | At Completion Units | 13877.2 | 37216.3 | 42374.9 | 33440.5 | 61260.1 | 62169 | 109264 | 112438.7 | 111187.2 | 111843.2 | 38764.4 | 11523.1 | 743.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-06-25 | 2023-07-27 | 370721.9 | 370721.9 | 370721.9 | 0 | 0% | 370721.9 | At Completion Units | 537.5 | 6021.6 | 8693.6 | 12144.5 | 9862.9 | 6035.4 | 17661 | 36091.4 | 44132.2 | 70663 | 61086.3 | 50448.3 | 32251.3 | 15092.9
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | At Completion Units | Staffed Remaining Units | Actual Units | Units % Complete | Remaining Units | Spreadsheet Field | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: IN INSULATION |  |  | 2022-05-29 | 2023-07-28 | 194256 | 194256 | 194256 | 0 | 0% | 194256 | At Completion Units | 3.2 | 46.9 | 174.6 | 3641.6 | 4711.2 | 6853.2 | 10406.6 | 11329.3 | 15632.1 | 28609.6 | 43058.8 | 34011.6 | 23871.3 | 9454.6 | 2451.7
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-05-29 | 2023-06-11 | 120839 | 120839 | 120839 | 0 | 0% | 120839 | At Completion Units | 3.2 | 46.9 | 28.7 | 3361.1 | 3759.5 | 4021.2 | 6925.8 | 8321 | 13314.9 | 21574.2 | 29275.2 | 17739.1 | 11290.5 | 1177.6
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-07-03 | 2023-07-28 | 73417 | 73417 | 73417 | 0 | 0% | 73417 | At Completion Units |  |  | 145.9 | 280.5 | 951.7 | 2831.9 | 3480.8 | 3008.3 | 2317.1 | 7035.4 | 13783.7 | 16272.4 | 12580.7 | 8277 | 2451.7

## Sheet1 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01
KEY QT: FD FOUNDATION |  |  | 21.04.21 A | 2023-01-09 |  | 349530.4 | 196468.1 | 56.21% | 403 |  | 153061.2 | Remaining Units | [8 empty] | 3244.3 | 40843.3 | 39536.7 | 37341 | 12355.2 | 9868.5 | 5221.1 | 1811.9 | 1591.2 | 504.3 | 66.3 | 68.6 | 188.7 | 420
Area Tag Kingisepp-2: 1 Ammonia |  |  | 26.08.21 A | 2022-04-19 |  | 16279.5 | 3127.9 | 19.21% | 138 |  | 13151.7 | Remaining Units | 2021-12-01: 406.4; 2022-01-01: 7389.6; 2022-02-01: 2559.7; 2022-03-01: 1320.9; 2022-04-01: 1475.1
Area Tag Kingisepp-2: 2 Urea |  |  | 21.04.21 A | 2023-01-09 |  | 333250.9 | 193340.3 | 58.02% | 375 |  | 139909.5 | Remaining Units | [8 empty] | 2838 | 33453.7 | 36977 | 36020 | 10880.2 | 9868.5 | 5221.1 | 1811.9 | 1591.2 | 504.3 | 66.3 | 68.6 | 188.7 | 420
KEY QT: EL ELEVATION |  |  | 23.06.21 A | 2023-01-15 |  | 88019.6 | 21218.7 | 24.11% | 409 |  | 66801 | Remaining Units | 2021-12-01: 1082.2; 2022-01-01: 23821.6; 2022-02-01: 16301.4; 2022-03-01: 16000.6; 2022-04-01: 3833; 2022-05-01: 4703.6; 2022-12-01: 221.7; 2023-01-01: 836.9
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2022-04-26 |  | 5965.2 | 1308.7 | 21.94% | 145 |  | 4656.5 | Remaining Units | 2021-12-01: 905.7; 2022-01-01: 2690.3; 2022-03-01: 693.8; 2022-04-01: 366.7
Area Tag Kingisepp-2: 2 Urea |  |  | 23.06.21 A | 2023-01-15 |  | 82054.4 | 19910 | 24.26% | 381 |  | 62144.4 | Remaining Units | 2021-12-01: 176.4; 2022-01-01: 21131.3; 2022-02-01: 16301.4; 2022-03-01: 15306.7; 2022-04-01: 3466.4; 2022-05-01: 4703.6; 2022-12-01: 221.7; 2023-01-01: 836.9
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01
KEY QT: FD FOUNDATION |  |  | 21.04.21 A | 2023-01-09 |  | 349530.4 | 196468.1 | 56.21% | 403 |  | 153061.2 | At Completion Units | 1635.6 | 7252.4 | 18421.4 | 26272.2 | 24365.3 | 22528.6 | 24967.7 | 25507.6 | 48761.6 | 40843.3 | 39536.7 | 37341 | 12355.2 | 9868.5 | 5221.1 | 1811.9 | 1591.2 | 504.3 | 66.3 | 68.6 | 188.7 | 420
Area Tag Kingisepp-2: 1 Ammonia |  |  | 26.08.21 A | 2022-04-19 |  | 16279.5 | 3127.9 | 19.21% | 138 |  | 13151.7 | At Completion Units | 2021-09-01: 166.4; 2021-10-01: 1031.5; 2021-11-01: 998.3; 2021-12-01: 1338.1; 2022-01-01: 7389.6; 2022-02-01: 2559.7; 2022-03-01: 1320.9; 2022-04-01: 1475.1
Area Tag Kingisepp-2: 2 Urea |  |  | 21.04.21 A | 2023-01-09 |  | 333250.9 | 193340.3 | 58.02% | 375 |  | 139909.5 | At Completion Units | 1635.6 | 7252.4 | 18421.4 | 26272.2 | 24365.3 | 22362.3 | 23936.2 | 24509.4 | 47423.5 | 33453.7 | 36977 | 36020 | 10880.2 | 9868.5 | 5221.1 | 1811.9 | 1591.2 | 504.3 | 66.3 | 68.6 | 188.7 | 420
KEY QT: EL ELEVATION |  |  | 23.06.21 A | 2023-01-15 |  | 88019.6 | 21218.7 | 24.11% | 409 |  | 66801 | At Completion Units |  |  | 13.3 | 68.6 | 68.6 | 3554 | 5567.8 | 5585.5 | 7443 | 23821.6 | 16301.4 | 16000.6 | 3833 | 4703.6 | [6 empty] | 221.7 | 836.9
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2022-04-26 |  | 5965.2 | 1308.7 | 21.94% | 145 |  | 4656.5 | At Completion Units | 2021-09-01: 80.9; 2021-10-01: 314.1; 2021-11-01: 333.4; 2021-12-01: 1486; 2022-01-01: 2690.3; 2022-03-01: 693.8; 2022-04-01: 366.7
Area Tag Kingisepp-2: 2 Urea |  |  | 23.06.21 A | 2023-01-15 |  | 82054.4 | 19910 | 24.26% | 381 |  | 62144.4 | At Completion Units |  |  | 13.3 | 68.6 | 68.6 | 3473.1 | 5253.7 | 5252.1 | 5957 | 21131.3 | 16301.4 | 15306.7 | 3466.4 | 4703.6 | [6 empty] | 221.7 | 836.9
0
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01
KEY QT: FD FOUNDATION |  |  | 21.04.21 A | 2023-01-17 |  | 26669.6 | 15322.9 | 57.45% | 411 |  | 11346.7 | At Completion Units | 49.5 | 340.6 | 1457.1 | 2025.9 | 1948.2 | 1969 | 2641.9 | 2365.1 | 2637.1 | 3518.3 | 2588.9 | 2619.6 | 1107.4 | 655.5 | 363.5 | 189 | 118.2 | 29.4 | 1.6 | 2.8 | 6.3 | 34.9
Area Tag Kingisepp-2: 1 Ammonia |  |  | 26.08.21 A | 2022-04-19 |  | 3636 | 1162 | 31.96% | 138 |  | 2474 | At Completion Units | 2021-09-01: 57.8; 2021-10-01: 358.5; 2021-11-01: 346.9; 2021-12-01: 442.9; 2022-01-01: 1079.2; 2022-02-01: 922.8; 2022-03-01: 334.9; 2022-04-01: 93
Area Tag Kingisepp-2: 2 Urea |  |  | 21.04.21 A | 2023-01-17 |  | 23033.6 | 14160.9 | 61.48% | 383 |  | 8872.7 | At Completion Units | 49.5 | 340.6 | 1457.1 | 2025.9 | 1948.2 | 1911.2 | 2283.4 | 2018.2 | 2194.2 | 2439.1 | 1666.1 | 2284.6 | 1014.4 | 655.5 | 363.5 | 189 | 118.2 | 29.4 | 1.6 | 2.8 | 6.3 | 34.9
KEY QT: EL ELEVATION |  |  | 23.06.21 A | 2023-01-06 |  | 6503.7 | 1441.4 | 22.16% | 400 |  | 5062.2 | At Completion Units | 2021-06-01: 2.6; 2021-07-01: 13.4; 2021-08-01: 13.4; 2021-09-01: 245.2; 2021-10-01: 371; 2021-11-01: 373.9; 2021-12-01: 444.6; 2022-01-01: 1643.9; 2022-02-01: 1772.8; 2022-03-01: 1298.1; 2022-04-01: 190.8; 2022-12-01: 52.9; 2023-01-01: 81
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2022-04-19 |  | 396 | 0.8 | 0.2% | 138 |  | 395.2 | At Completion Units | 2021-10-01: 0.1; 2021-11-01: 0.4; 2021-12-01: 14.9; 2022-01-01: 248.7; 2022-02-01: 55; 2022-03-01: 77
Area Tag Kingisepp-2: 2 Urea |  |  | 23.06.21 A | 2023-01-06 |  | 6107.7 | 1440.6 | 23.59% | 372 |  | 4667 | At Completion Units | 2021-06-01: 2.6; 2021-07-01: 13.4; 2021-08-01: 13.4; 2021-09-01: 245.2; 2021-10-01: 370.9; 2021-11-01: 373.6; 2021-12-01: 429.7; 2022-01-01: 1395.2; 2022-02-01: 1717.8; 2022-03-01: 1221.1; 2022-04-01: 190.8; 2022-12-01: 52.9; 2023-01-01: 81
[13 empty] | 0 | 0 | 0 | 0 | 0 | 57.8 | 358.6 | 347.3 | 457.8 | 1327.9 | 977.8 | 411.9 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 49.5 | 340.6 | 1459.7 | 2039.3 | 1961.6 | 2156.4 | 2654.3 | 2391.8 | 2623.9 | 3834.3 | 3383.9 | 3505.7 | 1205.2 | 655.5 | 363.5 | 189 | 118.2 | 29.4 | 1.6 | 2.8 | 59.2 | 115.9
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2023-03-03 |  | 10728.3 | 1225.4 | 11.42% | 428 |  | 9502.9 | At Completion Units |  | 8.9 | 197.5 | 397.1 | 749 | 446.1 | 729 | 1083.3 | 1251.9 | 1232.9 | 1040.7 | 885.3 | 781.5 | 671.3 | 583.3 | 302.9 | 201.9 | 121.1 | 44.3 | 0.3
Area Tag Kingisepp-2: 2 Urea |  |  | 01.08.21 A | 2023-05-12 |  | 7686 | 737.7 | 9.6% | 498 |  | 6948.3 | At Completion Units | 29 | 146 | 186.8 | 164 | 214.9 | 102.4 | 280.1 | 553.8 | 694.7 | 767.1 | 834.9 | 745.6 | 696 | 603 | 489.7 | 338.8 | 280.7 | 222.2 | 130.8 | 108.1 | 75.9 | 21.7
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-01-11 | 2023-03-22 |  | 535 | 0 | 0% | 436 |  | 535 | At Completion Units |  | 8.1 | 22.6 | 63.3 | 33.3 | 25.8 | 25.9 | 60 | 188.3 | 68.5 | 12.9 | 15.7 | 6.1 | 3.4 | 1.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2021-12-31 | 2023-06-21 |  | 3239.4 | 0 | 0% | 538 |  | 3239.4 | At Completion Units | 16.6 | 512.3 | 456.9 | 539.7 | 526.1 | 536.9 | 267.6 | 191.8 | 90.8 | 39.6 | 33.5 | 5 | 13 | 2.4 | 0.1 | 0.5 | 4 | 2.5
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
Area Tag Kingisepp-2: 1 Ammonia |  |  | 20.11.21 A | 2023-03-23 |  | 940632.4 | 27265.3 | 2.9% | 476 |  | 913367.1 | At Completion Units | 7315.1 | 29038.6 | 28855.7 | 35556.7 | 69513.3 | 80605.6 | 101537.4 | 128450.8 | 127473.6 | 190430.6 | 100412.7 | 22505.8 | 11545.8 | 3108.1 | 2724.8 | 1416.1 | 141.6
Area Tag Kingisepp-2: 2 Urea |  |  | 2021-12-31 | 2023-06-22 |  | 407054.8 | 0 | 0% | 539 |  | 407054.8 | At Completion Units |  | 434.7 | 13346 | 12053.8 | 36683.4 | 53564.8 | 65800 | 46841.4 | 56457.4 | 30143.5 | 21402.5 | 17272.4 | 13057.7 | 13546.3 | 7856.8 | 3298.8 | 699.2 | 3482.1 | 7163 | 3951.3
[13 empty] | 132.0226 | 524.0873 | 520.7863 | 641.7257 | 1254.5728 | 1454.7661 | 1832.5423 | 2318.2741 | 2300.6376 | 3436.8827 | 1812.2438 | 406.1836 | 208.3781 | 56.0948 | 49.1771 | 25.5577 | 2.5556 | 0 | 0 | 0
[13 empty] | 0 | 7.8454 | 240.868 | 217.5464 | 662.0603 | 966.735 | 1187.5554 | 845.3914 | 1018.9405 | 544.0285 | 386.2713 | 311.7315 | 235.6648 | 244.483 | 141.7992 | 59.5366 | 12.6191 | 62.8448 | 129.2775 | 71.3129
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
KEY QT: SB PIPING SB |  |  | 2022-03-28 | 2023-08-01 |  | 90194.1 | 0 | 0% | 492 |  | 90194.1 | At Completion Units | [5 empty] | 200.6 | 1712.5 | 2022.4 | 2713.6 | 3929 | 5184.9 | 7637.3 | 8981.7 | 10370.9 | 10729.5 | 9876.4 | 8528.8 | 6344.1 | 5157.1 | 4645.6 | 1199.5 | 930.2 | 30
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-03-28 | 2023-05-25 |  | 62394.5 | 0 | 0% | 424 |  | 62394.5 | At Completion Units | [5 empty] | 200.6 | 1712.5 | 2022.4 | 2677.9 | 3488.3 | 4518.3 | 7006.8 | 8305.9 | 8280.8 | 7546.4 | 6404.6 | 5274.7 | 2313.8 | 1492.7 | 1148.9
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-06-18 | 2023-08-01 |  | 27799.5 | 0 | 0% | 410 |  | 27799.5 | At Completion Units | [8 empty] | 35.7 | 440.7 | 666.6 | 630.5 | 675.7 | 2090.1 | 3183 | 3471.8 | 3254.1 | 4030.3 | 3664.5 | 3496.8 | 1199.5 | 930.2 | 30
KEY QT: LBP PIPING LB PREFAB |  |  | 22.10.21 A | 2023-01-04 |  | 318199.5 | 3787 | 1.19% | 439 |  | 314412.5 | At Completion Units | 541 | 1623 | 2688.7 | 33229.2 | 30814.8 | 34214.4 | 33034.8 | 34058.1 | 31295.3 | 28103.9 | 21191.6 | 20451.7 | 20065.4 | 14475.4 | 12410 | 2.1
Area Tag Kingisepp-2: 1 Ammonia |  |  | 22.10.21 A | 2023-01-04 |  | 215928.3 | 3787 | 1.75% | 439 |  | 212141.3 | At Completion Units | 541 | 1623 | 2373.8 | 23467.4 | 21997.7 | 24452.6 | 23663.9 | 24386.9 | 22446.9 | 19416.9 | 12504.5 | 12044.8 | 12446.3 | 7614.5 | 6945.9 | 2.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2021-12-31 | 2022-12-31 |  | 102271.2 | 0 | 0% | 366 |  | 102271.2 | At Completion Units | 2021-12-01: 314.9; 2022-01-01: 9761.7; 2022-02-01: 8817.1; 2022-03-01: 9761.7; 2022-04-01: 9371; 2022-05-01: 9671.3; 2022-06-01: 8848.4; 2022-07-01: 8687.1; 2022-08-01: 8687.1; 2022-09-01: 8406.9; 2022-10-01: 7619; 2022-11-01: 6861; 2022-12-01: 5464.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-02-22 | 2023-07-17 |  | 259751 | 0 | 0% | 511 |  | 259751 | At Completion Units |  |  |  |  | 776.3 | 3784.8 | 3905.2 | 7352.1 | 11312.3 | 14570.9 | 22647.7 | 30369.2 | 32696 | 30400.5 | 25835.4 | 25155.5 | 19654 | 14732.1 | 8984.3 | 4885.2 | 1914.2 | 775.4
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-02-22 | 2023-05-01 |  | 180275 | 0 | 0% | 434 |  | 180275 | At Completion Units |  |  |  |  | 776.3 | 3784.8 | 3905.2 | 6583.9 | 9522.7 | 11809 | 18359.6 | 23256.5 | 24230.7 | 21297.2 | 17580.2 | 16544 | 12580.2 | 7343.3 | 2614.5 | 87.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-14 | 2023-07-17 |  | 79476 | 0 | 0% | 430 |  | 79476 | At Completion Units | [7 empty] | 768.2 | 1789.6 | 2761.9 | 4288.1 | 7112.6 | 8465.3 | 9103.4 | 8255.3 | 8611.5 | 7073.8 | 7388.8 | 6369.9 | 4798 | 1914.2 | 775.4
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
KEY QT: SB PIPING SB |  |  | 2022-06-18 | 2023-08-01 |  | 27799.5 | 0 | 0% | 410 |  | 27799.5 | At Completion Units | [6 empty] | 35.7 | 440.7 | 666.6 | 630.5 | 675.7 | 2090.1 | 3183 | 3471.8 | 3254.1 | 4030.3 | 3664.5 | 3496.8 | 1199.5 | 930.2 | 30
KEY QT: LBP PIPING LB PREFAB |  |  | 2021-12-31 | 2022-12-31 |  | 102271.2 | 0 | 0% | 366 |  | 102271.2 | At Completion Units | 314.9 | 9761.7 | 8817.1 | 9761.7 | 9371 | 9671.3 | 8848.4 | 8687.1 | 8687.1 | 8406.9 | 7619 | 6861 | 5464.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-05-14 | 2023-07-17 |  | 79476 | 0 | 0% | 430 |  | 79476 | At Completion Units | [5 empty] | 768.2 | 1789.6 | 2761.9 | 4288.1 | 7112.6 | 8465.3 | 9103.4 | 8255.3 | 8611.5 | 7073.8 | 7388.8 | 6369.9 | 4798 | 1914.2 | 775.4
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
KEY QT: SB PIPING SB |  |  | 2022-03-28 | 2023-05-25 |  | 62394.5 | 0 | 0% | 424 |  | 62394.5 | At Completion Units | [5 empty] | 200.6 | 1712.5 | 2022.4 | 2677.9 | 3488.3 | 4518.3 | 7006.8 | 8305.9 | 8280.8 | 7546.4 | 6404.6 | 5274.7 | 2313.8 | 1492.7 | 1148.9
KEY QT: LBP PIPING LB PREFAB |  |  | 22.10.21 A | 2023-01-04 |  | 215928.3 | 3787 | 1.75% | 439 |  | 212141.3 | At Completion Units | 541 | 1623 | 2373.8 | 23467.4 | 21997.7 | 24452.6 | 23663.9 | 24386.9 | 22446.9 | 19416.9 | 12504.5 | 12044.8 | 12446.3 | 7614.5 | 6945.9 | 2.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-02-22 | 2023-05-01 |  | 180275 | 0 | 0% | 434 |  | 180275 | At Completion Units |  |  |  |  | 776.3 | 3784.8 | 3905.2 | 6583.9 | 9522.7 | 11809 | 18359.6 | 23256.5 | 24230.7 | 21297.2 | 17580.2 | 16544 | 12580.2 | 7343.3 | 2614.5 | 87.1

## PAVING (hidden)
PAVING [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0
Urea | 13232.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.1 | 229.7 | 430.6 | 962.5 | 1468.9 | 1529.5 | 1507.1 | 1781.3 | 1757.7 | 1192.9 | 598 | 332.6 | 449.3 | 667.7 | 149 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 13232.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.1 | 229.7 | 430.6 | 962.5 | 1468.9 | 1529.5 | 1507.1 | 1781.3 | 1757.7 | 1192.9 | 598 | 332.6 | 449.3 | 667.7 | 149 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.1 | 405.8 | 836.4 | 1798.9 | 3267.8 | 4797.3 | 6304.4 | 8085.7 | 9843.4 | 11036.3 | 11634.3 | 11966.9 | 12416.2 | 13083.9 | 13232.9 | 13232.9 | 13232.9 | 13232.9 | 13232.9 | 13232.9 | 13232.9
PAVING [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 78203.7 | 0.6812% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.745% | 4.46% | 4.71% | 7.089% | 8.132% | 9.745% | 9.21% | 9.912% | 10.43% | 10.35% | 8.006% | 5.396% | 3.27% | 5.404% | 1.146% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 78203.7 | 0.6812% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.745% | 4.46% | 4.71% | 7.089% | 8.132% | 9.745% | 9.21% | 9.912% | 10.43% | 10.35% | 8.006% | 5.396% | 3.27% | 5.404% | 1.146% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 78203.7 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.745% | 7.205% | 11.91% | 19% | 27.14% | 36.88% | 46.09% | 56% | 66.43% | 76.78% | 84.79% | 90.18% | 93.45% | 98.85% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## UG PRESSURE PIPING (hidden)
UG PRESSURE PIPING [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659.3 | 1052.2 | 2055.5 | 3683.3 | 4600.5 | 4517.6 | 5056.9 | 4497.4 | 3242.4 | 1688.5 | 854.6 | 91.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea | 17100 |  |  | 0 | 0 | 0 | 0 | 0 | 472 | 494.4 | 762.2 | 1346.5 | 1756.9 | 2022.7 | 2032.5 | 1876.1 | 1999.2 | 1674.8 | 1321.1 | 686 | 439.7 | 215.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 49100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 494.4 | 1421.5 | 2398.7 | 3812.4 | 5706 | 6633 | 6393.7 | 7056.1 | 6172.2 | 4563.5 | 2374.5 | 1294.3 | 307.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 966.4 | 2387.9 | 4786.6 | 8599 | 14305 | 20938 | 27331.7 | 34387.8 | 40560 | 45123.5 | 47498 | 48792.3 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100 | 49100
UG PRESSURE PIPING [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 23228.4 | 0.2023% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1975% | 1.426% | 3.049% | 4.894% | 7.649% | 8.255% | 9.175% | 7.247% | 3.901% | 2.785% | 1.077% | 0.1097% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 23446 | 0.2042% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4019% | 1.401% | 2.268% | 3.06% | 5.127% | 6.553% | 7.015% | 6.476% | 6.358% | 4.713% | 3.025% | 2.164% | 1.183% | 0.4881% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 46674.4 | 0.4066% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4019% | 1.401% | 2.465% | 4.486% | 8.176% | 11.45% | 14.66% | 14.73% | 15.53% | 11.96% | 6.926% | 4.95% | 2.259% | 0.5978% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 46674.4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.4019% | 1.803% | 4.268% | 8.754% | 16.93% | 28.38% | 43.04% | 57.77% | 73.31% | 85.27% | 92.19% | 97.14% | 99.4% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## UG GRAVITY PIPING (hidden)
UG GRAVITY PIPING [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0
Urea | 18213.6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 353.3 | 400.4 | 464.1 | 753.5 | 911 | 989.5 | 1320.9 | 1306.1 | 1375.1 | 1375.1 | 1375.1 | 1414.5 | 1272 | 1267.8 | 911 | 946.1 | 495 | 428.4 | 295.9 | 214.9 | 85.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 18213.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 353.3 | 400.4 | 464.1 | 753.5 | 911 | 989.5 | 1320.9 | 1306.1 | 1375.1 | 1375.1 | 1375.1 | 1414.5 | 1272 | 1267.8 | 911 | 946.1 | 495 | 428.4 | 295.9 | 214.9 | 85.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 611.3 | 1011.7 | 1475.8 | 2229.3 | 3140.3 | 4129.8 | 5450.7 | 6756.8 | 8131.9 | 9507 | 10882.1 | 12296.6 | 13568.6 | 14836.4 | 15747.4 | 16693.5 | 17188.5 | 17616.9 | 17912.8 | 18127.7 | 18213.6 | 18213.6 | 18213.6 | 18213.6 | 18213.6 | 18213.6 | 18213.6 | 18213.6
UG GRAVITY PIPING [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 17823.8 | 0.1553% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4573% | 0.8489% | 2.178% | 2.737% | 3.53% | 3.87% | 4.97% | 7.546% | 7.797% | 8.871% | 8.871% | 8.871% | 9.003% | 7.267% | 7.227% | 3.87% | 4.018% | 2.815% | 2.526% | 1.456% | 0.9072% | 0.363% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 17823.8 | 0.1553% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4573% | 0.8489% | 2.178% | 2.737% | 3.53% | 3.87% | 4.97% | 7.546% | 7.797% | 8.871% | 8.871% | 8.871% | 9.003% | 7.267% | 7.227% | 3.87% | 4.018% | 2.815% | 2.526% | 1.456% | 0.9072% | 0.363% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 17823.8 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4573% | 1.306% | 3.484% | 6.221% | 9.751% | 13.62% | 18.59% | 26.14% | 33.93% | 42.81% | 51.68% | 60.55% | 69.55% | 76.82% | 84.04% | 87.91% | 91.93% | 94.75% | 97.27% | 98.73% | 99.64% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## STEEL U
STEEL [t]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 1926.004 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.121 | 363.024 | 522.472 | 333.29 | 283.2653 | 233.8317 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 1217.1142 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.323 | 31.085 | 351.037 | 158.084 | 131.745 | 183.596 | 126.857 | 97.3872 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 11186.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498.7 | 545.9 | 1027.9 | 1289.6 | 1550.8 | 1503.9 | 1287.2 | 1128 | 905.1 | 676.6 | 345.7 | 239.6 | 137.8 | 49.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 8291.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 248.3 | 518 | 705.5 | 649.9 | 603.5 | 827.1 | 913.1 | 832 | 699.6 | 559.5 | 492 | 379.9 | 233 | 175.6 | 145.6 | 72.1 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 22621.8182 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.323 | 31.085 | 379.158 | 521.108 | 654.217 | 516.886 | 1141.8223 | 1125.4189 | 1843.9 | 1995.1 | 2200.7 | 2107.4 | 2114.3 | 2041.1 | 1737.1 | 1376.2 | 905.2 | 731.6 | 517.7 | 282.6 | 176 | 145.6 | 72.1 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.323 | 32.408 | 411.566 | 932.674 | 1586.891 | 2103.777 | 3245.5993 | 4371.0182 | 6214.9182 | 8210.0182 | 10410.7182 | 12518.1182 | 14632.4182 | 16673.5182 | 18410.6182 | 19786.8182 | 20692.0182 | 21423.6182 | 21941.3182 | 22223.9182 | 22399.9182 | 22545.5182 | 22617.6182 | 22621.8182 | 22621.8182 | 22621.8182 | 22621.8182 | 22621.8182 | 22621.8182 | 22621.8182
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Sheet6 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | At Completion Units | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
KEY QT: ST MAIN STEEL STRUCTURE |  |  | 01.08.21 A | 2023-06-02 |  | 21632 | At Completion Units | 34 | 179.3 | 396.2 | 603.7 | 940.2 | 731.6 | 794.2 | 1546 | 1995.1 | 2200.7 | 2107.3 | 2114.3 | 2041.1 | 1737.1 | 1376.2 | 905.2 | 731.6 | 517.7 | 282.6 | 176 | 145.6 | 72.1 | 4.2
Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2023-03-03 |  | 12602.7 | At Completion Units |  | 7.8 | 220.7 | 453.8 | 733.7 | 498.7 | 545.9 | 1027.9 | 1289.6 | 1550.8 | 1503.9 | 1287.2 | 1128 | 905.1 | 676.6 | 345.7 | 239.6 | 137.8 | 49.6 | 0.4
Area Tag Kingisepp-2: 2 Urea |  |  | 01.08.21 A | 2023-06-02 |  | 9029.3 | At Completion Units | 34 | 171.5 | 175.5 | 150 | 206.6 | 233 | 248.3 | 518 | 705.5 | 649.9 | 603.5 | 827.1 | 913.1 | 832 | 699.6 | 559.5 | 492 | 379.9 | 233 | 175.6 | 145.6 | 72.1 | 4.2
KEY QT: LBP PIPING LB PREFAB |  |  | 22.10.21 A | 2023-01-04 |  | 318199.5 | At Completion Units |  |  | 542.2 | 1652.6 | 1770.5 | 33043.4 | 29890.6 | 33220.1 | 32075.6 | 33930.8 | 31381.3 | 29033.2 | 22370.2 | 21477.4 | 20761.5 | 14604.1 | 12444 | 2.1
Area Tag Kingisepp-2: 1 Ammonia |  |  | 22.10.21 A | 2023-01-04 |  | 215928.3 | At Completion Units |  |  | 542.2 | 1652.6 | 1770.5 | 23255.8 | 21050.3 | 23432.6 | 22676.7 | 24233.8 | 22477.9 | 20320.6 | 13657.6 | 13045.8 | 13120.9 | 7723.9 | 6964.9 | 2.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-01-01 | 2022-12-31 |  | 102271.2 | At Completion Units | 2022-01-01: 9787.5; 2022-02-01: 8840.3; 2022-03-01: 9787.5; 2022-04-01: 9398.8; 2022-05-01: 9697.1; 2022-06-01: 8903.4; 2022-07-01: 8712.6; 2022-08-01: 8712.6; 2022-09-01: 8431.5; 2022-10-01: 7640.6; 2022-11-01: 6880.2; 2022-12-01: 5479.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-02-23 | 2023-08-01 |  | 259751 | At Completion Units | [6 empty] | 665.4 | 3437.8 | 3326.9 | 6368.7 | 9960.3 | 15446 | 23133.3 | 28491.5 | 32959 | 32588.6 | 28847.6 | 25273.1 | 19099.7 | 10750.1 | 7716.4 | 4819.7 | 4643.2 | 2178.1 | 45.6
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-02-23 | 2023-04-16 |  | 180275 | At Completion Units | [6 empty] | 665.4 | 3437.8 | 3326.9 | 5427.9 | 7931.6 | 12791.9 | 19895.4 | 23230.6 | 24983 | 24035.4 | 20756.2 | 16782.1 | 12134.7 | 3481.7 | 1394.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-14 | 2023-08-01 |  | 79476 | At Completion Units | [9 empty] | 940.8 | 2028.7 | 2654.1 | 3237.9 | 5260.9 | 7976 | 8553.1 | 8091.5 | 8491.1 | 6965 | 7268.4 | 6322 | 4819.7 | 4643.2 | 2178.1 | 45.6
KEY QT: EC ELECTRICAL CABLES |  |  | 2022-05-18 | 2023-08-08 |  | 744840.9 | At Completion Units | [9 empty] | 3660.8 | 23340.6 | 69031.5 | 70740.8 | 74020.7 | 82199.5 | 82055.4 | 65486.1 | 55833.8 | 53416 | 43296.7 | 42222.5 | 35479.2 | 20493.5 | 19960.5 | 3603.4
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-01 | 2023-06-02 |  | 441690.9 | At Completion Units | 2022-06-01: 5706.8; 2022-07-01: 33465; 2022-08-01: 45552.6; 2022-09-01: 64263.3; 2022-10-01: 76030.2; 2022-11-01: 71886.4; 2022-12-01: 50273.9; 2023-01-01: 35519; 2023-02-01: 20273.8; 2023-03-01: 13476.9; 2023-04-01: 15729.1; 2023-05-01: 8946.8; 2023-06-01: 567.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-18 | 2023-08-08 |  | 303150 | At Completion Units | [9 empty] | 3660.8 | 17633.8 | 35566.5 | 25188.2 | 9757.3 | 6169.4 | 10169 | 15212.2 | 20314.8 | 33142.2 | 29819.8 | 26493.3 | 26532.4 | 19926.4 | 19960.5 | 3603.4
KEY QT: IC INSTRUMENT CABLES |  |  | 2022-06-11 | 2023-08-21 |  | 1116824 | At Completion Units | [10 empty] | 14414.6 | 43237.9 | 51068.5 | 45585 | 71123.1 | 68204.4 | 122627.6 | 137547.9 | 149651.8 | 168531.3 | 99850.7 | 64011.8 | 41874.4 | 27356.2 | 11738.9
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-11 | 2023-06-02 |  | 746102.1 | At Completion Units | 2022-06-01: 13877.2; 2022-07-01: 37216.3; 2022-08-01: 42374.9; 2022-09-01: 33440.5; 2022-10-01: 61260.1; 2022-11-01: 62169; 2022-12-01: 109264; 2023-01-01: 112438.7; 2023-02-01: 111187.2; 2023-03-01: 111843.2; 2023-04-01: 38764.4; 2023-05-01: 11523.1; 2023-06-01: 743.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-06-25 | 2023-08-21 |  | 370721.9 | At Completion Units | [10 empty] | 537.5 | 6021.6 | 8693.6 | 12144.5 | 9862.9 | 6035.4 | 13363.6 | 25109.1 | 38464.5 | 56688.1 | 61086.3 | 52488.6 | 41131 | 27356.2 | 11738.9
[9 empty] | 0 | 542.2 | 1652.6 | 1770.5 | 23255.8 | 21715.7 | 26870.4 | 26003.6 | 29661.7 | 30409.5 | 33112.5 | 33553 | 36276.4 | 38103.9 | 31759.3 | 27721.1 | 16784.2 | 12134.7 | 3481.7 | 1394.4 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 9787.5 | 8840.3 | 9787.5 | 9398.8 | 10637.9 | 10932.1 | 11366.7 | 11950.5 | 13692.4 | 15616.6 | 15433.3 | 13570.6 | 8491.1 | 6965 | 7268.4 | 6322 | 4819.7 | 4643.2 | 2178.1 | 45.6

## SUPPORTS
SUPPORTS [KG]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 924390.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461.6 | 22425.4 | 46204.5 | 48981.3 | 55671.5 | 65341.9 | 96384.5 | 93217.9 | 100474.7 | 98855.6 | 95698.8 | 85682.3 | 64478.3 | 21387 | 11562.4 | 11562.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 273361 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208.3952 | 3125.1731 | 4458.4116 | 5874.14 | 6534.8132 | 6534.8132 | 8082.393 | 7510.8163 | 12797.9953 | 18701.0161 | 15220.4008 | 30022.3124 | 27671.0708 | 31643.8876 | 29628.9286 | 21782.1128 | 21079.5341 | 21782.1128 | 702.6732 | 0 | 0 | 0 | 0
Overall Per Month | 1197751.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669.9952 | 25550.5731 | 50662.9116 | 54855.44 | 62206.3132 | 71876.7132 | 104466.893 | 100728.7163 | 113272.6953 | 117556.6161 | 110919.2008 | 115704.6124 | 92149.3708 | 53030.8876 | 41191.3286 | 33344.5128 | 21079.5341 | 21782.1128 | 702.6732 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6669.9952 | 32220.5683 | 82883.4799 | 137738.9199 | 199945.2331 | 271821.9462 | 376288.8392 | 477017.5555 | 590290.2508 | 707846.8669 | 818766.0677 | 934470.6801 | 1026620.0509 | 1079650.9384 | 1120842.2671 | 1154186.7799 | 1175266.314 | 1197048.4268 | 1197751.1 | 1197751.1 | 1197751.1 | 1197751.1 | 1197751.1
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## UG PRESSURE PIPING U
PIPING PREFABRICATION [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 18220.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3404.45 | 4255.57 | 3404.45 | 4255.57 | 246 | 1043.27 | 1610.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 10999.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2304.07 | 2880.09 | 2304.07 | 1481.19 | 476 | 850 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 14839.48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543.38 | 1004.87 | 2249.64 | 2939.04 | 2351.23 | 2244.73 | 1731.72 | 774.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 10079.01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083.02 | 1477.12 | 1477.12 | 1846.4 | 1433.7 | 1071.82 | 1053.11 | 636.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 54137.97 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708.52 | 7135.66 | 5708.52 | 5736.76 | 3348.4 | 4375.26 | 6041.51 | 4785.44 | 3784.93 | 3316.55 | 2784.83 | 1411.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5708.52 | 12844.18 | 18552.7 | 24289.46 | 27637.86 | 32013.12 | 38054.63 | 42840.07 | 46625 | 49941.55 | 52726.38 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97 | 54137.97
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PIPING PREFAB U
PIPING PREFABRICATION [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 47832.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4827 | 3707 | 5931 | 8103.75 | 14041.5 | 11221.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 25947.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2647 | 1712 | 2901 | 7595.5 | 5792.75 | 5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 198629 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9924 | 21050.3 | 23432.6 | 22676.7 | 24233.8 | 22477.9 | 20320.6 | 13657.6 | 13045.8 | 13120.9 | 7723.9 | 6964.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 101251.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8768 | 8840.3 | 9787.5 | 9398.8 | 9697.1 | 8903.4 | 8712.6 | 8712.6 | 8431.5 | 7640.6 | 6880.2 | 5479.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 373660.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7474 | 5419 | 8832 | 34391.25 | 49724.85 | 49741 | 32075.5 | 33930.9 | 31381.3 | 29033.2 | 22370.2 | 21477.3 | 20761.5 | 14604.1 | 12444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7474 | 12893 | 21725 | 56116.25 | 105841.1 | 155582.1 | 187657.6 | 221588.5 | 252969.8 | 282003 | 304373.2 | 325850.5 | 346612 | 361216.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1 | 373660.1
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PIPING ERE U
PIPING ERECTION [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 180275 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665.4 | 3437.8 | 4326.9 | 4427.9 | 7931.6 | 12791.9 | 19895.4 | 23230.6 | 24983 | 24035.4 | 20756.2 | 16782.1 | 12134.7 | 3481.7 | 1394.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 79476 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.1 | 879.8 | 851.4 | 1079.9 | 1645.6 | 2258.2 | 2842 | 4937.3 | 8038.3 | 8782.8 | 8319.4 | 8675.6 | 7131.7 | 7452.9 | 6468.1 | 4982.6 | 3900.9 | 775.4 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 259832 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143.5 | 4374.6 | 5178.3 | 5507.8 | 9577.2 | 15050.1 | 22737.4 | 28167.9 | 33021.3 | 32818.2 | 29075.6 | 25457.7 | 19266.4 | 10934.6 | 7862.5 | 4982.6 | 3900.9 | 775.4 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143.5 | 5518.1 | 10696.4 | 16204.2 | 25781.4 | 40831.5 | 63568.9 | 91736.8 | 124758.1 | 157576.3 | 186651.9 | 212109.6 | 231376 | 242310.6 | 250173.1 | 255155.7 | 259056.6 | 259832 | 259832 | 259832 | 259832 | 259832 | 259832
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PIPING U
PIPING PREFABRICATION + ERECTION [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 47832.15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4827 | 3707 | 5931 | 8103.75 | 14041.5 | 11221.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 26028.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2647 | 1712 | 2901 | 7595.5 | 5816.75 | 5356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 378904 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9924 | 21715.7 | 26870.4 | 27003.6 | 28661.7 | 30409.5 | 33112.5 | 33553 | 36276.4 | 38103.9 | 31759.3 | 27721.1 | 16782.1 | 12134.7 | 3481.7 | 1394.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 180727.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8768 | 9294.4 | 10667.3 | 10250.2 | 10777 | 10549 | 10970.8 | 11554.6 | 13368.8 | 15678.9 | 15663 | 13798.5 | 8675.6 | 7131.7 | 7452.9 | 6468.1 | 4982.6 | 3900.9 | 775.4 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 633492.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7474 | 5419 | 8832 | 34391.25 | 50868.35 | 54115.6 | 37253.8 | 39438.7 | 40958.5 | 44083.3 | 45107.6 | 49645.2 | 53782.8 | 47422.3 | 41519.6 | 25457.7 | 19266.4 | 10934.6 | 7862.5 | 4982.6 | 3900.9 | 775.4 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7474 | 12893 | 21725 | 56116.25 | 106984.6 | 161100.2 | 198354 | 237792.7 | 278751.2 | 322834.5 | 367942.1 | 417587.3 | 471370.1 | 518792.4 | 560312 | 585769.7 | 605036.1 | 615970.7 | 623833.2 | 628815.8 | 632716.7 | 633492.1 | 633492.1 | 633492.1 | 633492.1 | 633492.1 | 633492.1
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PIPING SB
PIPING SB [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 60491.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491.9 | 1771 | 2081.2 | 3061.9 | 4526.7 | 5265.9 | 8464.3 | 8638.8 | 8670.7 | 7450.6 | 5274.7 | 1955.5 | 1378.6 | 459.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 27799.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.8 | 431.3 | 671.5 | 630.5 | 675.7 | 1072.2 | 3192.5 | 3471.8 | 3704.2 | 4030.3 | 3664.5 | 3496.8 | 2217.3 | 510.1 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 88290.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491.9 | 1771 | 2112 | 3493.2 | 5198.2 | 5896.4 | 9140 | 9711 | 11863.2 | 10922.4 | 8978.9 | 5985.8 | 5043.1 | 3956.3 | 2217.3 | 510.1 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491.9 | 3262.9 | 5374.9 | 8868.1 | 14066.3 | 19962.7 | 29102.7 | 38813.7 | 50676.9 | 61599.3 | 70578.2 | 76564 | 81607.1 | 85563.4 | 87780.7 | 88290.8 | 88290.8 | 88290.8 | 88290.8 | 88290.8 | 88290.8
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## EQUIPMENT U
EQUIPMENT [t]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 339 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 49 | 39 | 73 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 73.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 16920.3784 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520.7863 | 641.7257 | 1254.5728 | 1454.7661 | 2832.5423 | 2718.2741 | 2300.6376 | 2036.8827 | 1912.2438 | 806.1836 | 308.3781 | 56.0948 | 49.1771 | 25.5577 | 2.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 7338.6662 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.868 | 217.5464 | 662.0603 | 966.735 | 1187.5554 | 845.3914 | 1018.9405 | 544.0285 | 386.2713 | 311.7315 | 235.6648 | 244.483 | 141.7992 | 59.5366 | 12.6191 | 62.8448 | 129.2775 | 71.3129 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 24671.2247 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 49 | 800.6543 | 932.2721 | 2157.8131 | 2421.5012 | 4020.0977 | 3563.6655 | 3319.5782 | 2580.9112 | 2298.5151 | 1117.9151 | 544.0428 | 300.5778 | 190.9762 | 85.0943 | 15.1747 | 62.8448 | 129.2775 | 71.3129 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 59 | 859.6543 | 1791.9264 | 3949.7396 | 6371.2408 | 10391.3384 | 13955.004 | 17274.5822 | 19855.4934 | 22154.0085 | 23271.9236 | 23815.9664 | 24116.5443 | 24307.5205 | 24392.6148 | 24407.7895 | 24470.6343 | 24599.9118 | 24671.2247 | 24671.2247 | 24671.2247 | 24671.2247 | 24671.2247 | 24671.2247 | 24671.2247
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## TRAYS U
CABLE TRAYS [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 390 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 1596 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 71889 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224.2038 | 4015.5771 | 7335.008 | 6029.2811 | 8099.4242 | 9431.9159 | 10341.8583 | 8838.4331 | 6386.0173 | 5683.3414 | 3496.8292 | 700.7364 | 296.4828 | 9.8914 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 65912 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163.1238 | 3004.847 | 2930.4177 | 3511.3157 | 4877.7397 | 5998.7917 | 4590.9947 | 4421.24 | 5919.8897 | 6600.3062 | 6304.2663 | 5541.0341 | 3960.1977 | 4249.3887 | 1670.8504 | 909.3653 | 150.466 | 107.7652 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 139787 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713.1238 | 4440.847 | 4154.6215 | 7526.8928 | 12212.7477 | 12028.0728 | 12690.4189 | 13853.156 | 16261.7479 | 15438.7393 | 12690.2836 | 11224.3755 | 7457.0269 | 4950.1251 | 1967.3332 | 919.2567 | 150.466 | 107.7652 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713.1238 | 6153.9708 | 10308.5923 | 17835.4851 | 30048.2328 | 42076.3056 | 54766.7245 | 68619.8805 | 84881.6284 | 100320.3678 | 113010.6514 | 124235.0269 | 131692.0538 | 136642.1789 | 138609.5121 | 139528.7688 | 139679.2348 | 139787 | 139787 | 139787 | 139787 | 139787 | 139787
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## ELECTRICAL U
ELECTRICAL CABLES LAYING [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 441691 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5706.8 | 33465 | 45552.6 | 64020.4 | 73235.8 | 71886.4 | 50273.9 | 34821.7 | 20548.6 | 13840.3 | 8344.6 | 15452.3 | 4542.6 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 303150 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660.8 | 17633.8 | 36173.3 | 26896.7 | 10307.9 | 6003.1 | 8515.6 | 14166 | 29973.1 | 34449 | 29819.8 | 26493.3 | 25835.4 | 19316.6 | 13905.6 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 744841 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660.8 | 23340.6 | 69638.3 | 72449.3 | 74328.3 | 79238.9 | 80402 | 64439.9 | 64794.8 | 54997.6 | 43660.1 | 34837.9 | 41287.7 | 23859.2 | 13905.6 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660.8 | 27001.4 | 96639.7 | 169089 | 243417.3 | 322656.2 | 403058.2 | 467498.1 | 532292.9 | 587290.5 | 630950.6 | 665788.5 | 707076.2 | 730935.4 | 744841 | 744841 | 744841 | 744841 | 744841 | 744841
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## INSTRUMENTATION U
INSTRUMENTATION CABLES [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 746102.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13877.2 | 37216.3 | 42374.9 | 30330.2 | 59796.5 | 61228.1 | 104282.9 | 111438 | 119341.8 | 109609.6 | 38764.4 | 11523.1 | 6319.1 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 370722 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537.5 | 6021.6 | 8693.6 | 12144.5 | 9862.9 | 6035.4 | 13363.6 | 32271.5 | 41865.2 | 65073.1 | 61086.3 | 52488.6 | 37730.4 | 20193.8 | 3354 | 0 | 0 | 0 | 0
Overall Per Month | 1116824.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14414.7 | 43237.9 | 51068.5 | 42474.7 | 69659.4 | 67263.5 | 117646.5 | 143709.5 | 161207 | 174682.7 | 99850.7 | 64011.7 | 44049.5 | 20193.8 | 3354 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14414.7 | 57652.6 | 108721.1 | 151195.8 | 220855.2 | 288118.7 | 405765.2 | 549474.7 | 710681.7 | 885364.4 | 985215.1 | 1049226.8 | 1093276.3 | 1113470.1 | 1116824.1 | 1116824.1 | 1116824.1 | 1116824.1 | 1116824.1
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PAINTING U
PAINTING [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 6873.5635 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467 | 655 | 1015 | 185.097 | 1247.526 | 3303.9404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 5551.7728 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 470 | 1001 | 501.9086 | 2054.1556 | 1379.7086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 122000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6258.6534 | 6051.854 | 7813.4231 | 7983.0761 | 8533.2506 | 8795.5073 | 10033.2194 | 8257.5399 | 8221.706 | 9829.964 | 10583.919 | 9182.8543 | 7613.5804 | 6105.6704 | 4034.6568 | 1548.9286 | 793.7267 | 358.4699 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 46000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744.4427 | 1977.3014 | 2523.6317 | 2902.8178 | 3162.5959 | 3448.3119 | 3032.6402 | 4461.6644 | 4738.8973 | 3837.3796 | 2928.0006 | 2529.606 | 1948.8914 | 1455.1397 | 1688.8467 | 1212.5054 | 987.4146 | 779.5566 | 632.3238 | 8.0325 | 0 | 0 | 0 | 0
Overall Per Month | 180425.3362 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 1125 | 2016 | 8690.1017 | 11330.837 | 15020.7039 | 10885.8939 | 11695.8466 | 12243.8192 | 13065.8597 | 12719.2043 | 12960.6033 | 13667.3436 | 13511.9196 | 11712.4602 | 9562.4718 | 7560.8101 | 5723.5036 | 2761.434 | 1781.1413 | 1138.0265 | 632.3238 | 8.0325 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 1737 | 3753 | 12443.1017 | 23773.9387 | 38794.6425 | 49680.5364 | 61376.383 | 73620.2022 | 86686.0619 | 99405.2662 | 112365.8695 | 126033.2131 | 139545.1326 | 151257.5928 | 160820.0647 | 168380.8747 | 174104.3783 | 176865.8123 | 178646.9536 | 179784.98 | 180417.3038 | 180425.3362 | 180425.3362 | 180425.3362 | 180425.3362 | 180425.3362
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## INSULATION U
INSULATION [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea Actual | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ammonia Forecast | 120839 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 46.9 | 28.7 | 3361.1 | 3759.5 | 4021.2 | 6925.8 | 8321 | 13314.9 | 21431.5 | 29265 | 16133.3 | 11443.4 | 2783.5 | 0 | 0 | 0 | 0 | 0 | 0
Urea Forecast | 73417 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145.9 | 280.5 | 951.7 | 2831.9 | 3480.8 | 3008.3 | 2317.1 | 6793.9 | 8728.2 | 15543.9 | 12675.1 | 11548.2 | 4498.6 | 612.9 | 0 | 0 | 0 | 0
Overall Per Month | 194256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 46.9 | 174.6 | 3641.6 | 4711.2 | 6853.1 | 10406.6 | 11329.3 | 15632 | 28225.4 | 37993.2 | 31677.2 | 24118.5 | 14331.7 | 4498.6 | 612.9 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 50.1 | 224.7 | 3866.3 | 8577.5 | 15430.6 | 25837.2 | 37166.5 | 52798.5 | 81023.9 | 119017.1 | 150694.3 | 174812.8 | 189144.5 | 193643.1 | 194256 | 194256 | 194256 | 194256 | 194256
FOUNDATIONS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 0 | 0%
Urea | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1000308.4 | 8.713% | 0% | 0% | 0% | 0% | 0% | 11.06% | 12.38% | 13.97% | 10.84% | 9.512% | 9.621% | 9.966% | 5.782% | 3.186% | 5.443% | 2.047% | 3.261% | 2.594% | 0.2397% | 0.06673% | 0.02492% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1000308.4 |  | 0% | 0% | 0% | 0% | 0% | 11.06% | 23.44% | 37.42% | 48.26% | 57.77% | 67.39% | 77.36% | 83.14% | 86.32% | 91.77% | 93.81% | 97.07% | 99.67% | 99.91% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## STEEL STRUCTURE (hidden)
STRUCTURAL STEEL [t]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 12602.7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 7.8 | 221.6 | 456.5 | 869.8 | 359.8 | 561.2 | 1058.8 | 1060.9 | 1020.5 | 1004.4 | 1093.9 | 1026.4 | 1070.3924 | 1020.9064 | 867.3219 | 491.843 | 329.1202 | 81.1161 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea | 9029.4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 171.5 | 175.5 | 150.1 | 210.8 | 175.1 | 206.3 | 593.5 | 876.5 | 882.7 | 1016 | 833.2 | 824.8 | 715.5 | 587.3 | 457.1 | 395.4 | 304.8 | 167 | 154.7 | 80.6 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 21632.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 179.3 | 397.1 | 606.6 | 1080.6 | 534.9 | 767.5 | 1652.3 | 1937.4 | 1903.2 | 2020.4 | 1927.1 | 1851.2 | 1785.8924 | 1608.2064 | 1324.4219 | 887.243 | 633.9202 | 248.1161 | 155.1 | 80.6 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 213.3 | 610.4 | 1217 | 2297.6 | 2832.5 | 3600 | 5252.3 | 7189.7 | 9092.9 | 11113.3 | 13040.4 | 14891.6 | 16677.4924 | 18285.6988 | 19610.1207 | 20497.3637 | 21131.2839 | 21379.4 | 21534.5 | 21615.1 | 21632.1 | 21632.1 | 21632.1 | 21632.1 | 21632.1 | 21632.1 | 21632.1 | 21632.1
Steel Delivery |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2647.2076 | 2939.7399 | 3598.6443 | 4244.9209 | 6442.6957 | 10932.9713 | 15910.6898 | 20226.4765 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491 | 21443.7491
STRUCTURAL STEEL [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 710400.5 | 6.188% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.2033% | 0.8955% | 1.364% | 1.612% | 2.789% | 3.228% | 3.471% | 4.955% | 5.551% | 5.282% | 4.814% | 4.754% | 4.239% | 2.526% | 1.954% | 1.017% | 0.6238% | 0.4197% | 0.3544% | 0.1294% | 0.03832% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 704116.8 | 6.133% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8933% | 0.9545% | 0.7625% | 0.7625% | 0.7625% | 1.233% | 1.365% | 2.06% | 1.934% | 1.736% | 1.832% | 1.897% | 3.09% | 4.48% | 5.027% | 5.032% | 5.05% | 4.942% | 3.419% | 1.455% | 0.7728% | 0.1968% | 0.1181% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1414517.3 | 12.32% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8933% | 1.158% | 1.658% | 2.126% | 2.375% | 4.022% | 4.593% | 5.531% | 6.889% | 7.287% | 7.115% | 6.711% | 7.845% | 8.72% | 7.554% | 6.985% | 6.068% | 5.566% | 3.839% | 1.81% | 0.9021% | 0.2351% | 0.1181% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1414517.3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0.8933% | 2.051% | 3.709% | 5.835% | 8.21% | 12.23% | 16.82% | 22.36% | 29.25% | 36.53% | 43.65% | 50.36% | 58.2% | 66.92% | 74.48% | 81.46% | 87.53% | 93.1% | 96.93% | 98.74% | 99.65% | 99.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2201-BL016
1715-BL010&BL029
1801-BL001
2801-BL014
2301-BL019

## Sheet3 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
KEY QT: ST MAIN STEEL STRUCTURE |  |  | 01.08.21 A | 2023-05-08 |  | 21632 | 2175.8 | 10.06% | 494 |  | 19456.2 | Remaining Units |  |  |  |  | 155 | 716 | 1207.9 | 1893 | 2287.5 | 2287.2 | 2168.4 | 1885.8 | 1742.8 | 1504 | 1271.3 | 785.9 | 632.5 | 447.1 | 219 | 155 | 80.6 | 17
[15 empty] | Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
[15 empty] | Area Tag Kingisepp-2: 1 Ammonia |  |  | 23.09.21 A | 2023-03-03 |  | 12602.7 | 1439.6 | 11.42% | 428 |  | 11163.1 | Remaining Units |  |  |  |  | 149.3 | 524.1 | 856.3 | 1272.6 | 1470.7 | 1448.3 | 1222.5 | 1039.9 | 918 | 788.5 | 685.2 | 355.8 | 237.1 | 142.3 | 52 | 0.4
[15 empty] | Area Tag Kingisepp-2: 2 Urea |  |  | 01.08.21 A | 2023-05-08 |  | 9029.3 | 736.2 | 8.15% | 494 |  | 8293.1 | Remaining Units |  |  |  |  | 5.7 | 191.9 | 351.6 | 620.4 | 816.8 | 838.9 | 945.9 | 845.9 | 824.8 | 715.5 | 586.1 | 430.1 | 395.4 | 304.8 | 167 | 154.7 | 80.6 | 17

## CLADDING (hidden)
CLADDING [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 33149.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247.5 | 2164.3 | 1164.3 | 998.9 | 1280.9 | 3044.6 | 4204.7 | 2636.2 | 1264.6 | 1084.9 | 1538 | 176.9 | 2609 | 4746.5 | 2988.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea | 54536.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.7 | 1785.6 | 3222 | 3309.2 | 3162.6 | 1446.2 | 1460.7 | 3393.1 | 5277.8 | 6449.8 | 6723.6 | 8471.6 | 5360.8 | 2773 | 1663.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 87686 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3284.2 | 3949.9 | 4386.3 | 4308.1 | 4443.5 | 4490.8 | 5665.4 | 6029.3 | 6542.4 | 7534.7 | 8261.6 | 8648.5 | 7969.8 | 7519.5 | 4652 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3284.2 | 7234.1 | 11620.4 | 15928.5 | 20372 | 24862.8 | 30528.2 | 36557.5 | 43099.9 | 50634.6 | 58896.2 | 67544.7 | 75514.5 | 83034 | 87686 | 87686 | 87686 | 87686 | 87686 | 87686 | 87686 | 87686
CLADDING [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 92464.6 | 0.8054% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.704% | 2.468% | 1.328% | 1.139% | 1.461% | 3.472% | 4.795% | 3.006% | 1.442% | 1.237% | 1.754% | 0.2017% | 2.975% | 5.413% | 3.408% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 150592.9 | 1.312% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04185% | 2.036% | 3.674% | 3.774% | 3.607% | 1.649% | 1.666% | 3.87% | 6.019% | 7.356% | 7.668% | 9.661% | 6.114% | 3.162% | 1.897% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 243057.5 | 2.117% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.745% | 4.505% | 5.002% | 4.913% | 5.068% | 5.121% | 6.461% | 6.876% | 7.461% | 8.593% | 9.422% | 9.863% | 9.089% | 8.575% | 5.305% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 243057.5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.745% | 8.25% | 13.25% | 18.17% | 23.23% | 28.35% | 34.82% | 41.69% | 49.15% | 57.75% | 67.17% | 77.03% | 86.12% | 94.69% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## BUILDINGS (MASONARY) (hidden)
BUILDINGS (MASONARY) [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 1816.3 |  | 2022-05-01: 137.2; 2022-06-01: 584.3; 2022-07-01: 584.3; 2022-08-01: 447.1; 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 15.4; 2022-12-01: 16
Urea | 1815.1 |  | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2022-02-01: 12.9; 2022-03-01: 308.9; 2022-04-01: 347.5; 2022-05-01: 380.8; 2022-06-01: 300.9; 2022-07-01: 133.6; 2022-08-01: 109.2; 2022-09-01: 32.7; 2022-10-01: 8.5; 2022-11-01: 48.5; 2022-12-01: 90; 2023-01-01: 41.6; 2023-10-01: 0; 2023-11-01: 0
Overall Per Month | 3631.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9 | 308.9 | 347.5 | 518 | 885.2 | 717.9 | 556.3 | 48.7 | 24.5 | 63.9 | 106 | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9 | 321.8 | 669.3 | 1187.3 | 2072.5 | 2790.4 | 3346.7 | 3395.4 | 3419.9 | 3483.8 | 3589.8 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4 | 3631.4
BUILDINGS (MASONARY) [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 39342 | 0.3427% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.778% | 16.09% | 16.09% | 12.31% | 0.4406% | 0.4406% | 0.4241% | 0.4406% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 19760 | 0.1721% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3552% | 8.506% | 9.569% | 10.49% | 8.286% | 3.679% | 3.007% | 0.9005% | 0.2341% | 1.336% | 2.478% | 1.146% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 59102 | 0.5148% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3552% | 8.506% | 9.569% | 14.26% | 24.38% | 19.77% | 15.32% | 1.341% | 0.6747% | 1.76% | 2.919% | 1.146% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 59102 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3552% | 8.862% | 18.43% | 32.7% | 57.07% | 76.84% | 92.16% | 93.5% | 94.18% | 95.94% | 98.85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## PIPING (hidden)
PIPING WORKS [DI]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 396290.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 1623 | 2372.2 | 23224.5 | 22798.3 | 25839.1 | 25973.3 | 29630.4 | 30369.9 | 32945.2 | 33413.6 | 36249.6 | 38076.1 | 31649.9 | 27702.1 | 16784.2 | 12134.7 | 3481.7 | 1394.4 | 87.1 | 0 | 0 | 0 | 0 | 0 | 0
Piping SB | 0
Piping LB Prefab | 215928.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 1623 | 2372.2 | 23224.5 | 22022 | 22401.3 | 22646.4 | 24202.5 | 22438.3 | 20153.3 | 13629.1 | 13019 | 13093.1 | 7614.5 | 6945.9 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Piping LB Erection | 180362.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.3 | 3437.8 | 3326.9 | 5427.9 | 7931.6 | 12791.9 | 19784.5 | 23230.6 | 24983 | 24035.4 | 20756.2 | 16782.1 | 12134.7 | 3481.7 | 1394.4 | 87.1 | 0 | 0 |  | 0 | 0 | 0
Urea | 181747.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.9 | 8761.7 | 9817.1 | 9761.7 | 9371 | 10429.2 | 10638 | 11459.3 | 12975.2 | 15519.5 | 16266.8 | 15964.4 | 13719.4 | 8611.5 | 7073.8 | 7388.8 | 6369.9 | 4798 | 1914.2 | 593 | 0 | 0 | 0 | 0
Piping SB | 0
Piping LB Prefab | 102271.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314.9 | 8761.7 | 9817.1 | 9761.7 | 9371 | 9671.3 | 8848.4 | 8687.1 | 8687.1 | 8406.9 | 7619 | 6861 | 5464.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Piping LB Erection | 79476.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.9 | 1789.6 | 2772.2 | 4288.1 | 7112.6 | 8647.8 | 9103.4 | 8255.3 | 8611.5 | 7073.8 | 7388.8 | 6369.9 | 4798 | 1914.2 | 593 | 0 | 0 | 0 | 0
Overall Per Month | 578037.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 1623 | 2687.1 | 31986.2 | 32615.4 | 35600.8 | 35344.3 | 40059.6 | 41007.9 | 44404.5 | 46388.8 | 51769.1 | 54342.9 | 47614.3 | 41421.5 | 25395.7 | 19208.5 | 10870.5 | 7764.3 | 4885.1 | 1914.2 | 593 | 0 | 0 | 0 | 0 | 0
Cumulative | 577444.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 2164 | 4851.1 | 36837.3 | 69452.7 | 105053.5 | 140397.8 | 180457.4 | 221465.3 | 265869.8 | 312258.6 | 364027.7 | 418370.6 | 465984.9 | 507406.4 | 532802.1 | 552010.6 | 562881.1 | 570645.4 | 575530.5 | 577444.7 | 578037.7 | 578037.7 | 578037.7 | 578037.7 | 578037.7 | 578037.7
Feasibility | 579242.4 |  | 0 | 0 | 0 | 0 | 0 | 13193.7457 | 41171.9313 | 87108.9127 | 143658.8577 | 200705.8087 | 271820.7275 | 339377.1038 | 397265.5725 | 445272.9925 | 482619.5943 | 513832.96 | 545143.457 | 562250.5515 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4 | 579242.4
PIPING WORKS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 1609119.7 | 14.02% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2925% | 0.3803% | 0.3803% | 0.7404% | 1.343% | 2.255% | 3.219% | 4.428% | 4.797% | 4.914% | 5.007% | 4.507% | 4.723% | 4.295% | 4.202% | 3.742% | 3.033% | 1.854% | 1.017% | 0.7571% | 0.4119% | 0.02151% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping SB | 334830.3 | 2.917% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.002786% | 0.02515% | 0.0336% | 0.4745% | 1.21% | 1.693% | 1.909% | 1.934% | 1.853% | 1.206% | 0.6656% | 0.3815% | 0.3095% | 0.02151% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping LB Prefab | 843198.4 | 7.345% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2925% | 0.3803% | 0.3803% | 0.7404% | 1.343% | 2.255% | 3.13% | 4.024% | 4.17% | 4.09% | 3.485% | 2.093% | 1.486% | 0.9311% | 0.5216% | 0.1922% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping LB Erection | 431091 | 3.755% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.08964% | 0.4049% | 0.6245% | 0.7986% | 1.489% | 1.939% | 2.028% | 1.671% | 1.771% | 1.616% | 1.18% | 0.6484% | 0.3512% | 0.3756% | 0.1025% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 1247992.5 | 10.87% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3819% | 0.4359% | 0.5848% | 0.9088% | 1.436% | 1.732% | 2.005% | 3.708% | 3.634% | 3.848% | 3.692% | 3.819% | 3.272% | 2.991% | 2.817% | 2.432% | 2.173% | 1.477% | 0.8326% | 0.6499% | 0.494% | 0.3554% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping SB | 215604.7 | 1.878% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1245% | 0.3844% | 0.3844% | 0.3905% | 0.5723% | 0.5493% | 0.7391% | 0.9239% | 0.9512% | 0.8715% | 0.4953% | 0.4177% | 0.3867% | 0.3554% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping LB Prefab | 679398 | 5.918% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3819% | 0.4359% | 0.5848% | 0.9088% | 1.387% | 1.6% | 1.771% | 3.18% | 2.914% | 2.588% | 2.37% | 2.355% | 1.44% | 0.9679% | 0.6887% | 0.2048% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Piping LB Erection | 352989.8 | 3.075% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04882% | 0.1318% | 0.2343% | 0.5272% | 0.5955% | 0.875% | 0.9372% | 1.074% | 1.259% | 1.474% | 1.39% | 1.303% | 1.222% | 0.6058% | 0.3373% | 0.2322% | 0.1074% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 2857112.2 | 24.89% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6744% | 0.8162% | 0.9651% | 1.649% | 2.779% | 3.987% | 5.225% | 8.136% | 8.431% | 8.761% | 8.699% | 8.326% | 7.996% | 7.286% | 7.019% | 6.174% | 5.207% | 3.332% | 1.849% | 1.407% | 0.906% | 0.377% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 2857112.2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6744% | 1.491% | 2.456% | 4.105% | 6.884% | 10.87% | 16.09% | 24.23% | 32.66% | 41.42% | 50.12% | 58.45% | 66.44% | 73.73% | 80.75% | 86.92% | 92.13% | 95.46% | 97.31% | 98.72% | 99.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Sheet4 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | Actual Units | Units % Complete | Remaining Units | Curve | Spreadsheet Field | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: SB PIPING SB |  |  | 2022-03-01 | 2023-05-10 | 62394.5 | 0 | 0% | 62394.5 |  | At Completion Units | [5 empty] | 1340.9 | 1505.8 | 1771 | 2081.2 | 3061.9 | 4526.7 | 5814.3 | 8464.3 | 8638.8 | 8670.7 | 7450.6 | 5274.7 | 1955.5 | 1378.6 | 459.5
KEY QT: LBP PIPING LB PREFAB |  |  | 22.10.21 A | 2023-01-04 | 215928.3 | 3787 | 1.75% | 212141.3 |  | At Completion Units | 541 | 1623 | 2372.2 | 23224.5 | 21022 | 23401.3 | 22646.4 | 24202.5 | 22438.3 | 20153.3 | 13629.1 | 13019 | 13093.1 | 7614.5 | 6945.9 | 2.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-02-22 | 2023-04-16 | 180275 | 0 | 0% | 180275 |  | At Completion Units |  |  |  |  | 776.3 | 3437.8 | 3326.9 | 5427.9 | 7931.6 | 12791.9 | 19784.5 | 23230.6 | 24983 | 24035.4 | 20756.2 | 16782.1 | 12134.7 | 3481.7 | 1394.4
KEY QT: SB PIPING SB |  |  | 2022-06-21 | 2023-07-13 | 27799.5 | 0 | 0% | 27799.5 |  | At Completion Units | [8 empty] | 30.8 | 440.7 | 671.5 | 630.5 | 675.7 | 2090.1 | 3183 | 3471.8 | 3824.2 | 4030.3 | 3664.5 | 3496.8 | 1199.5 | 390.1
KEY QT: LBP PIPING LB PREFAB |  |  | 2021-12-31 | 2022-12-31 | 102271.2 | 0 | 0% | 102271.2 |  | At Completion Units | 2021-12-01: 314.9; 2022-01-01: 9761.7; 2022-02-01: 8817.1; 2022-03-01: 9761.7; 2022-04-01: 9371; 2022-05-01: 9671.3; 2022-06-01: 8848.4; 2022-07-01: 8687.1; 2022-08-01: 8687.1; 2022-09-01: 8406.9; 2022-10-01: 7619; 2022-11-01: 6861; 2022-12-01: 5464.1
KEY QT: LBE PIPING LB ERECT |  |  | 2022-05-14 | 2023-07-13 | 79476 | 0 | 0% | 79476 |  | At Completion Units | [7 empty] | 757.9 | 1789.6 | 2772.2 | 4288.1 | 7112.6 | 8647.8 | 9103.4 | 8255.3 | 8611.5 | 7073.8 | 7388.8 | 6369.9 | 4798 | 1914.2 | 593
[6 empty] | Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | Actual Units | Units % Complete | Remaining Units | Curve | Spreadsheet Field | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
[6 empty] | KEY QT: ST MAIN STEEL STRUCTURE |  |  | 23.09.21 A | 2023-03-03 | 12602.7 | 1406.4 | 11.16% | 11196.2 |  | At Completion Units |  | 7.8 | 221.6 | 456.5 | 869.8 | 359.8 | 561.2 | 1058.8 | 1260.9 | 1520.5 | 1504.4 | 1293.9 | 1126.4 | 899.1 | 685.4 | 346.9 | 239.6 | 140.1 | 49.6 | 0.4
[6 empty] | KEY QT: ST MAIN STEEL STRUCTURE |  |  | 01.08.21 A | 2023-05-08 | 9029.3 | 736.2 | 8.15% | 8293.1 |  | At Completion Units | 34 | 171.5 | 175.5 | 150.1 | 210.8 | 175.1 | 206.3 | 593.5 | 876.5 | 882.7 | 1016 | 833.2 | 824.8 | 715.5 | 587.3 | 457.1 | 395.4 | 304.8 | 167 | 154.7 | 80.6 | 17
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | Actual Units | Units % Complete | Remaining Units | Curve | Spreadsheet Field | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
KEY QT: EC ELECTRICAL CABLES |  |  | 2022-05-27 | 2023-07-20 | 744841 | 0 | 0% | 744841 |  | At Completion Units | 672.9 | 13386 | 59018.9 | 71127.3 | 26482.3 | 36551 | 66050.9 | 95792.1 | 150280.8 | 77531 | 47099.7 | 35557.5 | 34738.4 | 22096.5 | 8455.8
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-01 | 2023-06-02 | 441691 | 0 | 0% | 441691 |  | At Completion Units |  | 2155.1 | 26653.8 | 45939.2 | 16725 | 25259.4 | 49479.1 | 78186.2 | 115748.8 | 45229.9 | 17279.9 | 9064.2 | 9366.3 | 604.3
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-27 | 2023-07-20 | 303150 | 0 | 0% | 303150 |  | At Completion Units | 672.9 | 11231 | 32365.1 | 25188.2 | 9757.3 | 11291.6 | 16571.8 | 17605.9 | 34531.9 | 32301.1 | 29819.8 | 26493.3 | 25372.1 | 21492.2 | 8455.8
KEY QT: IC INSTRUMENT CABLES |  |  | 2022-06-11 | 2023-08-02 | 1116824 | 0 | 0% | 1116824 |  | At Completion Units |  | 14414.6 | 34099.7 | 44524.2 | 34664 | 67189.8 | 75158.1 | 118295.3 | 159717.3 | 174597.2 | 175365.1 | 99850.7 | 61971.4 | 35325.3 | 20533.4 | 1118
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-11 | 2023-06-02 | 746102.1 | 0 | 0% | 746102.1 |  | At Completion Units |  | 13877.2 | 31322.7 | 41747.2 | 27451.8 | 52002.5 | 60460.7 | 94355.7 | 125974.8 | 136035.4 | 111843.2 | 38764.4 | 11523.1 | 743.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-06-25 | 2023-08-02 | 370721.9 | 0 | 0% | 370721.9 |  | At Completion Units |  | 537.5 | 2776.9 | 2776.9 | 7212.2 | 15187.3 | 14697.3 | 23939.7 | 33742.5 | 38561.9 | 63521.9 | 61086.3 | 50448.3 | 34581.8 | 20533.4 | 1118
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | Actual Units | Units % Complete | Remaining Units | Curve | Spreadsheet Field | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
KEY QT: EC ELECTRICAL CABLES |  |  | 2022-05-27 | 2023-07-20 | 744840.9 | 0 | 0% | 744840.9 |  | Remaining Units | 672.9 | 14309.6 | 65830.1 | 70740.8 | 74020.7 | 87321.8 | 89671.2 | 69294.9 | 70050.9 | 52574.9 | 43296.7 | 42222.5 | 34318.9 | 22059.3 | 8455.8
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-01 | 2023-06-02 | 441690.9 | 0 | 0% | 441690.9 |  | Remaining Units |  | 3078.6 | 33465 | 45552.6 | 64263.3 | 76030.2 | 73099.4 | 51689.1 | 35519 | 20273.8 | 13476.9 | 15729.1 | 8946.8 | 567.1
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-05-27 | 2023-07-20 | 303150 | 0 | 0% | 303150 |  | Remaining Units | 672.9 | 11231 | 32365.1 | 25188.2 | 9757.3 | 11291.6 | 16571.8 | 17605.9 | 34531.9 | 32301.1 | 29819.8 | 26493.3 | 25372.1 | 21492.2 | 8455.8

## EQUIPMENT (hidden)
EQUIPMENT [t]
[39 empty] | TAG NO. | EQUIPMENT DESCRIPTION | Vendor | EQUIPMENT ETA SITE | ERECTION WINDOW
[39 empty] | 11-101-C | Secondary Reformer Waste Heat Boiler | KBR USA LLC | 25-May-22 | Jun
[39 empty] | 11-103-D | Secondary Reformer | Godrej & Boyce Mfg. Co. Ltd. | 25-May-22 | Jun
[39 empty] | 11-104-D1 | HT Shift Converter | Godrej & Boyce Mfg. Co. Ltd. | 25-May-22 | Jun
[39 empty] | 11-104-D2 | LT Shift Converter | Godrej & Boyce Mfg. Co. Ltd. | 25-May-22 | Jun
[39 empty] | 11-105-D | Ammonia Converter | KBR USA LLC | 14-Jun-22 | July
[39 empty] | 11-105-D | Ammonia Basket | KBR USA LLC | 25-May-22 | Jun
[39 empty] | 11-120-C | Ammonia unitized chiller | KBR USA LLC | 30-May-22 | Jun
[39 empty] | 11-121-D | CO2 Absorber | Larsen & Toubro Ltd. Heavy Engineer | 28-Jun-22 | July
[39 empty] | 11-122-D1 | LP Flash Column | Larsen & Toubro Ltd. Heavy Engineer | 15-Jul-22 | July
[39 empty] | 11-122-D2 | Carbon Dioxide Stripper | Larsen & Toubro Ltd. Heavy Engineer | 25-May-22 | June
[39 empty] | 11-123-C1 | Ammonia Converter Effluent Cooler / steam generator | Larsen & Toubro Ltd. Heavy Engineer | 25-May-22 | June
[39 empty] | 11-123-C2 | Ammonia Converter Effluent Cooler / BFW Preheater | Larsen & Toubro Ltd. Heavy Engineer | 25-May-22 | June
[39 empty] | 11-141-D | Steam Drum | Larsen & Toubro Ltd. Heavy Engineer | 25-May-22 | June
[39 empty] | 11-146-D | Ammonia Separator | Godrej & Boyce Mfg. Co. Ltd. | 25-May-22 | June
[39 empty] | 11-163-D | HP flash Column | Larsen & Toubro Ltd. Heavy Engineer | 15-Jul-22 | July
[39 empty] | 22-E-201 | HP Stripper | Stamicarbon B.V. | 09-Jun-22 | August
[39 empty] | 22-E-205 | Pool Condenser | Stamicarbon B.V. | 23-Jul-22 | August
[39 empty] | 22-R-201 | Reactor | Stamicarbon B.V. | 23-Jul-22 | August
The following are already under shipment and they will be erected by 400t crane
[39 empty] | TAG NO. | EQUIPMENT DESCRIPTION | Vendor | EQUIPMENT ETA SITE | ERECTION WINDOW
[39 empty] | 11-114-C | Methanator Feed / Effluent Exchanger | Curo Co Ltd. | 21-Mar-22 | March
[39 empty] | 11-121-C | Ammonia Conv. Feed / Effluent Exchanger | Curo Co Ltd. | 21-Mar-22 | March
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 11-124-C | Ammonia Converter Effluent Cooler | Curo Co Ltd. | 21-Mar-22 | March
Ammonia | 16976.4883 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.0226 | 524.0873 | 520.7863 | 641.7257 | 1254.5728 | 1454.7661 | 2832.5423 | 2718.2741 | 2300.6376 | 2036.8827 | 1812.2438 | 406.1836 | 208.3781 | 56.0948 | 49.1771 | 25.5577 | 2.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Urea | 7346.5117 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8454 | 240.868 | 217.5464 | 662.0603 | 966.735 | 1187.5554 | 845.3914 | 1018.9405 | 544.0285 | 386.2713 | 311.7315 | 235.6648 | 244.483 | 141.7992 | 59.5366 | 12.6191 | 62.8448 | 129.2775 | 71.3129 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 24323 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.0226 | 531.9328 | 761.6543 | 859.2721 | 1916.6331 | 2421.5012 | 4020.0977 | 3563.6655 | 3319.5782 | 2580.9112 | 2198.5151 | 717.9151 | 444.0428 | 300.5778 | 190.9762 | 85.0943 | 15.1747 | 62.8448 | 129.2775 | 71.3129 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.0226 | 663.9553 | 1425.6097 | 2284.8818 | 4201.5149 | 6623.0161 | 10643.1138 | 14206.7793 | 17526.3575 | 20107.2687 | 22305.7838 | 23023.6989 | 23467.7418 | 23768.3196 | 23959.2958 | 24044.3901 | 24059.5648 | 24122.4096 | 24251.6871 | 24323 | 24323 | 24323 | 24323 | 24323 | 24323 | 24323
EQUIPMENT [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 568809.1 | 4.955% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.515% | 1.472% | 2.197% | 3.331% | 4.446% | 6.358% | 7.478% | 7.714% | 7.919% | 6.573% | 5.201% | 3.292% | 2.679% | 1.731% | 0.7242% | 0.2088% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 350997 | 3.057% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.239% | 0.9326% | 1.222% | 1.66% | 1.9% | 2.132% | 2.496% | 2.946% | 4.016% | 3.98% | 4.102% | 3.951% | 3.075% | 2.875% | 2.174% | 0.4441% | 0.01645% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 919806.1 | 8.012% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.754% | 2.404% | 3.419% | 4.992% | 6.346% | 8.49% | 9.974% | 10.66% | 11.93% | 10.55% | 9.303% | 7.243% | 5.754% | 4.606% | 2.898% | 0.6529% | 0.01645% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 919806.1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.754% | 3.158% | 6.577% | 11.57% | 17.91% | 26.4% | 36.38% | 47.04% | 58.97% | 69.53% | 78.83% | 86.07% | 91.83% | 96.43% | 99.33% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## ELECTRICAL (hidden)
ELECTRICAL CABLES [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 441690.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3078.6 | 33465 | 45552.6 | 64263.3 | 76030.2 | 73099.4 | 51689.1 | 35519 | 20273.8 | 13476.9 | 15729.1 | 8946.8 | 567.1 | 0 | 0 | 0 | 0 | 0
Urea | 303150 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672.9 | 11231 | 32365.1 | 25188.2 | 9757.3 | 11291.6 | 16571.8 | 17605.9 | 34531.9 | 32301.1 | 29819.8 | 26493.3 | 25372.1 | 21492.2 | 8455.8 | 0 | 0 | 0 | 0
Overall Per Month | 744840.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672.9 | 14309.6 | 65830.1 | 70740.8 | 74020.6 | 87321.8 | 89671.2 | 69295 | 70050.9 | 52574.9 | 43296.7 | 42222.4 | 34318.9 | 22059.3 | 8455.8 | 0 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672.9 | 14982.5 | 80812.6 | 151553.4 | 225574 | 312895.8 | 402567 | 471862 | 541912.9 | 594487.8 | 637784.5 | 680006.9 | 714325.8 | 736385.1 | 744840.9 | 744840.9 | 744840.9 | 744840.9 | 744840.9 | 744840.9
ELECTRICAL WORKS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 623395.4 | 5.43% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.06863% | 0.3833% | 1.434% | 4.364% | 7.889% | 9.688% | 9.563% | 7.769% | 6.672% | 3.952% | 3.55% | 1.769% | 0.5498% | 0.04278% | 0% | 0% | 0% | 0% | 0% | 0%
Urea | 457126.4 | 3.982% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0103% | 0.1086% | 0.278% | 0.4519% | 1.113% | 2.059% | 3.964% | 5.812% | 8.723% | 6.935% | 4.814% | 3.301% | 2.078% | 1.377% | 1.092% | 0.1889% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 1080521.8 | 9.412% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0103% | 0.1086% | 0.3467% | 0.8352% | 2.548% | 6.422% | 11.85% | 15.5% | 18.29% | 14.7% | 11.49% | 7.253% | 5.628% | 3.146% | 1.642% | 0.2316% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative | 1080521.8 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0103% | 0.1189% | 0.4656% | 1.301% | 3.849% | 10.27% | 22.12% | 37.62% | 55.91% | 70.61% | 82.1% | 89.35% | 94.98% | 98.13% | 99.77% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Sheet2 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01
Area Tag Kingisepp-2: 2 Urea |  |  | 15.04.21 A | 2023-09-15 |  | 2318377.1 | 131585.8 | 5.68% | 837 |  | 2186791.3 | At Completion Units | 177.4 | 1603.8 | 10534.4 | 8482.8 | 10557 | 12755.1 | 19116.1 | 21416.6 | 72338.2 | 111495 | 42248.9 | 50730.6 | 27046 | 28658.7 | 45528.1 | 76093.2 | 63374.3 | 70726.4 | 109011.1 | 136546.2 | 196657.4 | 194865.4 | 162066.8 | 214159.1 | 215493.9 | 189278 | 137493.2 | 71959 | 16158.7 | 1805.6
KEY QT: EC ELECTRICAL CABLES |  |  | 2022-06-19 | 2023-07-24 |  | 303150 | 0 | 0% | 401 |  | 303150 | At Completion Units | 2022-06-01: 9591.7; 2022-07-01: 28193.3; 2022-08-01: 20906.2; 2022-09-01: 9757.3; 2022-10-01: 11291.6; 2022-11-01: 20609.1; 2022-12-01: 21777.7; 2023-01-01: 35397.7; 2023-02-01: 32301.1; 2023-03-01: 29819.8; 2023-04-01: 26493.3; 2023-05-01: 25372.1; 2023-06-01: 21492.2; 2023-07-01: 10147
KEY QT: IC INSTRUMENT CABLES |  |  | 2022-09-12 | 2023-08-11 |  | 370721.9 | 0 | 0% | 334 |  | 370721.9 | At Completion Units | 2022-09-01: 5420.7; 2022-10-01: 15187.3; 2022-11-01: 14786.9; 2022-12-01: 26716.6; 2023-01-01: 36519.5; 2023-02-01: 47593.6; 2023-03-01: 65820.3; 2023-04-01: 57900.9; 2023-05-01: 47156.8; 2023-06-01: 31396.5; 2023-07-01: 17241.9; 2023-08-01: 4981
[17 empty] | Activity ID | Activity Name | At Completion Duration | Start | Finish | UoM | Budgeted Units | Actual Units | Units % Complete | Original Duration | Curve | Remaining Units | Spreadsheet Field | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
[17 empty] | KEY QT: EC ELECTRICAL CABLES |  |  | 2022-06-01 | 2023-06-17 |  | 441691 | 0 | 0% | 382 |  | 441691 | At Completion Units | 1963.3 | 9244.5 | 29373.6 | 63021.9 | 87547 | 74230.7 | 71261.6 | 37185 | 26544.3 | 16523 | 10293.4 | 9366.3 | 5136.4
[17 empty] | KEY QT: IC INSTRUMENT CABLES |  |  | 2022-06-11 | 2023-06-17 |  | 746102.1 | 0 | 0% | 372 |  | 746102.1 | At Completion Units | 2385.7 | 3697.8 | 16510.1 | 59341.5 | 96339.7 | 80083.8 | 113985.6 | 102121.8 | 105759.7 | 109269.8 | 38764.4 | 11523.1 | 6319.1

## INSTRUMENTATION (hidden)
INSTRUMENTAION CABLES [m]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 746102 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13877.2 | 31322.7 | 31747.2 | 37894.7 | 61216.3 | 74279.9 | 109264 | 112438.7 | 111187.2 | 111843.2 | 38764.4 | 11523.1 | 743.4 | 0 |  | 0 | 0 | 0 | 0
Urea | 370721.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537.5 | 2776.9 | 2776.9 | 7212.2 | 15187.3 | 14697.3 | 23939.7 | 33742.5 | 38561.9 | 63521.9 | 61086.3 | 50448.3 | 34581.8 | 20533.4 | 1118 |  | 0 | 0 | 0
Overall Per Month | 1116823.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14414.7 | 34099.6 | 34524.1 | 45106.9 | 76403.6 | 88977.2 | 133203.7 | 146181.2 | 149749.1 | 175365.1 | 99850.7 | 61971.4 | 35325.2 | 20533.4 | 1118 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14414.7 | 48514.3 | 83038.4 | 128145.3 | 204548.9 | 293526.1 | 426729.8 | 572911 | 722660.1 | 898025.2 | 997875.9 | 1059847.3 | 1095172.5 | 1115705.9 | 1116823.9 | 1116823.9 | 1116823.9 | 1116823.9 | 1116823.9
INSTRUMENTAION WORKS [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 678446.2 | 5.91% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4028% | 1.467% | 2.995% | 8.165% | 13.15% | 10.67% | 6.414% | 5.425% | 4.89% | 3.451% | 2.995% | 0.9591% | 0.2605% | 0% | 0% | 0% | 0% | 0%
Urea | 429330.2 | 3.74% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.0777% | 1.578% | 4.528% | 4.937% | 5.896% | 6.109% | 5.249% | 3.654% | 2.695% | 1.79% | 1.489% | 0.6042% | 0.126% | 0.02448% | 0% | 0% | 0% | 0%
Overall Per Month | 1107776.4 | 9.649% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4804% | 3.045% | 7.523% | 13.1% | 19.05% | 16.78% | 11.66% | 9.079% | 7.585% | 5.24% | 4.484% | 1.563% | 0.3865% | 0.02448% | 0% | 0% | 0% | 0%
Cumulative | 1107776.4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4804% | 3.526% | 11.05% | 24.15% | 43.2% | 59.97% | 71.64% | 80.72% | 88.3% | 93.54% | 98.03% | 99.59% | 99.98% | 100% | 100% | 100% | 100% | 100%

## Sheet5 (hidden)
Activity ID | Activity Name | At Completion Duration | Start | Finish | Budgeted Units | Actual Units | Units % Complete | Remaining Units | Curve | Spreadsheet Field | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
KEY QT: IC INSTRUMENT CABLES |  |  | 2022-06-11 | 2023-08-02 | 1116824 | 0 | 0% | 1116824 |  | Remaining Units | 14414.6 | 34099.7 | 44524.2 | 35107 | 76403.5 | 88977.3 | 133203.7 | 146181.2 | 149749.1 | 175365.1 | 99850.7 | 61971.4 | 35325.3 | 20533.4 | 1118
Area Tag Kingisepp-2: 1 Ammonia |  |  | 2022-06-11 | 2023-06-02 | 746102.1 | 0 | 0% | 746102.1 |  | Remaining Units | 13877.2 | 31322.7 | 41747.2 | 27894.7 | 61216.3 | 74279.9 | 109264 | 112438.7 | 111187.2 | 111843.2 | 38764.4 | 11523.1 | 743.4
Area Tag Kingisepp-2: 2 Urea |  |  | 2022-06-25 | 2023-08-02 | 370721.9 | 0 | 0% | 370721.9 |  | Remaining Units | 537.5 | 2776.9 | 2776.9 | 7212.2 | 15187.3 | 14697.3 | 23939.7 | 33742.5 | 38561.9 | 63521.9 | 61086.3 | 50448.3 | 34581.8 | 20533.4 | 1118

## PAINTING (hidden)
PAINTING [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 102301 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.6 | 153.4 | 1873.6 | 4580.8 | 10182.6 | 13094.7 | 13924.8 | 12587.2 | 12155.3 | 11390.6 | 7206.1 | 3190.2 | 1002.5 | 1037.3 | 1590.4 | 1735.6 | 2011.7 | 1771 | 1502.9 | 818.5 | 391.7 | 60.5 | 0 | 0 | 0
Urea | 23429.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241.5 | 680.1 | 1160.9 | 1590 | 2367.9 | 2786.8 | 3338.2 | 3947.6 | 3611.7 | 2565.4 | 948.9 | 167.2 | 23.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall Per Month | 125730.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.1 | 833.5 | 3034.5 | 6170.8 | 12550.5 | 15881.5 | 17263 | 16534.8 | 15767 | 13956 | 8155 | 3357.4 | 1026.2 | 1037.3 | 1590.4 | 1735.6 | 2011.7 | 1771 | 1502.9 | 818.5 | 391.7 | 60.5 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.1 | 1114.6 | 4149.1 | 10319.9 | 22870.4 | 38751.9 | 56014.9 | 72549.7 | 88316.7 | 102272.7 | 110427.7 | 113785.1 | 114811.3 | 115848.6 | 117439 | 119174.6 | 121186.3 | 122957.3 | 124460.2 | 125278.7 | 125670.4 | 125730.9 | 125730.9 | 125730.9 | 125730.9 | 125730.9
PAINTING [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 298112.4 | 2.597% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.02089% | 0.08099% | 0.9848% | 2.416% | 5.404% | 7.082% | 7.737% | 7.21% | 7.516% | 8.211% | 7.085% | 5.072% | 3.556% | 2.143% | 2.151% | 3.282% | 2.851% | 1.344% | 0.8893% | 0.5136% | 0.4295% | 0.04307% | 0% | 0% | 0% | 0%
Urea | 94031.1 | 0.819% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.195% | 0.5528% | 1.518% | 1.781% | 2.609% | 2.964% | 3.135% | 3.874% | 3.446% | 2.585% | 0.9873% | 0.3319% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overall Per Month | 392143.5 | 3.416% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2159% | 0.6338% | 2.503% | 4.197% | 8.013% | 10.05% | 10.87% | 11.08% | 10.96% | 10.8% | 8.072% | 5.404% | 3.556% | 2.143% | 2.151% | 3.282% | 2.851% | 1.344% | 0.8893% | 0.5136% | 0.4295% | 0.04307% | 0% | 0% | 0% | 0%
Cumulative | 392143.5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2159% | 0.8497% | 3.352% | 7.549% | 15.56% | 25.61% | 36.48% | 47.56% | 58.53% | 69.32% | 77.39% | 82.8% | 86.35% | 88.5% | 90.65% | 93.93% | 96.78% | 98.12% | 99.01% | 99.53% | 99.96% | 100% | 100% | 100% | 100% | 100%

## INSULATION (hidden)
INSULATION [m2]
| Sum |  | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 163457.6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.1 | 244.9 | 1220.3 | 3370.8 | 7429.1 | 15159.1 | 25645.2 | 29709.5 | 30725 | 17445.7 | 12352.3 | 10670.3 | 6754.6 | 2692.7 | 0 | 0 | 0
Urea | 73420.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 110.4 | 955.1 | 3395.6 | 7894.5 | 11946 | 10322.6 | 6717.5 | 5001.5 | 5676.3 | 9047.9 | 7875 | 3847.5 | 607.7 | 0 | 0 | 0
Overall Per Month | 236877.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.6 | 355.3 | 2175.4 | 6766.4 | 15323.6 | 27105.1 | 35967.8 | 36427 | 35726.5 | 23122 | 21400.2 | 18545.3 | 10602.1 | 3300.4 | 0 | 0 | 0 | 0
Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.6 | 415.9 | 2591.3 | 9357.7 | 24681.3 | 51786.4 | 87754.2 | 124181.2 | 159907.7 | 183029.7 | 204429.9 | 222975.2 | 233577.3 | 236877.7 | 236877.7 | 236877.7 | 236877.7 | 236877.7
INSULATION [%]
| MHRS | WEIGHT [%] | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
Ammonia | 714705.8 | 6.225% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.01151% | 0.07357% | 0.4153% | 1.252% | 3.08% | 6.907% | 12.26% | 14.22% | 14.15% | 7.447% | 5.569% | 6.236% | 4.506% | 1.02% | 0.1952% | 0% | 0%
Urea | 209359.5 | 1.824% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.006699% | 0.0329% | 0.2908% | 1.086% | 2.519% | 3.816% | 3.299% | 2.181% | 1.645% | 1.735% | 2.594% | 2.2% | 1.075% | 0.1761% | 0% | 0% | 0% | 0%
Overall Per Month | 924065.3 | 8.049% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.01821% | 0.1065% | 0.7061% | 2.338% | 5.598% | 10.72% | 15.56% | 16.4% | 15.8% | 9.183% | 8.163% | 8.436% | 5.581% | 1.196% | 0.1952% | 0% | 0% | 0%
Cumulative | 924065.3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.01821% | 0.1247% | 0.8308% | 3.169% | 8.767% | 19.49% | 35.05% | 51.45% | 67.25% | 76.43% | 84.59% | 93.03% | 98.61% | 99.8% | 100% | 100% | 100% | 100%

## DATABASE (hidden)
Activity ID | Activity Name | Original Duration | Start | Finish | Remaining Units | Curve | Spreadsheet Field | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01
Area Tag Kingisepp-2: 1 Ammonia |  | 1001 | 20.12.19 A | 2023-08-28 | 16718831.7 |  | Remaining Units |  |  |  | 24727.8 | 45547.7 | 43314.7 | 178745.8 | 380635.5 | 581508.7 | 970523 | 1080498.4 | 1097319.2 | 1172049.8 | 1242976.4 | 1344506 | 1381362.5 | 1276470.7 | 1216365.6 | 1039099 | 932665.8 | 759580.1 | 552047 | 516715.4 | 377039.8 | 174091.3 | 169800.3 | 106302.6 | 37208.7 | 8848 | 6278.4 | 2603.5
KEY QT: PL PILING |  | 330 | 20.12.19 A | 2021-10-26 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EW EXCAVATION |  | 180 | 2021-05-11 | 2021-11-06 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGE UNDERGROUND - EARTHING |  | 403 | 2021-07-20 | 2022-08-26 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 317 | 2021-08-31 | 2022-07-13 | 32000 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659.3 | 1052.2 | 2055.5 | 3683.3 | 4600.5 | 4517.6 | 5056.9 | 4497.4 | 3242.4 | 1688.5 | 854.6 | 91.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGG UNDERGROUND - GRAVITY PIPES |  | 495 | 2021-09-30 | 2023-02-06 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: BF BACKFILLING |  | 421 | 2021-08-13 | 2022-10-07 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: FD FOUNDATION |  | 390 | 2021-05-11 | 2022-06-04 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EL ELEVATION |  | 428 | 2021-06-05 | 2022-08-06 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: PV PAVING |  | 219 | 2022-08-23 | 2023-03-29 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: FSH FINISHING |  | 324 | 2022-03-24 | 2023-02-10 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: GT GROUTING |  | 544 | 2021-09-13 | 2023-03-10 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: ST MAIN STEEL STRUCTURE |  | 543 | 2021-08-03 | 2023-01-27 | 11361823.2 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 |  | 85317.4 | 340786.8 | 465649.7 | 616789.2 | 838306.9 | 898026.3 | 817383.5 | 1136123.8 | 1188017.7 | 1217984.5 | 1111917.4 | 844198 | 535447.5 | 420180.8 | 387239.9 | 178776.1 | 111048.5 | 106935.6 | 61693.6 |  | 0 | 0 | 0 | 0 | 0
KEY QT: SS SECONDARY STEEL |  | 420 | 2022-01-25 | 2023-03-20 | 840908.2 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 33510.8 | 38443.9 | 38538.1 | 68369 | 167196.5 | 218496.6 | 103253.9 | 59345.1 | 53413.4 | 39682.9 | 334.3 | 8022.4 | 9025.2 | 2674.1 | 0 | 0 | 0 | 0
KEY QT: CD CLADDING |  | 471 | 2022-01-26 | 2023-05-11 | 33149.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3247.5 | 2164.3 | 1164.3 | 998.9 | 1280.9 | 3044.6 | 4204.7 | 2636.2 | 1264.6 | 1084.9 | 1538 | 176.9 | 2609 | 4746.5 | 2988.2 | 0 | 0 | 0
KEY QT: EQ EQUIPMENT |  | 552 | 2021-08-25 | 2023-02-27 | 11072.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322.3 | 293.3 | 368.6 | 780.9 | 925.2 | 1097.8 | 1176.1 | 1183.1 | 1220.9 | 1102.1 | 937.4 | 743.1 | 453 | 284.3 | 160.9 | 23.1 | 0 | 0 | 0 | 0 | 0 |  | 0
KEY QT: SUP SUPPORTS |  | 450 | 2022-02-02 | 2023-04-28 | 826381 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 667.8 | 5255.9 | 14320.4 | 19677.5 | 68738.7 | 106001.1 | 121164.2 | 119619.6 | 111808.5 | 112769.5 | 71519.2 | 37601.7 | 19211.1 | 15773.7 | 2144.1 | 0 | 0 | 0
KEY QT: SB PIPING SB |  | 400 | 2022-03-25 | 2023-04-28 | 61709.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7 | 132.4 | 176.9 | 2498.4 | 6372.3 | 8914.6 | 10054.5 | 10181.7 | 9757.9 | 6349.9 | 3505 | 2008.7 | 1629.6 | 113.3 | 0 | 0 | 0
KEY QT: LBP PIPING LB PREFAB |  | 376 | 2021-10-23 | 2022-11-03 | 255590.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 1379.6 | 3758 | 4832.6 | 6458.5 | 11333.6 | 18432.9 | 27113.3 | 35218.8 | 36221.9 | 35420.5 | 30179.9 | 18129.7 | 12865.5 | 8063.4 | 4516.9 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: LBE PIPING LB ERECT |  | 427 | 2022-01-27 | 2023-03-29 | 137625.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817.6 | 3692.8 | 5696.5 | 7284.6 | 13577.6 | 17686.3 | 18495.7 | 15241.8 | 16152 | 14737.3 | 10765.1 | 5914.1 | 3203.5 | 3426 | 934.7 | 0 | 0 | 0 | 0
KEY QT: EC ELECTRICAL CABLES |  | 384 | 2022-04-14 | 2023-05-02 | 746084 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6219.1 | 11091.2 | 10385.5 | 74986.4 | 93467 | 99198.5 | 85116 | 99026.8 | 83227.5 | 73605.8 | 76628.2 | 24281.5 | 8850.5 | 0 | 0 | 0 |  | 0
KEY QT: IC INSTRUMENT CABLES |  | 319 | 2022-06-20 | 2023-05-05 | 890201.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17706.3 | 30736 | 59608.5 | 110176.9 | 160606.3 | 160288.4 | 125913.7 | 99327.4 | 74757.6 | 35542.6 | 15538.2 | 0 | 0 | 0 |  | 0 | 0
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 236 | 2022-09-26 | 2023-05-20 | 100055.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100.7 | 8592 | 13351 | 12459.2 | 12028.2 | 12829.8 | 13547 | 22509.8 | 2637.4 | 0 | 0
KEY QT: PA PAINTING |  | 625 | 2021-10-26 | 2023-07-12 | 102301 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.6 | 153.4 | 1873.6 | 4580.8 | 10182.6 | 13094.7 | 13924.8 | 12587.2 | 12155.3 | 11390.6 | 7206.1 | 3190.2 | 1002.5 | 1037.3 | 1590.4 | 1735.6 | 2011.7 | 1771 | 1502.9 | 818.5 | 391.7 | 60.5
KEY QT: IN INSULATION |  | 425 | 2022-06-30 | 2023-08-28 | 163457.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.1 | 244.9 | 1220.3 | 3370.8 | 7429.1 | 15159.1 | 25645.2 | 29709.5 | 30725 | 17445.7 | 12352.3 | 10670.3 | 6754.6 | 1527.1 | 1165.6
Area Tag Kingisepp-2: 2 Urea |  | 893 | 01.11.20 A | 2023-07-22 | 15522466.6 |  | Remaining Units |  |  |  |  | 38958.5 | 260289.3 | 317704.8 | 230593.8 | 309123.6 | 314402.3 | 418366.2 | 543437.1 | 629881.7 | 628358.7 | 596085.9 | 629061.4 | 825572.3 | 1124154.6 | 1346852 | 1451924.8 | 1621735.8 | 1626914.3 | 1253915.3 | 665999.3 | 393448 | 169957.3 | 91671.2 | 23331 | 6788.4 | 3939
KEY QT: PL PILING |  | 233 | 01.11.20 A | 2021-12-29 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EW EXCAVATION |  | 333 | 2021-05-11 | 2022-04-08 | 161740.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 36110.1 | 52269.4 | 7909.7 | 904.7 | 3617.4 | 2080.5 | 1794.7 | 1728.2 | 16112.2 | 20459.4 | 18754.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGE UNDERGROUND - EARTHING |  | 383 | 2021-07-17 | 2022-08-03 | 57.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 3.4 | 4.1 | 4.6 | 5.2 | 5.2 | 4.8 | 5.4 | 4.5 | 4.1 | 4 | 4 | 3.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 420 | 2021-06-05 | 2022-07-29 | 17100 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 472 | 494.4 | 762.2 | 1346.5 | 1756.9 | 2022.7 | 2032.5 | 1876.1 | 1999.2 | 1674.8 | 1321.1 | 686 | 439.7 | 215.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGG UNDERGROUND - GRAVITY PIPES |  | 654 | 2021-07-06 | 2023-04-20 | 18213.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 353.3 | 400.4 | 464.1 | 753.5 | 911 | 989.5 | 1320.9 | 1306.1 | 1375.1 | 1375.1 | 1375.1 | 1414.5 | 1272 | 1267.8 | 911 | 946.1 | 495 | 428.4 | 295.9 | 214.9 | 85.9 | 0 | 0 | 0 | 0
KEY QT: BF BACKFILLING |  | 424 | 2021-08-07 | 2022-10-05 | 74859.2 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 68.9 | 164.1 | 1657.7 | 2808.1 | 3971.9 | 3750.6 | 2775.6 | 2560 | 3032.9 | 4112.9 | 5291.2 | 5327.4 | 5327 | 4237.4 | 7925.7 | 21847.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: FD FOUNDATION |  | 531 | 20.04.21 A | 2022-07-25 | 25654.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 2167.2 | 2794.1 | 2515.8 | 2402.4 | 2354 | 2307.6 | 2319.2 | 1578.6 | 1298.7 | 1259.7 | 1353.4 | 1244.2 | 1396.8 | 483.1 | 179.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EL ELEVATION |  | 406 | 2021-06-15 | 2022-07-25 | 7318.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0.6 | 344 | 1126 | 984.4 | 812.3 | 826.1 | 440.4 | 426.5 | 454.8 | 386.3 | 393.6 | 329 | 289 | 90.8 | 71.2 | 68.2 | 68.2 | 68.2 | 70.9 | 68.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: PV PAVING |  | 422 | 2022-03-23 | 2023-05-18 | 13232.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.1 | 229.7 | 430.6 | 962.5 | 1468.9 | 1529.5 | 1507.1 | 1781.3 | 1757.7 | 1192.9 | 598 | 332.6 | 449.3 | 667.7 | 149 | 0 | 0 | 0
KEY QT: FSH FINISHING |  | 258 | 2022-03-11 | 2022-11-23 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: GT GROUTING |  | 583 | 2021-09-23 | 2023-04-28 | 146.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0.3 | 1.7 | 0 | 0 | 1.9 | 1.6 | 1.9 | 3.6 | 5.4 | 7.7 | 13.1 | 11.1 | 10.8 | 5.3 | 18.5 | 41.7 | 12 | 5.5 | 0 | 0 | 0 | 0
KEY QT: ST MAIN STEEL STRUCTURE |  | 612 | 2021-07-03 | 2023-03-06 | 12153070.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 279842 | 280543.7 | 212023.9 | 191634.4 | 215450.2 | 343321.9 | 339790.9 | 541326.7 | 534888.4 | 504908.3 | 534404.2 | 607322.2 | 850422.1 | 1141931.5 | 1167045.1 | 1148006.5 | 1140992.3 | 1058396.4 | 640977.2 | 261615.5 | 158226.7 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: SS SECONDARY STEEL |  | 470 | 2022-01-12 | 2023-04-26 | 1042969.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908.4 | 15856.2 | 37800.8 | 20018.2 | 10691.4 | 12316.9 | 12390.2 | 26858 | 94906.9 | 111189.5 | 134427.6 | 171193.5 | 180084.8 | 104233.6 | 43963 | 40706.4 | 24423.9 | 0 | 0 | 0 | 0
KEY QT: CD CLADDING |  | 408 | 2022-03-15 | 2023-04-26 | 54536.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.7 | 1785.6 | 3222 | 3309.2 | 3162.6 | 1446.2 | 1460.7 | 3393.1 | 5277.8 | 6449.8 | 6723.6 | 8471.6 | 5360.8 | 2773 | 1663.8 | 0 | 0 | 0 | 0
KEY QT: EQ EQUIPMENT |  | 477 | 2021-11-10 | 2023-03-01 | 5000.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 147 | 170.6 | 287 | 425 | 534.2 | 597.6 | 617 | 618.7 | 526.1 | 407.2 | 304.3 | 164 | 93.6 | 51.4 | 9.1 | 0.3 | 0 | 0 | 0 | 0 | 0
KEY QT: SUP SUPPORTS |  | 373 | 2022-04-28 | 2023-05-05 | 273360.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.1 | 2573.5 | 6737.8 | 17332.7 | 38448.1 | 46682.8 | 44875.8 | 36687.1 | 26890.5 | 17164.7 | 12928.7 | 11961.9 | 10945.2 | 0 | 0 | 0 | 0
KEY QT: SB PIPING SB |  | 402 | 2022-03-30 | 2023-05-05 | 22255.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367.1 | 1133.8 | 1133.8 | 1151.7 | 1688 | 1620 | 2179.7 | 2724.9 | 2805.4 | 2570.2 | 1460.8 | 1231.8 | 1140.4 | 1048.3 | 0 | 0 | 0 | 0
KEY QT: LBP PIPING LB PREFAB |  | 450 | 2021-08-03 | 2022-10-26 | 116574.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 1053.3 | 2352.3 | 3082.3 | 4474.5 | 6895.9 | 8117.5 | 8682.9 | 15591.3 | 14286.2 | 12688 | 11619.1 | 11544.6 | 7061.2 | 4745.1 | 3376.3 | 1003.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: LBE PIPING LB ERECT |  | 471 | 2021-12-21 | 2023-04-05 | 62770.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 669.6 | 1190.4 | 2678.5 | 3025.7 | 4445.5 | 4761.8 | 5456.2 | 6398.6 | 7487.9 | 7060.3 | 6621.8 | 6209.5 | 3077.7 | 1713.5 | 1180 | 545.6 | 0 | 0 | 0 | 0 | 0
KEY QT: EC ELECTRICAL CABLES |  | 317 | 2022-06-23 | 2023-05-05 | 507733.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3030.6 | 25155.7 | 43843.6 | 42619.3 | 66783.9 | 87242.5 | 96960.4 | 55711 | 34836.1 | 23083.9 | 16059.1 | 12407 | 0 | 0 | 0 | 0
KEY QT: IC INSTRUMENT CABLES |  | 334 | 2022-06-20 | 2023-05-20 | 516851 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173.1 | 14160.8 | 26052.4 | 39965.9 | 58151.2 | 95004 | 108765.4 | 80161.2 | 56774.6 | 24537.9 | 7599.1 | 1505.4 | 0 | 0 | 0
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 253 | 2022-10-10 | 2023-06-20 | 45179.2 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 4699.6 | 5658.2 | 6689 | 7234.6 | 6391.1 | 5455.3 | 5605.1 | 2527.4 | 715.9 | 0 | 0
KEY QT: PA PAINTING |  | 332 | 2021-12-08 | 2022-11-04 | 23429.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241.5 | 680.1 | 1160.9 | 1590 | 2367.9 | 2786.8 | 3338.2 | 3947.6 | 3611.7 | 2565.4 | 948.9 | 167.2 | 23.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: IN INSULATION |  | 387 | 2022-07-01 | 2023-07-22 | 73420.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 110.4 | 955.1 | 3395.6 | 7894.5 | 11946 | 10322.6 | 6717.5 | 5001.5 | 5676.3 | 9047.9 | 7875 | 3847.5 | 607.7 | 0
KEY QT: RW RAILWAYS |  | 79 | 2022-10-05 | 2022-12-23 | 2614.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.1 | 1050.5 | 1346.7 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Area Tag Kingisepp-2: 0 Common |  | 208 | 2022-11-11 | 2023-06-06 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: RD ROADS |  | 208 | 2022-11-11 | 2023-06-06 | 0 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 1230000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15478.2731 | 26868.4141 | 52107.817 | 96313.0718 | 140396.8173 | 140118.9195 | 110069.6719 | 86828.7909 | 65350.6688 | 31070.1879 | 13582.9904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3647.9886 | 12378.912 | 22774.1629 | 34936.8933 | 50833.8926 | 83049.4148 | 95079.1843 | 70074.3206 | 49630.5135 | 21450.2362 | 6642.8867 | 1315.9718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity ID | Activity Name | Original Duration | Start | Finish | Remaining Units | Curve | Spreadsheet Field | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 45170
Area Tag Kingisepp-2: 1 Ammonia |  | 771 | 2021-08-09 | 2023-09-18 | 5819735.4 |  | Remaining Units | [6 empty] | 11232.7 | 24896.3 | 34233.9 | 55489.5 | 94155 | 141335.9 | 183734.1 | 263544.2 | 304724.5 | 339400.5 | 350913.2 | 375687.7 | 460287.5 | 430707.6 | 471523.8 | 456609.2 | 482234.9 | 361303.2 | 269330.2 | 238651.2 | 186163.3 | 125330.9 | 67494.7 | 48893.9 | 35016.6 | 6840.9
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 317 | 2021-09-21 | 2022-08-03 | 23228.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.2 | 665.8 | 1423.1 | 2284.2 | 3570.3 | 3853.2 | 4282.6 | 3382.5 | 1820.7 | 1300.1 | 502.5 | 51.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: MS MASONARY |  | 317 | 2022-04-21 | 2023-03-03 | 39342.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2580.4 | 11368.7 | 11368.7 | 8788.3 | 245.3 | 1275.6 | 1275.6 | 1030.3 | 451.9 | 469.9 | 433.8 | 54.2 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: ST MAIN STEEL STRUCTURE |  | 543 | 2021-08-24 | 2023-02-17 | 643191.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 2875.6 | 12667.3 | 19289.4 | 22806.4 | 39454.8 | 45655.4 | 49078.7 | 68372.2 | 76004.2 | 71707.8 | 61818.1 | 53139.8 | 42561.3 | 28182.6 | 23546.9 | 10680.8 | 6094.9 | 5869.2 | 3386.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: SS SECONDARY STEEL |  | 407 | 2022-02-28 | 2023-04-10 | 67209 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.6 | 1718.5 | 2514.9 | 3012.8 | 6282.5 | 14110.3 | 17406.3 | 7553.8 | 4089.6 | 3711.1 | 2728.6 | 67.8 | 1626.4 | 1829.7 | 542.1 | 0 | 0 | 0 | 0 | 0
KEY QT: CD CLADDING |  | 483 | 2022-02-04 | 2023-06-01 | 92464.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1508.5 | 1452.6 | 1412.6 | 617.1 | 2767.5 | 8454 | 5182.5 | 4690.7 | 1328.7 | 16510.4 | 19004.9 | 10970.1 | 2887.9 | 10313.9 | 5363.2 | 0 | 0 | 0 | 0
KEY QT: EQ EQUIPMENT |  | 552 | 2021-09-15 | 2023-03-20 | 568809.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4737.1 | 13535.8 | 20205.5 | 30641.9 | 40897.8 | 58481.5 | 68780.9 | 70951.4 | 72836.3 | 60463.2 | 47842.4 | 30284.5 | 24643 | 15926.1 | 6660.9 | 1920.8 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: SUP SUPPORTS |  | 450 | 2022-02-23 | 2023-05-19 | 213742.6 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.6 | 194.8 | 1526.9 | 4115.7 | 5526.2 | 17172.5 | 27355.6 | 31569.8 | 31125.1 | 28788.1 | 28979 | 17698.4 | 9598.5 | 5212.6 | 4278.8 | 569 | 0 | 0 | 0 | 0
KEY QT: SB PIPING SB |  | 400 | 2022-04-15 | 2023-05-19 | 334830.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.6 | 718.7 | 960 | 13556.3 | 34575.3 | 48369.6 | 54554.4 | 55244.4 | 52945.2 | 34453.7 | 19017.7 | 10898.8 | 8842 | 614.6 | 0 | 0 | 0 | 0
KEY QT: LBP PIPING LB PREFAB |  | 472 | 2021-08-09 | 2022-11-24 | 843198.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 8357.2 | 10864.3 | 10864.3 | 21155 | 38364.1 | 64420.5 | 89417 | 114956.8 | 119132.3 | 116853.1 | 99564.2 | 59810.3 | 42443.7 | 26601.5 | 14901.4 | 5492.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: LBE PIPING LB ERECT |  | 427 | 2022-02-17 | 2023-04-19 | 431091 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2561 | 11567.1 | 17843.4 | 22818 | 42530 | 55399.6 | 57935 | 47742.5 | 50593.6 | 46162.4 | 33719.9 | 18524.9 | 10034.6 | 10731.3 | 2927.7 | 0 | 0 | 0 | 0 | 0
KEY QT: TRA TRAYS |  | 399 | 2022-04-05 | 2023-05-09 | 249677.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4234.9 | 16743.6 | 28933 | 32676.6 | 36226.8 | 37603.3 | 31471.8 | 22242.4 | 18488.4 | 13057.5 | 5223.2 | 2066.5 | 614.9 | 94.8 | 0 | 0 | 0 | 0
KEY QT: EC ELECTRICAL CABLES |  | 384 | 2022-05-05 | 2023-05-23 | 248603.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468.3 | 2294.3 | 4211.6 | 15264 | 38175.1 | 42479.3 | 32335.4 | 28143.8 | 33463.3 | 28478.8 | 17371.5 | 4868.4 | 1050.1 | 0 | 0 | 0 | 0
KEY QT: TER ELECTRICAL TERMINATIONS |  | 289 | 2022-09-01 | 2023-06-17 | 171587.2 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023.6 | 19859.6 | 36511.8 | 40687.3 | 26145 | 10101.1 | 16488.4 | 12539 | 4769.2 | 462.2 | 0 | 0 | 0
KEY QT: EEQ ELECTRICAL EQ |  | 315 | 2022-07-19 | 2023-05-29 | 30706 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 6710 | 6818.2 | 3335.4 | 4431.6 | 2150.3 | 642.3 | 1025.7 | 3999.7 | 1442 | 45.8 | 0 | 0 | 0 | 0
KEY QT: OEL OTHER ELECRICAL |  | 357 | 2022-06-01 | 2023-05-23 | 110144.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.2 | 6657.4 | 18731.4 | 30073 | 31322.5 | 9933.8 | 6314.6 | 4871.3 | 1014.6 | 465.9 | 262.9 | 75.3 | 0 | 0 | 0 | 0
KEY QT: ETH EARTHING |  | 325 | 2022-05-09 | 2023-03-29 | 62353.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.3 | 1425.6 | 4524.6 | 6443.7 | 6155.3 | 7679.1 | 20116.3 | 6647 | 6975.5 | 2083 | 30 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: IC INSTRUMENT CABLES |  | 319 | 2022-07-11 | 2023-05-26 | 243904.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4461.6 | 7745.9 | 15022.2 | 27964 | 48352.9 | 51814.8 | 31768.9 | 25042.5 | 18850.1 | 8962.4 | 3919.6 | 0 | 0 | 0 | 0
KEY QT: FIN FIELD INSTRUMENTS [INCL. F&G] |  | 254 | 2022-08-02 | 2023-04-12 | 85894.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4334.9 | 7771.6 | 13718.3 | 16586.7 | 17358.9 | 13923 | 7740.3 | 3696.4 | 764.7 | 0 | 0 | 0 | 0 | 0
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 240 | 2022-10-17 | 2023-06-14 | 58681.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397.1 | 9900.5 | 11561.3 | 5993 | 5701.1 | 6081 | 6359.7 | 10457.1 | 1230.9 | 0 | 0 | 0
KEY QT: OIN OTHER INSTRMENTATION |  | 353 | 2022-08-08 | 2023-07-26 | 289964.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4169.2 | 10386.3 | 47369.9 | 70826.4 | 37461 | 19369.9 | 21613.2 | 25547.9 | 22137.5 | 18804 | 9394.2 | 2885.3 | 0 | 0
KEY QT: PA PAINTING |  | 644 | 2021-11-13 | 2023-08-18 | 298112.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.9 | 317.6 | 3862 | 9474.6 | 21190.4 | 27771.6 | 30338.7 | 28272.2 | 29472.7 | 32199.9 | 27782.3 | 19889.1 | 13945.5 | 8405.2 | 8433.9 | 12870.2 | 11179.6 | 5270.4 | 3487.3 | 2014.2 | 1684.2 | 168.9 | 0
KEY QT: IN INSULATION |  | 425 | 2022-07-21 | 2023-09-18 | 714705.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.4 | 679.8 | 3837.4 | 11572.6 | 28456.8 | 63829.7 | 113306.5 | 131380.8 | 130767.6 | 68816.6 | 51463.1 | 57620.7 | 41639.2 | 9424.7 | 1803.9
Area Tag Kingisepp-2: 2 Urea |  | 914 | 10.04.21 A | 2023-08-12 | 5631412.1 |  | Remaining Units |  |  |  |  | 96080.8 | 126708.5 | 154830.8 | 151542.1 | 137081.8 | 176394.9 | 194543.2 | 155531.7 | 163185.5 | 250843.1 | 247082.4 | 284448.1 | 276709.6 | 274888.1 | 322030.4 | 343536.5 | 382190 | 408382.5 | 421096.2 | 337088.1 | 252258.1 | 209638.6 | 102734.2 | 86556 | 49168 | 19561.3 | 7301.6
KEY QT: UGE UNDERGROUND - EARTHING |  | 406 | 2021-08-07 | 2022-09-16 | 104385.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 5143 | 6404.5 | 7289.3 | 8147 | 9312.5 | 9236 | 8525.5 | 9550.4 | 8247.5 | 7462.8 | 7287.9 | 7287.9 | 7062.7 | 3428.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EW EXCAVATION |  | 385 | 10.04.21 A | 2022-04-29 | 24925.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 10248.2 | 9358.8 | 1112.3 | 498.6 | 803.8 | 364.5 | 314.4 | 302.7 | 579.8 | 700.5 | 642.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 420 | 2021-06-26 | 2022-08-19 | 23446 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 187.6 | 653.8 | 1058.4 | 1428.2 | 2392.8 | 3058.7 | 3274.4 | 3022.5 | 2967.6 | 2199.9 | 1412.1 | 1010.2 | 552 | 227.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: UGG UNDERGROUND - GRAVITY PIPES |  | 654 | 2021-07-27 | 2023-05-11 | 17823.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 81.5 | 151.3 | 388.2 | 487.8 | 629.2 | 689.7 | 885.8 | 1345 | 1389.8 | 1581.2 | 1581.2 | 1581.2 | 1604.6 | 1295.2 | 1288.2 | 689.7 | 716.2 | 501.8 | 450.3 | 259.5 | 161.7 | 64.7 | 0 | 0 | 0 | 0
KEY QT: BF BACKFILLING |  | 443 | 09.08.21 A | 2022-10-26 | 38166.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 89.2 | 211.5 | 1703.5 | 1478 | 1914.1 | 2256.8 | 2610.1 | 1084.7 | 1620.5 | 2930.4 | 3393.9 | 3185.7 | 3185.6 | 3083.3 | 3573.2 | 5845.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: FD FOUNDATION |  | 593 | 20.04.21 A | 2022-09-26 | 1000308.4 |  | Remaining Units | 0 | 0 | 0 | 0 | 110683.4 | 123832.1 | 139764 | 108440.3 | 95146.7 | 96238.2 | 99694.2 | 57834.9 | 31865.2 | 54448.2 | 20478.4 | 32621.6 | 25947.1 | 2397.3 | 667.5 | 249.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: EL ELEVATION |  | 418 | 2021-06-24 | 2022-08-15 | 114357.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 8.6 | 38.6 | 21040 | 16419.5 | 11006 | 12120.1 | 7237.9 | 7121.1 | 7984.2 | 8938.1 | 8637 | 6948.2 | 6138.2 | 707.4 | 12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: PV PAVING |  | 422 | 2022-04-13 | 2023-06-08 | 78203.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146.4 | 3487.9 | 3683.4 | 5544.2 | 6359.8 | 7621.1 | 7202.9 | 7751.3 | 8155.2 | 8092.3 | 6260.8 | 4219.5 | 2556.9 | 4225.9 | 896.1 | 0 | 0 | 0
KEY QT: FSH FINISHING |  | 457 | 2022-04-01 | 2023-07-01 | 210460 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540.9 | 7032.3 | 7032.3 | 8059 | 4001.9 | 1066.2 | 39.5 | 0 | 0 | 18803.5 | 34975.9 | 56194.4 | 44133.1 | 3393.3 | 7750.1 | 16791.8 | 645.8 | 0 | 0
KEY QT: GT GROUTING |  | 583 | 2021-10-14 | 2023-05-19 | 18540.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377.9 | 126 | 38 | 215.5 | 0 | 3.2 | 238.5 | 197.5 | 237.2 | 454.2 | 682.7 | 1015.7 | 1662.5 | 1398.4 | 1366.7 | 673 | 2329.8 | 5278.5 | 1548 | 697.2 | 0 | 0 | 0 | 0
KEY QT: ST MAIN STEEL STRUCTURE |  | 686 | 2021-07-01 | 2023-05-17 | 607328.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 12635.4 | 13502.2 | 10786.3 | 10786.3 | 10786.3 | 17434.1 | 18843.7 | 27573.3 | 25199.6 | 23448.7 | 25189.1 | 25967.4 | 42843.9 | 60960.5 | 58702.7 | 57749.1 | 57397.8 | 53270.3 | 32353.4 | 13333 | 8183.3 | 239 | 143.4 | 0 | 0 | 0 | 0
KEY QT: SS SECONDARY STEEL |  | 488 | 2022-01-15 | 2023-05-17 | 96788 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 1572.2 | 2161.6 | 1109.8 | 727.3 | 866 | 871.7 | 2414 | 12406.7 | 13424.5 | 14037.8 | 16641.1 | 16013.3 | 7255.1 | 2747.9 | 2544.4 | 1526.6 | 0 | 0 | 0 | 0
KEY QT: CD CLADDING |  | 418 | 2022-03-26 | 2023-05-17 | 150592.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.8 | 4096.5 | 9077 | 6714.9 | 6427.7 | 5191.8 | 4983.6 | 10186 | 15271.1 | 22450.7 | 24220 | 15687.6 | 12742.6 | 8429.1 | 5057.5 | 0 | 0 | 0 | 0
KEY QT: EQ EQUIPMENT |  | 477 | 2021-12-01 | 2023-03-22 | 350997 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198.6 | 8578 | 11240.5 | 15270.4 | 17473.4 | 19607.3 | 22961.7 | 27101.2 | 36939 | 36604 | 37731.4 | 36337.7 | 28282.4 | 26441.4 | 19994.3 | 4084.4 | 151.3 | 0 | 0 | 0 | 0 | 0
KEY QT: SUP SUPPORTS |  | 373 | 2022-05-19 | 2023-05-26 | 77055 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.1 | 752.5 | 1959.6 | 5162 | 11354.4 | 13612.5 | 13033.6 | 10402.6 | 7276.4 | 4508.7 | 3231.8 | 2989.6 | 2733.2 | 0 | 0 | 0 | 0
KEY QT: SB PIPING SB |  | 402 | 2022-04-20 | 2023-05-26 | 215604.7 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3556.5 | 10983.4 | 10983.4 | 11157.6 | 16352.1 | 15694.1 | 21115.8 | 26397.8 | 27177.5 | 24898.5 | 14151.9 | 11933.4 | 11047.1 | 10155.6 | 0 | 0 | 0 | 0
KEY QT: LBP PIPING LB PREFAB |  | 471 | 2021-08-03 | 2022-11-16 | 679398 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 10911.7 | 12454.4 | 16708.9 | 25966.8 | 39632.1 | 45713.8 | 50604.2 | 90866.4 | 83260.2 | 73946.2 | 67716.2 | 67282.4 | 41152.8 | 27654.6 | 19677.3 | 5850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: LBE PIPING LB ERECT |  | 492 | 2021-12-21 | 2023-04-26 | 352989.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394.7 | 3765.6 | 6694.4 | 15062.4 | 17014.9 | 24999.4 | 26777.6 | 30682.6 | 35982.4 | 42108.2 | 39703.5 | 37237.5 | 34919.2 | 17307.7 | 9635.9 | 6635.5 | 3068.3 | 0 | 0 | 0 | 0 | 0
KEY QT: TRA TRAYS |  | 386 | 2022-03-22 | 2023-04-11 | 209116.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1694 | 6885.7 | 17544.8 | 26485 | 27429.2 | 21960.8 | 19862.5 | 21113.2 | 20292 | 20938 | 15405.8 | 7070.3 | 2217.9 | 217.7 | 0 | 0 | 0 | 0 | 0
KEY QT: EC ELECTRICAL CABLES |  | 337 | 2022-06-24 | 2023-05-26 | 207385.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945.8 | 2354.9 | 8012.6 | 16292 | 28994.5 | 49786.7 | 39520.9 | 25280.7 | 16721.5 | 12038.5 | 5679.3 | 1758.4 | 0 | 0 | 0 | 0
KEY QT: TER ELECTRICAL TERMINATIONS |  | 255 | 2022-10-10 | 2023-06-21 | 103100.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3625.6 | 10751.4 | 21124 | 22298.3 | 14569.5 | 9453.8 | 9196.3 | 10040.8 | 2040.8 | 0 | 0 | 0
KEY QT: EEQ ELECTRICAL EQ |  | 267 | 2022-06-24 | 2023-03-17 | 42382.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.5 | 212.2 | 1118.8 | 8154.1 | 6842.4 | 11127.3 | 6251.4 | 3309.2 | 4327.6 | 962.8 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: OEL OTHER ELECRICAL |  | 277 | 2022-05-14 | 2023-02-14 | 56168 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248.9 | 1419.6 | 7990.4 | 11951.6 | 11407.2 | 14654.2 | 6407.3 | 1606.5 | 429.2 | 53.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: ETH EARTHING |  | 299 | 2022-03-24 | 2023-01-16 | 48089.8 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.3 | 1173.9 | 2755.4 | 2440.9 | 1472.8 | 1162.9 | 6974.7 | 8678.7 | 16185.9 | 6433.7 | 699.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KEY QT: IC INSTRUMENT CABLES |  | 334 | 2022-07-11 | 2023-06-10 | 106242.3 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860.7 | 2920.7 | 5374.5 | 8257.8 | 11991.2 | 19492.5 | 22283.3 | 16449.1 | 11674.5 | 5054.6 | 1571.3 | 312.1 | 0 | 0 | 0
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 258 | 2022-10-26 | 2023-07-11 | 23136.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.5 | 903.1 | 2891.4 | 4318.8 | 4140.8 | 4659.4 | 3565.9 | 1892.7 | 481.1 | 94.2 | 0 | 0
KEY QT: OIN OTHER INSTRMENTATION |  | 374 | 2022-08-02 | 2023-08-10 | 299951 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14563.9 | 44780.5 | 46244.7 | 52415.8 | 45294.6 | 31540.4 | 19884.7 | 13516.4 | 11207.2 | 13029.8 | 5899.8 | 1302 | 271.2 | 0
KEY QT: PA PAINTING |  | 616 | 2021-11-05 | 2023-07-13 | 94031.1 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 764.6 | 2167.9 | 5951.4 | 6984.4 | 10231.6 | 11622.8 | 12294.5 | 15192.9 | 13512.8 | 10135 | 3871.7 | 1301.5
KEY QT: IN INSULATION |  | 387 | 2022-07-22 | 2023-08-12 | 209359.5 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.9 | 304 | 2687.2 | 10030.8 | 23273.9 | 35258.1 | 30482.2 | 20155.8 | 15200.7 | 16035.9 | 23971.6 | 20333.6 | 9936.6 | 1627.2 | 0
KEY QT: RW RAILWAYS |  | 79 | 2022-10-26 | 2023-01-13 | 51315.9 |  | Remaining Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3678.9 | 19620.8 | 20375.4 | 7640.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Activity ID | Activity Name | Original Duration | Start | Finish | Remaining Units | Curve | Spreadsheet Field | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
[8 empty] | KEY QT: CD CLADDING |  | 466 | 2022-02-04 | 2023-05-15 | 92557.9 |  | Remaining Units | 93.2 | 1508.5 | 1452.6 | 1412.6 | 617.1 | 2767.5 | 8454 | 5182.5 | 4690.7 | 1328.7 | 16510.4 | 19004.9 | 10970.1 | 2887.9 | 10313.9 | 5363.2
[8 empty] | KEY QT: CD CLADDING |  | 418 | 2022-03-26 | 2023-05-17 | 150592.9 |  | Remaining Units |  | 56.8 | 4096.5 | 9077 | 6714.9 | 6427.7 | 5191.8 | 4983.6 | 10186 | 15271.1 | 22450.7 | 24220 | 15687.6 | 12742.6 | 8429.1 | 5057.5
Activity ID | Activity Name | Original Duration | Start | Finish | Remaining Units | Curve | Spreadsheet Field | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01
Total |  | 932 | 10.04.21 A | 2023-08-30 | 30782898.3 |  | Remaining Units |  |  |  |  | 38277.9 | 335790.4 | 380764.8 | 566648.4 | 677597 | 856921.7 | 1266079 | 1234519 | 1447913.2 | 1850943.9 | 1870230.6 | 1920573.9 | 1932281.1 | 2095738.8 | 2291041.1 | 2241272.6 | 2276198.4 | 2133500.6 | 2070072.5 | 1485515.4 | 855476 | 548076.7 | 227878.8 | 139498.7 | 26183 | 11709.6 | 2195.2 | 311.5
Area Tag Kingisepp-2: 1 Ammonia |  | 752 | 2021-08-09 | 2023-08-30 | 15562994.4 |  | Remaining Units | [6 empty] | 86697 | 345204.1 | 471534.5 | 625342.8 | 903799.5 | 873226.6 | 855491.4 | 1228482 | 1294469.2 | 1339913.2 | 1272024.5 | 1162498.6 | 1019396.9 | 843643.4 | 818554.8 | 635348.5 | 574424.5 | 441711.4 | 330770.5 | 233255.3 | 118346.4 | 65999.3 | 14126.2 | 7146.3 | 1587.6
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 317 | 2021-09-21 | 2022-08-03 | 32000 |  | Remaining Units | 2021-09-01: 659.3; 2021-10-01: 1052.2; 2021-11-01: 2055.5; 2021-12-01: 3683.3; 2022-01-01: 4600.5; 2022-02-01: 4517.6; 2022-03-01: 5056.9; 2022-04-01: 4497.4; 2022-05-01: 3242.4; 2022-06-01: 1688.5; 2022-07-01: 854.6; 2022-08-01: 91.8
KEY QT: ST MAIN STEEL STRUCTURE |  | 543 | 2021-08-24 | 2023-02-17 | 11361823.1 |  | Remaining Units | 2021-08-01: 85317.4; 2021-09-01: 340786.8; 2021-10-01: 465649.7; 2021-11-01: 616789.2; 2021-12-01: 888306.9; 2022-01-01: 848026.3; 2022-02-01: 817383.5; 2022-03-01: 1136123.8; 2022-04-01: 1188017.7; 2022-05-01: 1217984.5; 2022-06-01: 1111917.4; 2022-07-01: 844198; 2022-08-01: 535447.5; 2022-09-01: 420180.8; 2022-10-01: 387239.9; 2022-11-01: 178776.1; 2022-12-01: 111048.5; 2023-01-01: 106935.6; 2023-02-01: 61693.6
KEY QT: SS SECONDARY STEEL |  | 407 | 2022-02-28 | 2023-04-10 | 840908.3 |  | Remaining Units | 2022-02-01: 602; 2022-03-01: 33510.8; 2022-04-01: 38443.9; 2022-05-01: 38538.1; 2022-06-01: 68369; 2022-07-01: 167196.5; 2022-08-01: 218496.6; 2022-09-01: 103253.9; 2022-10-01: 59345.1; 2022-11-01: 53413.4; 2022-12-01: 39682.9; 2023-01-01: 334.3; 2023-02-01: 8022.4; 2023-03-01: 9025.2; 2023-04-01: 2674.1
KEY QT: CD CLADDING |  | 441 | 2022-03-01 | 2023-05-15 | 33149.4 |  | Remaining Units | 2022-03-01: 1908-11-20 12:00; 2022-04-01: 1905-12-03 07:12; 2022-05-01: 1903-03-09 07:12; 2022-06-01: 1902-09-24 21:36; 2022-07-01: 1903-07-03 21:36; 2022-08-01: 1908-05-01 14:24; 2022-09-01: 1911-07-05 16:48; 2022-10-01: 1907-03-20 04:48; 2022-11-01: 1903-06-17 14:24; 2022-12-01: 1902-12-19 21:36; 2023-01-01: 1904-03-17; 2023-02-01: 1900-06-24 21:36; 2023-03-01: 1907-02-21; 2023-04-01: 1912-12-28 12:00; 2023-05-01: 1908-03-06 04:48
KEY QT: EQ EQUIPMENT |  | 475 | 2021-12-01 | 2023-03-20 | 11072 |  | Remaining Units | 2021-12-01: 322.3; 2022-01-01: 293.3; 2022-02-01: 368.6; 2022-03-01: 780.9; 2022-04-01: 925.2; 2022-05-01: 1097.8; 2022-06-01: 1176.1; 2022-07-01: 1183.1; 2022-08-01: 1220.9; 2022-09-01: 1102.1; 2022-10-01: 937.4; 2022-11-01: 743.1; 2022-12-01: 453; 2023-01-01: 284.3; 2023-02-01: 160.9; 2023-03-01: 23.1
KEY QT: SUP SUPPORTS |  | 450 | 2022-02-23 | 2023-05-19 | 826381 |  | Remaining Units | 2022-02-01: 108; 2022-03-01: 667.8; 2022-04-01: 5255.9; 2022-05-01: 14320.4; 2022-06-01: 19677.5; 2022-07-01: 68738.7; 2022-08-01: 106001.1; 2022-09-01: 121164.2; 2022-10-01: 119619.6; 2022-11-01: 111808.5; 2022-12-01: 112769.5; 2023-01-01: 71519.2; 2023-02-01: 37601.7; 2023-03-01: 19211.1; 2023-04-01: 15773.7; 2023-05-01: 2144.1
KEY QT: SB PIPING SB |  | 400 | 2022-04-15 | 2023-05-19 | 61710 |  | Remaining Units | 2022-04-01: 14.7; 2022-05-01: 132.4; 2022-06-01: 176.9; 2022-07-01: 2498.4; 2022-08-01: 6372.3; 2022-09-01: 8914.6; 2022-10-01: 10054.5; 2022-11-01: 10181.7; 2022-12-01: 9757.9; 2023-01-01: 6349.9; 2023-02-01: 3505; 2023-03-01: 2008.7; 2023-04-01: 1629.6; 2023-05-01: 113.3
KEY QT: LBP PIPING LB PREFAB |  | 472 | 2021-08-09 | 2022-11-24 | 255590 |  | Remaining Units | 2021-08-01: 1379.6; 2021-09-01: 3758; 2021-10-01: 4832.6; 2021-11-01: 6458.5; 2021-12-01: 11333.6; 2022-01-01: 18432.9; 2022-02-01: 27113.3; 2022-03-01: 35218.8; 2022-04-01: 36221.9; 2022-05-01: 35420.5; 2022-06-01: 30179.9; 2022-07-01: 18129.7; 2022-08-01: 12865.5; 2022-09-01: 8063.4; 2022-10-01: 4516.9; 2022-11-01: 1665
KEY QT: LBE PIPING LB ERECT |  | 427 | 2022-02-17 | 2023-04-19 | 137625.6 |  | Remaining Units | 2022-02-01: 817.6; 2022-03-01: 3692.8; 2022-04-01: 5696.5; 2022-05-01: 7284.6; 2022-06-01: 13577.6; 2022-07-01: 17686.3; 2022-08-01: 18495.7; 2022-09-01: 15241.8; 2022-10-01: 16152; 2022-11-01: 14737.3; 2022-12-01: 10765.1; 2023-01-01: 5914.1; 2023-02-01: 3203.5; 2023-03-01: 3426; 2023-04-01: 934.7
KEY QT: EC ELECTRICAL CABLES |  | 384 | 2022-05-05 | 2023-05-23 | 746084 |  | Remaining Units | 2022-05-01: 6219.1; 2022-06-01: 11091.2; 2022-07-01: 10385.5; 2022-08-01: 74986.4; 2022-09-01: 93467; 2022-10-01: 99198.5; 2022-11-01: 85116; 2022-12-01: 99026.8; 2023-01-01: 83227.5; 2023-02-01: 73605.8; 2023-03-01: 76628.2; 2023-04-01: 24281.5; 2023-05-01: 8850.5
KEY QT: IC INSTRUMENT CABLES |  | 319 | 2022-07-11 | 2023-05-26 | 890202 |  | Remaining Units | 2022-07-01: 17706.3; 2022-08-01: 30736; 2022-09-01: 59608.5; 2022-10-01: 110176.9; 2022-11-01: 160606.3; 2022-12-01: 160288.4; 2023-01-01: 125913.7; 2023-02-01: 99327.4; 2023-03-01: 74757.6; 2023-04-01: 35542.6; 2023-05-01: 15538.2
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 240 | 2022-10-17 | 2023-06-14 | 100055 |  | Remaining Units | 2022-10-01: 2100.7; 2022-11-01: 8592; 2022-12-01: 13351; 2023-01-01: 12459.2; 2023-02-01: 12028.2; 2023-03-01: 12829.8; 2023-04-01: 13547; 2023-05-01: 22509.8; 2023-06-01: 2637.4
KEY QT: PA PAINTING |  | 631 | 2021-11-13 | 2023-08-05 | 102301 |  | Remaining Units | [9 empty] | 39.6 | 153.4 | 1873.6 | 4580.8 | 10182.6 | 13094.7 | 13924.8 | 12587.2 | 12155.3 | 11390.6 | 7206.1 | 3190.2 | 1002.5 | 1037.3 | 1590.4 | 1735.6 | 2011.7 | 1771 | 1502.9 | 818.5 | 391.7 | 60.5 | 311.5
KEY QT: IN INSULATION |  | 406 | 2022-07-21 | 2023-08-30 | 162292 |  | Remaining Units | 2022-07-01: 38.1; 2022-08-01: 244.9; 2022-09-01: 1220.3; 2022-10-01: 3370.8; 2022-11-01: 7429.1; 2022-12-01: 15159.1; 2023-01-01: 25645.2; 2023-02-01: 29709.5; 2023-03-01: 30725; 2023-04-01: 17445.7; 2023-05-01: 12352.3; 2023-06-01: 10670.3; 2023-07-01: 6754.6; 2023-08-01: 1527.1
KEY QT: MS MASONARY |  | 218 | 2022-04-21 | 2022-11-24 | 1801 |  | Remaining Units | 2022-04-01: 137.2; 2022-05-01: 584.3; 2022-06-01: 584.3; 2022-07-01: 447.1; 2022-08-01: 3.1; 2022-09-01: 16; 2022-10-01: 16; 2022-11-01: 12.9
Area Tag Kingisepp-2: 2 Urea |  | 914 | 10.04.21 A | 2023-08-12 | 15219904 |  | Remaining Units |  |  |  |  | 38277.9 | 335790.4 | 294067.8 | 221444.4 | 206062.5 | 231578.9 | 362279.5 | 361292.3 | 592421.8 | 622461.9 | 575761.4 | 580660.7 | 660256.6 | 933240.3 | 1271644.3 | 1397629.1 | 1457643.6 | 1498152.1 | 1495648.1 | 1043804 | 524705.5 | 314821.3 | 109532.3 | 73499.4 | 12056.8 | 4563.3 | 607.7
KEY QT: UGE UNDERGROUND - EARTHING |  | 406 | 2021-08-07 | 2022-09-16 | 57.8 |  | Remaining Units | 2021-08-01: 2.8; 2021-09-01: 3.4; 2021-10-01: 4.1; 2021-11-01: 4.6; 2021-12-01: 5.2; 2022-01-01: 5.2; 2022-02-01: 4.8; 2022-03-01: 5.4; 2022-04-01: 4.5; 2022-05-01: 4.1; 2022-06-01: 4; 2022-07-01: 4; 2022-08-01: 3.8; 2022-09-01: 1.8
KEY QT: EW EXCAVATION |  | 385 | 10.04.21 A | 2022-04-29 | 161740.6 |  | Remaining Units | 2021-06-01: 36110.1; 2021-07-01: 52269.4; 2021-08-01: 7909.7; 2021-09-01: 904.7; 2021-10-01: 3617.4; 2021-11-01: 2080.5; 2021-12-01: 1794.7; 2022-01-01: 1728.2; 2022-02-01: 16112.2; 2022-03-01: 20459.4; 2022-04-01: 18754.4
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 408 | 2021-07-08 | 2022-08-19 | 17100 |  | Remaining Units | 2021-07-01: 472; 2021-08-01: 494.4; 2021-09-01: 762.2; 2021-10-01: 1346.5; 2021-11-01: 1756.9; 2021-12-01: 2022.7; 2022-01-01: 2032.5; 2022-02-01: 1876.1; 2022-03-01: 1999.2; 2022-04-01: 1674.8; 2022-05-01: 1321.1; 2022-06-01: 686; 2022-07-01: 439.7; 2022-08-01: 215.9
KEY QT: UGG UNDERGROUND - GRAVITY PIPES |  | 643 | 2021-08-07 | 2023-05-11 | 18214.1 |  | Remaining Units | [6 empty] | 258 | 353.3 | 400.4 | 464.1 | 753.5 | 911 | 989.5 | 1320.9 | 1306.1 | 1375.1 | 1375.1 | 1375.1 | 1414.5 | 1272 | 1267.8 | 911 | 946.1 | 495 | 428.4 | 295.9 | 214.9 | 85.9
KEY QT: BF BACKFILLING |  | 463 | 20.07.21 A | 2022-10-26 | 74859.3 |  | Remaining Units | 2021-07-01: 68.9; 2021-08-01: 164.1; 2021-09-01: 1657.7; 2021-10-01: 2808.1; 2021-11-01: 3971.9; 2021-12-01: 3750.6; 2022-01-01: 2775.6; 2022-02-01: 2560; 2022-03-01: 3032.9; 2022-04-01: 4112.9; 2022-05-01: 5291.2; 2022-06-01: 5327.4; 2022-07-01: 5327; 2022-08-01: 4237.4; 2022-09-01: 7925.7; 2022-10-01: 21847.8
KEY QT: FD FOUNDATION |  | 554 | 20.04.21 A | 2022-08-17 | 25654.1 |  | Remaining Units | 2021-06-01: 2167.2; 2021-07-01: 2794.1; 2021-08-01: 2515.8; 2021-09-01: 2402.4; 2021-10-01: 2354; 2021-11-01: 2307.6; 2021-12-01: 2319.2; 2022-01-01: 1578.6; 2022-02-01: 1298.7; 2022-03-01: 1259.7; 2022-04-01: 1353.4; 2022-05-01: 1244.2; 2022-06-01: 1396.8; 2022-07-01: 483.1; 2022-08-01: 179.3
KEY QT: EL ELEVATION |  | 587 | 2021-06-24 | 2023-01-31 | 7319 |  | Remaining Units |  |  |  |  | 0.6 | 344 | 1126 | 984.4 | 812.3 | 826.1 | 440.4 | 426.5 | 454.8 | 386.3 | 393.6 | 329 | 289 | 90.8 | 71.2 | 68.2 | 68.2 | 68.2 | 70.9 | 68.2
KEY QT: PV PAVING |  | 422 | 2022-04-13 | 2023-06-08 | 13232.8 |  | Remaining Units | 2022-04-01: 176.1; 2022-05-01: 229.7; 2022-06-01: 430.6; 2022-07-01: 962.5; 2022-08-01: 1468.9; 2022-09-01: 1529.5; 2022-10-01: 1507.1; 2022-11-01: 1781.3; 2022-12-01: 1757.7; 2023-01-01: 1192.9; 2023-02-01: 598; 2023-03-01: 332.6; 2023-04-01: 449.3; 2023-05-01: 667.7; 2023-06-01: 149
KEY QT: GT GROUTING |  | 583 | 2021-10-14 | 2023-05-19 | 146.1 |  | Remaining Units | 2021-10-01: 3; 2021-11-01: 1; 2021-12-01: 0.3; 2022-01-01: 1.7; 2022-03-01: 0; 2022-04-01: 1.9; 2022-05-01: 1.6; 2022-06-01: 1.9; 2022-07-01: 3.6; 2022-08-01: 5.4; 2022-09-01: 7.7; 2022-10-01: 13.1; 2022-11-01: 11.1; 2022-12-01: 10.8; 2023-01-01: 5.3; 2023-02-01: 18.5; 2023-03-01: 41.7; 2023-04-01: 12; 2023-05-01: 5.5
KEY QT: ST MAIN STEEL STRUCTURE |  | 635 | 2021-07-01 | 2023-03-27 | 12153070.1 |  | Remaining Units | [5 empty] | 279842 | 280543.7 | 212023.9 | 191634.4 | 215450.2 | 343321.9 | 339790.9 | 541326.7 | 534888.4 | 504908.3 | 534404.2 | 607322.2 | 850422.1 | 1141931.5 | 1167045.1 | 1148006.5 | 1140992.3 | 1058396.4 | 640977.2 | 261615.5 | 158226.7
KEY QT: SS SECONDARY STEEL |  | 488 | 2022-01-15 | 2023-05-17 | 1042969.3 |  | Remaining Units | 2022-01-01: 1908.4; 2022-02-01: 15856.2; 2022-03-01: 37800.8; 2022-04-01: 20018.2; 2022-05-01: 10691.4; 2022-06-01: 12316.9; 2022-07-01: 12390.2; 2022-08-01: 26858; 2022-09-01: 94906.9; 2022-10-01: 111189.5; 2022-11-01: 134427.6; 2022-12-01: 171193.5; 2023-01-01: 180084.8; 2023-02-01: 104233.6; 2023-03-01: 43963; 2023-04-01: 40706.4; 2023-05-01: 24423.9
KEY QT: CD CLADDING |  | 418 | 2022-03-26 | 2023-05-17 | 54536.4 |  | Remaining Units | 2022-03-01: 36.7; 2022-04-01: 1785.6; 2022-05-01: 3222; 2022-06-01: 3309.2; 2022-07-01: 3162.6; 2022-08-01: 1446.2; 2022-09-01: 1460.7; 2022-10-01: 3393.1; 2022-11-01: 5277.8; 2022-12-01: 6449.8; 2023-01-01: 6723.6; 2023-02-01: 8471.6; 2023-03-01: 5360.8; 2023-04-01: 2773; 2023-05-01: 1663.8
KEY QT: EQ EQUIPMENT |  | 487 | 2021-12-01 | 2023-04-01 | 5000 |  | Remaining Units | 2021-12-01: 47; 2022-01-01: 147; 2022-02-01: 170.6; 2022-03-01: 287; 2022-04-01: 425; 2022-05-01: 534.2; 2022-06-01: 597.6; 2022-07-01: 617; 2022-08-01: 618.7; 2022-09-01: 526.1; 2022-10-01: 407.2; 2022-11-01: 304.3; 2022-12-01: 164; 2023-01-01: 93.6; 2023-02-01: 51.4; 2023-03-01: 9.1; 2023-04-01: 0.3
KEY QT: SUP SUPPORTS |  | 373 | 2022-05-19 | 2023-05-26 | 273361 |  | Remaining Units | 2022-05-01: 132.1; 2022-06-01: 2573.5; 2022-07-01: 6737.8; 2022-08-01: 17332.7; 2022-09-01: 38448.1; 2022-10-01: 46682.8; 2022-11-01: 44875.8; 2022-12-01: 36687.1; 2023-01-01: 26890.5; 2023-02-01: 17164.7; 2023-03-01: 12928.7; 2023-04-01: 11961.9; 2023-05-01: 10945.2
KEY QT: SB PIPING SB |  | 402 | 2022-04-20 | 2023-05-26 | 22256 |  | Remaining Units | 2022-04-01: 367.1; 2022-05-01: 1133.8; 2022-06-01: 1133.8; 2022-07-01: 1151.7; 2022-08-01: 1688; 2022-09-01: 1620; 2022-10-01: 2179.7; 2022-11-01: 2724.9; 2022-12-01: 2805.4; 2023-01-01: 2570.2; 2023-02-01: 1460.8; 2023-03-01: 1231.8; 2023-04-01: 1140.4; 2023-05-01: 1048.3
KEY QT: LBP PIPING LB PREFAB |  | 471 | 2021-08-03 | 2022-11-16 | 116574.3 |  | Remaining Units | 2021-08-01: 1053.3; 2021-09-01: 2352.3; 2021-10-01: 3082.3; 2021-11-01: 4474.5; 2021-12-01: 6895.9; 2022-01-01: 8117.5; 2022-02-01: 8682.9; 2022-03-01: 15591.3; 2022-04-01: 14286.2; 2022-05-01: 12688; 2022-06-01: 11619.1; 2022-07-01: 11544.6; 2022-08-01: 7061.2; 2022-09-01: 4745.1; 2022-10-01: 3376.3; 2022-11-01: 1003.8
KEY QT: LBE PIPING LB ERECT |  | 492 | 2021-12-21 | 2023-04-26 | 62770.7 |  | Remaining Units | 2021-12-01: 248; 2022-01-01: 669.6; 2022-02-01: 1190.4; 2022-03-01: 2678.5; 2022-04-01: 3025.7; 2022-05-01: 4445.5; 2022-06-01: 4761.8; 2022-07-01: 5456.2; 2022-08-01: 6398.6; 2022-09-01: 7487.9; 2022-10-01: 7060.3; 2022-11-01: 6621.8; 2022-12-01: 6209.5; 2023-01-01: 3077.7; 2023-02-01: 1713.5; 2023-03-01: 1180; 2023-04-01: 545.6
KEY QT: EC ELECTRICAL CABLES |  | 337 | 2022-06-24 | 2023-05-26 | 507733 |  | Remaining Units | 2022-06-01: 3030.6; 2022-07-01: 25155.7; 2022-08-01: 43843.6; 2022-09-01: 42619.3; 2022-10-01: 66783.9; 2022-11-01: 87242.5; 2022-12-01: 96960.4; 2023-01-01: 55711; 2023-02-01: 34836.1; 2023-03-01: 23083.9; 2023-04-01: 16059.1; 2023-05-01: 12407
KEY QT: IC INSTRUMENT CABLES |  | 334 | 2022-07-11 | 2023-06-10 | 516851 |  | Remaining Units | 2022-07-01: 4173.1; 2022-08-01: 14160.8; 2022-09-01: 26052.4; 2022-10-01: 39965.9; 2022-11-01: 58151.2; 2022-12-01: 95004; 2023-01-01: 108765.4; 2023-02-01: 80161.2; 2023-03-01: 56774.6; 2023-04-01: 24537.9; 2023-05-01: 7599.1; 2023-06-01: 1505.4
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 258 | 2022-10-26 | 2023-07-11 | 45179 |  | Remaining Units | 2022-10-01: 203; 2022-11-01: 4699.6; 2022-12-01: 5658.2; 2023-01-01: 6689; 2023-02-01: 7234.6; 2023-03-01: 6391.1; 2023-04-01: 5455.3; 2023-05-01: 5605.1; 2023-06-01: 2527.4; 2023-07-01: 715.9
KEY QT: PA PAINTING |  | 386 | 2021-11-05 | 2022-11-25 | 23430 |  | Remaining Units | 2021-11-01: 241.5; 2021-12-01: 680.1; 2022-01-01: 1160.9; 2022-02-01: 1590; 2022-03-01: 2367.9; 2022-04-01: 2786.8; 2022-05-01: 3338.2; 2022-06-01: 3947.6; 2022-07-01: 3611.7; 2022-08-01: 2565.4; 2022-09-01: 948.9; 2022-10-01: 167.2; 2022-11-01: 23.7
KEY QT: IN INSULATION |  | 387 | 2022-07-22 | 2023-08-12 | 73420 |  | Remaining Units | 2022-07-01: 22.5; 2022-08-01: 110.4; 2022-09-01: 955.1; 2022-10-01: 3395.6; 2022-11-01: 7894.5; 2022-12-01: 11946; 2023-01-01: 10322.6; 2023-02-01: 6717.5; 2023-03-01: 5001.5; 2023-04-01: 5676.3; 2023-05-01: 9047.9; 2023-06-01: 7875; 2023-07-01: 3847.5; 2023-08-01: 607.7
KEY QT: RW RAILWAYS |  | 79 | 2022-10-26 | 2023-01-13 | 2614.4 |  | Remaining Units | 2022-10-01: 80.1; 2022-11-01: 1050.5; 2022-12-01: 1346.7; 2023-01-01: 137
KEY QT: MS MASONARY |  | 321 | 2022-01-28 | 2022-12-14 | 1815 |  | Remaining Units | 2022-01-01: 38.6; 2022-02-01: 308.9; 2022-03-01: 347.5; 2022-04-01: 380.8; 2022-05-01: 275.1; 2022-06-01: 133.6; 2022-07-01: 109.2; 2022-08-01: 32.7; 2022-09-01: 8.5; 2022-10-01: 48.5; 2022-11-01: 90; 2022-12-01: 41.6
Activity ID | Activity Name | Original Duration | Start | Finish | Remaining Units | Curve | Spreadsheet Field | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01
Area Tag Kingisepp-2: 1 Ammonia |  | 752 | 2021-08-09 | 2023-08-30 | 5819735.3 |  | Remaining Units | [6 empty] | 11232.7 | 23623.8 | 30819.4 | 45466.4 | 85157.9 | 131044 | 174729.5 | 254432.8 | 297421.1 | 340133.6 | 360095.2 | 378414.7 | 436369.8 | 444589.3 | 490678.3 | 496363.2 | 458935.1 | 389965 | 314002.5 | 270080.1 | 158943.1 | 100713.1 | 70722.3 | 46208.6 | 9593.7 | 1803.9
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 317 | 2021-09-21 | 2022-08-03 | 23228.5 |  | Remaining Units | 2021-09-01: 92.2; 2021-10-01: 665.8; 2021-11-01: 1423.1; 2021-12-01: 2284.2; 2022-01-01: 3570.3; 2022-02-01: 3853.2; 2022-03-01: 4282.6; 2022-04-01: 3382.5; 2022-05-01: 1820.7; 2022-06-01: 1300.1; 2022-07-01: 502.5; 2022-08-01: 51.2
KEY QT: ST MAIN STEEL STRUCTURE |  | 543 | 2021-08-24 | 2023-02-17 | 643191.4 |  | Remaining Units | 2021-08-01: 2875.6; 2021-09-01: 12667.3; 2021-10-01: 19289.4; 2021-11-01: 22806.4; 2021-12-01: 39454.8; 2022-01-01: 45655.4; 2022-02-01: 49078.7; 2022-03-01: 68372.2; 2022-04-01: 76004.2; 2022-05-01: 71707.8; 2022-06-01: 61818.1; 2022-07-01: 53139.8; 2022-08-01: 42561.3; 2022-09-01: 28182.6; 2022-10-01: 23546.9; 2022-11-01: 10680.8; 2022-12-01: 6094.9; 2023-01-01: 5869.2; 2023-02-01: 3386.1
KEY QT: SS SECONDARY STEEL |  | 407 | 2022-02-28 | 2023-04-10 | 67209.2 |  | Remaining Units | 2022-02-01: 14.6; 2022-03-01: 1718.5; 2022-04-01: 2514.9; 2022-05-01: 3012.8; 2022-06-01: 6282.5; 2022-07-01: 14110.3; 2022-08-01: 17406.3; 2022-09-01: 7553.8; 2022-10-01: 4089.6; 2022-11-01: 3711.1; 2022-12-01: 2728.6; 2023-01-01: 67.8; 2023-02-01: 1626.4; 2023-03-01: 1829.7; 2023-04-01: 542.1
KEY QT: CD CLADDING |  | 466 | 2022-02-04 | 2023-05-15 | 92557.9 |  | Remaining Units | 2022-02-01: 93.2; 2022-03-01: 1508.5; 2022-04-01: 1452.6; 2022-05-01: 1412.6; 2022-06-01: 617.1; 2022-07-01: 2767.5; 2022-08-01: 8454; 2022-09-01: 5182.5; 2022-10-01: 4690.7; 2022-11-01: 1328.7; 2022-12-01: 16510.4; 2023-01-01: 19004.9; 2023-02-01: 10970.1; 2023-03-01: 2887.9; 2023-04-01: 10313.9; 2023-05-01: 5363.2
KEY QT: EQ EQUIPMENT |  | 475 | 2021-12-01 | 2023-03-20 | 568809.2 |  | Remaining Units | 2021-12-01: 4737.1; 2022-01-01: 13535.8; 2022-02-01: 20205.5; 2022-03-01: 30641.9; 2022-04-01: 40897.8; 2022-05-01: 58481.5; 2022-06-01: 68780.9; 2022-07-01: 70951.4; 2022-08-01: 72836.3; 2022-09-01: 60463.2; 2022-10-01: 47842.4; 2022-11-01: 30284.5; 2022-12-01: 24643; 2023-01-01: 15926.1; 2023-02-01: 6660.9; 2023-03-01: 1920.8
KEY QT: SUP SUPPORTS |  | 450 | 2022-02-23 | 2023-05-19 | 213742.8 |  | Remaining Units | 2022-02-01: 31.6; 2022-03-01: 194.8; 2022-04-01: 1526.9; 2022-05-01: 4115.7; 2022-06-01: 5526.2; 2022-07-01: 17172.5; 2022-08-01: 27355.6; 2022-09-01: 31569.8; 2022-10-01: 31125.1; 2022-11-01: 28788.1; 2022-12-01: 28979; 2023-01-01: 17698.4; 2023-02-01: 9598.5; 2023-03-01: 5212.6; 2023-04-01: 4278.8; 2023-05-01: 569
KEY QT: SB PIPING SB |  | 400 | 2022-04-15 | 2023-05-19 | 334830.2 |  | Remaining Units | 2022-04-01: 79.6; 2022-05-01: 718.7; 2022-06-01: 960; 2022-07-01: 13556.3; 2022-08-01: 34575.3; 2022-09-01: 48369.6; 2022-10-01: 54554.4; 2022-11-01: 55244.4; 2022-12-01: 52945.2; 2023-01-01: 34453.7; 2023-02-01: 19017.7; 2023-03-01: 10898.8; 2023-04-01: 8842; 2023-05-01: 614.6
KEY QT: LBP PIPING LB PREFAB |  | 472 | 2021-08-09 | 2022-11-24 | 843198.3 |  | Remaining Units | 2021-08-01: 8357.2; 2021-09-01: 10864.3; 2021-10-01: 10864.3; 2021-11-01: 21155; 2021-12-01: 38364.1; 2022-01-01: 64420.5; 2022-02-01: 89417; 2022-03-01: 114956.8; 2022-04-01: 119132.3; 2022-05-01: 116853.1; 2022-06-01: 99564.2; 2022-07-01: 59810.3; 2022-08-01: 42443.7; 2022-09-01: 26601.5; 2022-10-01: 14901.4; 2022-11-01: 5492.7
KEY QT: LBE PIPING LB ERECT |  | 427 | 2022-02-17 | 2023-04-19 | 431091 |  | Remaining Units | 2022-02-01: 2561; 2022-03-01: 11567.1; 2022-04-01: 17843.4; 2022-05-01: 22818; 2022-06-01: 42530; 2022-07-01: 55399.6; 2022-08-01: 57935; 2022-09-01: 47742.5; 2022-10-01: 50593.6; 2022-11-01: 46162.4; 2022-12-01: 33719.9; 2023-01-01: 18524.9; 2023-02-01: 10034.6; 2023-03-01: 10731.3; 2023-04-01: 2927.7
KEY QT: TRA TRAYS |  | 399 | 2022-04-05 | 2023-05-09 | 249677.7 |  | Remaining Units | 2022-04-01: 4234.9; 2022-05-01: 16743.6; 2022-06-01: 28933; 2022-07-01: 32676.6; 2022-08-01: 36226.8; 2022-09-01: 37603.3; 2022-10-01: 31471.8; 2022-11-01: 22242.4; 2022-12-01: 18488.4; 2023-01-01: 13057.5; 2023-02-01: 5223.2; 2023-03-01: 2066.5; 2023-04-01: 614.9; 2023-05-01: 94.8
KEY QT: EC ELECTRICAL CABLES |  | 384 | 2022-05-05 | 2023-05-23 | 248603.9 |  | Remaining Units | 2022-05-01: 468.3; 2022-06-01: 2294.3; 2022-07-01: 4211.6; 2022-08-01: 15264; 2022-09-01: 38175.1; 2022-10-01: 42479.3; 2022-11-01: 32335.4; 2022-12-01: 28143.8; 2023-01-01: 33463.3; 2023-02-01: 28478.8; 2023-03-01: 17371.5; 2023-04-01: 4868.4; 2023-05-01: 1050.1
KEY QT: TER ELECTRICAL TERMINATIONS |  | 289 | 2022-09-01 | 2023-06-17 | 171587.2 |  | Remaining Units | 2022-09-01: 4023.6; 2022-10-01: 19859.6; 2022-11-01: 36511.8; 2022-12-01: 40687.3; 2023-01-01: 26145; 2023-02-01: 10101.1; 2023-03-01: 16488.4; 2023-04-01: 12539; 2023-05-01: 4769.2; 2023-06-01: 462.2
KEY QT: EEQ ELECTRICAL EQ |  | 315 | 2022-07-19 | 2023-05-29 | 30706.1 |  | Remaining Units | 2022-07-01: 105; 2022-08-01: 6710; 2022-09-01: 6818.2; 2022-10-01: 3335.4; 2022-11-01: 4431.6; 2022-12-01: 2150.3; 2023-01-01: 642.3; 2023-02-01: 1025.7; 2023-03-01: 3999.7; 2023-04-01: 1442; 2023-05-01: 45.8
KEY QT: OEL OTHER ELECRICAL |  | 357 | 2022-06-01 | 2023-05-23 | 110144.9 |  | Remaining Units | 2022-06-01: 1901-02-25 04:48; 2022-07-01: 1918-03-23 09:36; 2022-08-01: 1951-04-13 09:36; 2022-09-01: 1982-05-02; 2022-10-01: 1985-10-02 12:00; 2022-11-01: 1927-03-12 19:12; 2022-12-01: 1917-04-14 14:24; 2023-01-01: 1913-05-02 07:12; 2023-02-01: 1902-10-10 14:24; 2023-03-01: 1901-04-09 21:36; 2023-04-01: 1900-09-18 21:36; 2023-05-01: 1900-03-15 07:12
KEY QT: ETH EARTHING |  | 325 | 2022-05-09 | 2023-03-29 | 62353.4 |  | Remaining Units | 2022-05-01: 273.3; 2022-06-01: 1425.6; 2022-07-01: 4524.6; 2022-08-01: 6443.7; 2022-09-01: 6155.3; 2022-10-01: 7679.1; 2022-11-01: 20116.3; 2022-12-01: 6647; 2023-01-01: 6975.5; 2023-02-01: 2083; 2023-03-01: 30
KEY QT: IC INSTRUMENT CABLES |  | 319 | 2022-07-11 | 2023-05-26 | 243905 |  | Remaining Units | 2022-07-01: 4461.6; 2022-08-01: 7745.9; 2022-09-01: 15022.2; 2022-10-01: 27964; 2022-11-01: 48352.9; 2022-12-01: 51814.8; 2023-01-01: 31768.9; 2023-02-01: 25042.5; 2023-03-01: 18850.1; 2023-04-01: 8962.4; 2023-05-01: 3919.6
KEY QT: FIN FIELD INSTRUMENTS [INCL. F&G] |  | 254 | 2022-08-02 | 2023-04-12 | 85894.9 |  | Remaining Units | 2022-08-01: 4334.9; 2022-09-01: 7771.6; 2022-10-01: 13718.3; 2022-11-01: 16586.7; 2022-12-01: 17358.9; 2023-01-01: 13923; 2023-02-01: 7740.3; 2023-03-01: 3696.4; 2023-04-01: 764.7
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 240 | 2022-10-17 | 2023-06-14 | 58681.7 |  | Remaining Units | 2022-10-01: 1397.1; 2022-11-01: 9900.5; 2022-12-01: 11561.3; 2023-01-01: 5993; 2023-02-01: 5701.1; 2023-03-01: 6081; 2023-04-01: 6359.7; 2023-05-01: 10457.1; 2023-06-01: 1230.9
KEY QT: OIN OTHER INSTRMENTATION |  | 353 | 2022-08-08 | 2023-07-26 | 289964.8 |  | Remaining Units | 2022-08-01: 4169.2; 2022-09-01: 10386.3; 2022-10-01: 47369.9; 2022-11-01: 70826.4; 2022-12-01: 37461; 2023-01-01: 19369.9; 2023-02-01: 21613.2; 2023-03-01: 25547.9; 2023-04-01: 22137.5; 2023-05-01: 18804; 2023-06-01: 9394.2; 2023-07-01: 2885.3
KEY QT: PA PAINTING |  | 644 | 2021-11-13 | 2023-08-18 | 298112.6 |  | Remaining Units | [9 empty] | 81.9 | 317.6 | 3862 | 9474.6 | 21190.4 | 27771.6 | 30338.7 | 28272.2 | 29472.7 | 32199.9 | 27782.3 | 19889.1 | 13945.5 | 8405.2 | 8433.9 | 12870.2 | 11179.6 | 5270.4 | 3487.3 | 2014.2 | 1684.2 | 168.9
KEY QT: IN INSULATION |  | 406 | 2022-07-21 | 2023-08-30 | 712902 |  | Remaining Units | 2022-07-01: 106.4; 2022-08-01: 679.8; 2022-09-01: 3837.4; 2022-10-01: 11572.6; 2022-11-01: 28456.8; 2022-12-01: 63829.7; 2023-01-01: 113306.5; 2023-02-01: 131380.8; 2023-03-01: 130767.6; 2023-04-01: 68816.6; 2023-05-01: 51463.1; 2023-06-01: 57620.7; 2023-07-01: 41639.2; 2023-08-01: 9424.7; 2023-09-01: 1803.9
KEY QT: MS MASONARY |  | 317 | 2022-04-21 | 2023-03-03 | 39342.7 |  | Remaining Units | 2022-04-01: 2580.4; 2022-05-01: 11368.7; 2022-06-01: 11368.7; 2022-07-01: 8788.3; 2022-08-01: 245.3; 2022-09-01: 1275.6; 2022-10-01: 1275.6; 2022-11-01: 1030.3; 2022-12-01: 451.9; 2023-01-01: 469.9; 2023-02-01: 433.8; 2023-03-01: 54.2
Area Tag Kingisepp-2: 2 Urea |  | 914 | 10.04.21 A | 2023-08-12 | 5631412.2 |  | Remaining Units |  |  |  |  | 120940.2 | 146141.7 | 192420.1 | 157916.7 | 145413.4 | 159308.1 | 185369.1 | 162457.8 | 157064.4 | 238629 | 223044.1 | 265139.2 | 269324.3 | 270446.8 | 296713.5 | 345847 | 383996.8 | 442519.9 | 444162 | 358873.3 | 255211.8 | 173894.6 | 88596.9 | 85587 | 47995.2 | 12500.8 | 1898.4
KEY QT: UGE UNDERGROUND - EARTHING |  | 406 | 2021-08-07 | 2022-09-16 | 104385.7 |  | Remaining Units | 2021-08-01: 5143; 2021-09-01: 6404.5; 2021-10-01: 7289.3; 2021-11-01: 8147; 2021-12-01: 9312.5; 2022-01-01: 9236; 2022-02-01: 8525.5; 2022-03-01: 9550.4; 2022-04-01: 8247.5; 2022-05-01: 7462.8; 2022-06-01: 7287.9; 2022-07-01: 7287.9; 2022-08-01: 7062.7; 2022-09-01: 3428.7
KEY QT: EW EXCAVATION |  | 385 | 10.04.21 A | 2022-04-29 | 24925.9 |  | Remaining Units | 2021-06-01: 10248.2; 2021-07-01: 9358.8; 2021-08-01: 1112.3; 2021-09-01: 498.6; 2021-10-01: 803.8; 2021-11-01: 364.5; 2021-12-01: 314.4; 2022-01-01: 302.7; 2022-02-01: 579.8; 2022-03-01: 700.5; 2022-04-01: 642.1
KEY QT: UGP UNDERGROUND - PRESSURE PIPES |  | 408 | 2021-07-08 | 2022-08-19 | 23445.8 |  | Remaining Units | 2021-07-01: 187.6; 2021-08-01: 653.8; 2021-09-01: 1058.4; 2021-10-01: 1428.2; 2021-11-01: 2392.8; 2021-12-01: 3058.7; 2022-01-01: 3274.4; 2022-02-01: 3022.5; 2022-03-01: 2967.6; 2022-04-01: 2199.9; 2022-05-01: 1412.1; 2022-06-01: 1010.2; 2022-07-01: 552; 2022-08-01: 227.8
KEY QT: UGG UNDERGROUND - GRAVITY PIPES |  | 643 | 2021-08-07 | 2023-05-11 | 17823.6 |  | Remaining Units | [6 empty] | 81.5 | 151.3 | 388.2 | 487.8 | 629.2 | 689.7 | 885.8 | 1345 | 1389.8 | 1581.2 | 1581.2 | 1581.2 | 1604.6 | 1295.2 | 1288.2 | 689.7 | 716.2 | 501.8 | 450.3 | 259.5 | 161.7 | 64.7
KEY QT: BF BACKFILLING |  | 463 | 20.07.21 A | 2022-10-26 | 38166.4 |  | Remaining Units | 2021-07-01: 89.2; 2021-08-01: 211.5; 2021-09-01: 1703.5; 2021-10-01: 1478; 2021-11-01: 1914.1; 2021-12-01: 2256.8; 2022-01-01: 2610.1; 2022-02-01: 1084.7; 2022-03-01: 1620.5; 2022-04-01: 2930.4; 2022-05-01: 3393.9; 2022-06-01: 3185.7; 2022-07-01: 3185.6; 2022-08-01: 3083.3; 2022-09-01: 3573.2; 2022-10-01: 5845.9
KEY QT: FD FOUNDATION |  | 593 | 20.04.21 A | 2022-09-26 | 1000308.3 |  | Remaining Units | 2021-06-01: 110683.4; 2021-07-01: 123832.1; 2021-08-01: 139764; 2021-09-01: 108440.3; 2021-10-01: 95146.7; 2021-11-01: 96238.2; 2021-12-01: 99694.2; 2022-01-01: 57834.9; 2022-02-01: 31865.2; 2022-03-01: 54448.2; 2022-04-01: 20478.4; 2022-05-01: 32621.6; 2022-06-01: 25947.1; 2022-07-01: 2397.3; 2022-08-01: 667.5; 2022-09-01: 249.3
KEY QT: EL ELEVATION |  | 418 | 2021-06-24 | 2022-08-15 | 114357.3 |  | Remaining Units | 2021-06-01: 8.6; 2021-07-01: 38.6; 2021-08-01: 21040; 2021-09-01: 16419.5; 2021-10-01: 11006; 2021-11-01: 12120.1; 2021-12-01: 7237.9; 2022-01-01: 7121.1; 2022-02-01: 7984.2; 2022-03-01: 8938.1; 2022-04-01: 8637; 2022-05-01: 6948.2; 2022-06-01: 6138.2; 2022-07-01: 707.4; 2022-08-01: 12.4
KEY QT: PV PAVING |  | 422 | 2022-04-13 | 2023-06-08 | 78203.9 |  | Remaining Units | 2022-04-01: 2146.4; 2022-05-01: 3487.9; 2022-06-01: 3683.4; 2022-07-01: 5544.2; 2022-08-01: 6359.8; 2022-09-01: 7621.1; 2022-10-01: 7202.9; 2022-11-01: 7751.3; 2022-12-01: 8155.2; 2023-01-01: 8092.3; 2023-02-01: 6260.8; 2023-03-01: 4219.5; 2023-04-01: 2556.9; 2023-05-01: 4225.9; 2023-06-01: 896.1
KEY QT: FSH FINISHING |  | 459 | 2022-03-30 | 2023-07-01 | 210460 |  | Remaining Units | 2022-03-01: 540.9; 2022-04-01: 7032.3; 2022-05-01: 7032.3; 2022-06-01: 8059; 2022-07-01: 4001.9; 2022-08-01: 1066.2; 2022-09-01: 39.5; 2022-12-01: 18803.5; 2023-01-01: 34975.9; 2023-02-01: 56194.4; 2023-03-01: 44133.1; 2023-04-01: 3393.3; 2023-05-01: 7750.1; 2023-06-01: 16791.8; 2023-07-01: 645.8
KEY QT: GT GROUTING |  | 583 | 2021-10-14 | 2023-05-19 | 18540.6 |  | Remaining Units | 2021-10-01: 377.9; 2021-11-01: 126; 2021-12-01: 38; 2022-01-01: 215.5; 2022-03-01: 3.2; 2022-04-01: 238.5; 2022-05-01: 197.5; 2022-06-01: 237.2; 2022-07-01: 454.2; 2022-08-01: 682.7; 2022-09-01: 1015.7; 2022-10-01: 1662.5; 2022-11-01: 1398.4; 2022-12-01: 1366.7; 2023-01-01: 673; 2023-02-01: 2329.8; 2023-03-01: 5278.5; 2023-04-01: 1548; 2023-05-01: 697.2
KEY QT: ST MAIN STEEL STRUCTURE |  | 686 | 2021-07-01 | 2023-05-17 | 607328.5 |  | Remaining Units | [5 empty] | 12635.4 | 13502.2 | 10786.3 | 10786.3 | 10786.3 | 17434.1 | 18843.7 | 27573.3 | 25199.6 | 23448.7 | 25189.1 | 25967.4 | 42843.9 | 60960.5 | 58702.7 | 57749.1 | 57397.8 | 53270.3 | 32353.4 | 13333 | 8183.3 | 239 | 143.4
KEY QT: SS SECONDARY STEEL |  | 488 | 2022-01-15 | 2023-05-17 | 96788.2 |  | Remaining Units | 2022-01-01: 468; 2022-02-01: 1572.2; 2022-03-01: 2161.6; 2022-04-01: 1109.8; 2022-05-01: 727.3; 2022-06-01: 866; 2022-07-01: 871.7; 2022-08-01: 2414; 2022-09-01: 12406.7; 2022-10-01: 13424.5; 2022-11-01: 14037.8; 2022-12-01: 16641.1; 2023-01-01: 16013.3; 2023-02-01: 7255.1; 2023-03-01: 2747.9; 2023-04-01: 2544.4; 2023-05-01: 1526.6
KEY QT: CD CLADDING |  | 418 | 2022-03-26 | 2023-05-17 | 150592.9 |  | Remaining Units | 2022-03-01: 56.8; 2022-04-01: 4096.5; 2022-05-01: 9077; 2022-06-01: 6714.9; 2022-07-01: 6427.7; 2022-08-01: 5191.8; 2022-09-01: 4983.6; 2022-10-01: 10186; 2022-11-01: 15271.1; 2022-12-01: 22450.7; 2023-01-01: 24220; 2023-02-01: 15687.6; 2023-03-01: 12742.6; 2023-04-01: 8429.1; 2023-05-01: 5057.5
KEY QT: EQ EQUIPMENT |  | 487 | 2021-12-01 | 2023-04-01 | 350996.7 |  | Remaining Units | 2021-12-01: 2198.6; 2022-01-01: 8578; 2022-02-01: 11240.5; 2022-03-01: 15270.4; 2022-04-01: 17473.4; 2022-05-01: 19607.3; 2022-06-01: 22961.7; 2022-07-01: 27101.2; 2022-08-01: 36939; 2022-09-01: 36604; 2022-10-01: 37731.4; 2022-11-01: 36337.7; 2022-12-01: 28282.4; 2023-01-01: 26441.4; 2023-02-01: 19994.3; 2023-03-01: 4084.4; 2023-04-01: 151.3
KEY QT: SUP SUPPORTS |  | 373 | 2022-05-19 | 2023-05-26 | 77055.1 |  | Remaining Units | 2022-05-01: 38.1; 2022-06-01: 752.5; 2022-07-01: 1959.6; 2022-08-01: 5162; 2022-09-01: 11354.4; 2022-10-01: 13612.5; 2022-11-01: 13033.6; 2022-12-01: 10402.6; 2023-01-01: 7276.4; 2023-02-01: 4508.7; 2023-03-01: 3231.8; 2023-04-01: 2989.6; 2023-05-01: 2733.2
KEY QT: SB PIPING SB |  | 402 | 2022-04-20 | 2023-05-26 | 215604.7 |  | Remaining Units | 2022-04-01: 3556.5; 2022-05-01: 10983.4; 2022-06-01: 10983.4; 2022-07-01: 11157.6; 2022-08-01: 16352.1; 2022-09-01: 15694.1; 2022-10-01: 21115.8; 2022-11-01: 26397.8; 2022-12-01: 27177.5; 2023-01-01: 24898.5; 2023-02-01: 14151.9; 2023-03-01: 11933.4; 2023-04-01: 11047.1; 2023-05-01: 10155.6
KEY QT: LBP PIPING LB PREFAB |  | 471 | 2021-08-03 | 2022-11-16 | 679398 |  | Remaining Units | 2021-08-01: 10911.7; 2021-09-01: 12454.4; 2021-10-01: 16708.9; 2021-11-01: 25966.8; 2021-12-01: 39632.1; 2022-01-01: 45713.8; 2022-02-01: 50604.2; 2022-03-01: 90866.4; 2022-04-01: 83260.2; 2022-05-01: 73946.2; 2022-06-01: 67716.2; 2022-07-01: 67282.4; 2022-08-01: 41152.8; 2022-09-01: 27654.6; 2022-10-01: 19677.3; 2022-11-01: 5850
KEY QT: LBE PIPING LB ERECT |  | 492 | 2021-12-21 | 2023-04-26 | 352989.8 |  | Remaining Units | 2021-12-01: 1394.7; 2022-01-01: 3765.6; 2022-02-01: 6694.4; 2022-03-01: 15062.4; 2022-04-01: 17014.9; 2022-05-01: 24999.4; 2022-06-01: 26777.6; 2022-07-01: 30682.6; 2022-08-01: 35982.4; 2022-09-01: 42108.2; 2022-10-01: 39703.5; 2022-11-01: 37237.5; 2022-12-01: 34919.2; 2023-01-01: 17307.7; 2023-02-01: 9635.9; 2023-03-01: 6635.5; 2023-04-01: 3068.3
KEY QT: TRA TRAYS |  | 386 | 2022-03-22 | 2023-04-11 | 209116.7 |  | Remaining Units | 2022-03-01: 1694; 2022-04-01: 6885.7; 2022-05-01: 17544.8; 2022-06-01: 26485; 2022-07-01: 27429.2; 2022-08-01: 21960.8; 2022-09-01: 19862.5; 2022-10-01: 21113.2; 2022-11-01: 20292; 2022-12-01: 20938; 2023-01-01: 15405.8; 2023-02-01: 7070.3; 2023-03-01: 2217.9; 2023-04-01: 217.7
KEY QT: EC ELECTRICAL CABLES |  | 337 | 2022-06-24 | 2023-05-26 | 207385.8 |  | Remaining Units | 2022-06-01: 945.8; 2022-07-01: 2354.9; 2022-08-01: 8012.6; 2022-09-01: 16292; 2022-10-01: 28994.5; 2022-11-01: 49786.7; 2022-12-01: 39520.9; 2023-01-01: 25280.7; 2023-02-01: 16721.5; 2023-03-01: 12038.5; 2023-04-01: 5679.3; 2023-05-01: 1758.4
KEY QT: TER ELECTRICAL TERMINATIONS |  | 255 | 2022-10-10 | 2023-06-21 | 103100.4 |  | Remaining Units | 2022-10-01: 3625.6; 2022-11-01: 10751.4; 2022-12-01: 21124; 2023-01-01: 22298.3; 2023-02-01: 14569.5; 2023-03-01: 9453.8; 2023-04-01: 9196.3; 2023-05-01: 10040.8; 2023-06-01: 2040.8
KEY QT: EEQ ELECTRICAL EQ |  | 267 | 2022-06-24 | 2023-03-17 | 42382.4 |  | Remaining Units | 2022-06-01: 76.5; 2022-07-01: 212.2; 2022-08-01: 1118.8; 2022-09-01: 8154.1; 2022-10-01: 6842.4; 2022-11-01: 11127.3; 2022-12-01: 6251.4; 2023-01-01: 3309.2; 2023-02-01: 4327.6; 2023-03-01: 962.8
KEY QT: OEL OTHER ELECRICAL |  | 277 | 2022-05-14 | 2023-02-14 | 56167.9 |  | Remaining Units | 2022-05-01: 248.9; 2022-06-01: 1419.6; 2022-07-01: 7990.4; 2022-08-01: 11951.6; 2022-09-01: 11407.2; 2022-10-01: 14654.2; 2022-11-01: 6407.3; 2022-12-01: 1606.5; 2023-01-01: 429.2; 2023-02-01: 53.1
KEY QT: ETH EARTHING |  | 299 | 2022-03-24 | 2023-01-16 | 48090 |  | Remaining Units | 2022-03-01: 111.3; 2022-04-01: 1173.9; 2022-05-01: 2755.4; 2022-06-01: 2440.9; 2022-07-01: 1472.8; 2022-08-01: 1162.9; 2022-09-01: 6974.7; 2022-10-01: 8678.7; 2022-11-01: 16185.9; 2022-12-01: 6433.7; 2023-01-01: 699.6
KEY QT: IC INSTRUMENT CABLES |  | 334 | 2022-07-11 | 2023-06-10 | 106242.5 |  | Remaining Units | 2022-07-01: 860.7; 2022-08-01: 2920.7; 2022-09-01: 5374.5; 2022-10-01: 8257.8; 2022-11-01: 11991.2; 2022-12-01: 19492.5; 2023-01-01: 22283.3; 2023-02-01: 16449.1; 2023-03-01: 11674.5; 2023-04-01: 5054.6; 2023-05-01: 1571.3; 2023-06-01: 312.1
KEY QT: ITE INSTRUMENT TERMINATIONS |  | 258 | 2022-10-26 | 2023-07-11 | 23136.8 |  | Remaining Units | 2022-10-01: 189.5; 2022-11-01: 903.1; 2022-12-01: 2891.4; 2023-01-01: 4318.8; 2023-02-01: 4140.8; 2023-03-01: 4659.4; 2023-04-01: 3565.9; 2023-05-01: 1892.7; 2023-06-01: 481.1; 2023-07-01: 94.2
KEY QT: OIN OTHER INSTRMENTATION |  | 374 | 2022-08-02 | 2023-08-10 | 299951 |  | Remaining Units | 2022-08-01: 14563.9; 2022-09-01: 44780.5; 2022-10-01: 46244.7; 2022-11-01: 52415.8; 2022-12-01: 45294.6; 2023-01-01: 31540.4; 2023-02-01: 19884.7; 2023-03-01: 13516.4; 2023-04-01: 11207.2; 2023-05-01: 13029.8; 2023-06-01: 5899.8; 2023-07-01: 1302; 2023-08-01: 271.2
KEY QT: PA PAINTING |  | 616 | 2021-11-05 | 2023-07-13 | 94031.2 |  | Remaining Units | [9 empty] | 764.6 | 2167.9 | 3791 | 5325.4 | 7972.1 | 9441.5 | 11430.5 | 13681.7 | 12544.6 | 8895 | 3349.5 | 1301.5 | 2160.4 | 1773.8 | 2431.4 | 2037.5 | 721 | 1511.2 | 968.2 | 1240 | 522.2
KEY QT: IN INSULATION |  | 387 | 2022-07-22 | 2023-08-12 | 209359.5 |  | Remaining Units | 2022-07-01: 61.9; 2022-08-01: 304; 2022-09-01: 2687.2; 2022-10-01: 10030.8; 2022-11-01: 23273.9; 2022-12-01: 35258.1; 2023-01-01: 30482.2; 2023-02-01: 20155.8; 2023-03-01: 15200.7; 2023-04-01: 16035.9; 2023-05-01: 23971.6; 2023-06-01: 20333.6; 2023-07-01: 9936.6; 2023-08-01: 1627.2
KEY QT: RW RAILWAYS |  | 79 | 2022-10-26 | 2023-01-13 | 51315.9 |  | Remaining Units | 2022-10-01: 3678.9; 2022-11-01: 19620.8; 2022-12-01: 20375.4; 2023-01-01: 7640.8
KEY QT: MS MASONARY |  | 321 | 2022-01-28 | 2022-12-14 | 19760.7 |  | Remaining Units | 2022-01-01: 13.3; 2022-02-01: 106.6; 2022-03-01: 119.9; 2022-04-01: 1640.4; 2022-05-01: 4454.3; 2022-06-01: 4405.5; 2022-07-01: 3481.8; 2022-08-01: 901.9; 2022-09-01: 233.8; 2022-10-01: 1185.5; 2022-11-01: 2201.6; 2022-12-01: 1016.1
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3 | 106.6 | 119.9 | 4220.8 | 15823 | 15774.2 | 12270.1 | 1147.2 | 1509.4 | 2461.1 | 3231.9 | 1468 | 469.9 | 433.8 | 54.2 | 0 | 0 | 0 | 0 | 0